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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.
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	Participant signature
	



	Assessor name
	Brett Stoward

	

	

	Assessor signature
	



	Date
	4/12/2018




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	In Queensland, individuals and companies must hold a QBCC licence to carry out:
Any building work valued over $3,300
Building work valued over $1,100 where it involves Hydraulic Services Design
Building work of any value where it involves:
Drainage
Plumbing and Drainage
Gas Fitting
Termite Management – Chemical
Fire Protection
Completed Residential Building Inspection
Building Design – Low Rise, Medium Rise and Open
Site Classification
	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	After agreeing to the connection offer, the electrical contractor will prepare the premises for connection
The electrical contractor will submit an Electrical Work Request (EWR) to the Distribution Network Service Provider once the work is complete
A copy of the EWR will be sent to the client’s preferred electricity retailer
Once all forms are received, the Distribution Network Service Provider will visit the premises to perform the requested work
The Distribution Network Service Provider must adhere to timeframes for new connections (e.g. Energex will attend the property within 5 business days)

Timeframes are dependent on network availability, access requirements, traffic control requirements or any other impacts that are outside of the control of your Distribution Network Service Provider

	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	Submit a Water Approval application.
Water and sewerage connection approvals are customised for all scales of development from a new house to a large factory or multi-stage residential sub-division
Where developers are proposing to connect to our water and sewerage services, councils will require evidence that a connection is available 
Generally the evidence required, and therefore the relative timing of the two approvals, will depend on the complexity of the proposed development and the likely availability of services

Standard connections for simple residential developments are usually completed within five (5) days

	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	Section J
	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Reduced impact on the environment by sourcing items locally and buying in bulk
	

	
	Client benefit
	Reduce energy bills
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Excavation

	Prepares the site for building by removing all vegetation and excavating footings.

	

	
	Electrician

	Arranges electricity to be connected; places wiring for lighting and power cables; Fixes switches, installs power points, wires electrical systems.

	

	
	Plumbing

	Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected.

	

	
	Steelfixing

	Installs reinforcing steel to improve the strength of concrete.

	

	
	Gas fitting

	Installs formwork and boxing; pours concrete (e.g. slabs).

	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	3
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	4
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Depending on the nature of the land, there may be soil testing, site-levelling and clearing undertaken prior to actual construction.
	

	
	
	Duration
	Varies
	

	
	2: Slab or base stage
	Trades
	It includes measuring out the design on the site, pouring the footings, under slab drainage, moisture barrier and special mesh for termite protection.
	

	
	
	Duration
	1-2 weeks
	

	
	3: Frame stage
	Trades
	This includes the installation of your internal and external support structure, along with walls, conduit for electrical and plumbing, the roof frame and sheeting, gutters and insulation.
	

	
	
	Duration
	3-4 weeks
	

	
	4: Lockup stage
	Trades
	You can literally start “locking up” the property because your windows, doors and remaining walls will be installed. It’s also safe for plumbers, electricians, cabinet makers and other tradesman to begin fitting out the property.
	

	
	
	Duration
	4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Plumbing, electrical (including lights and power points) and other fixtures and fittings will be installed. The design features that make the property a home will also be added such as cornices, tiling, cabinets and shelving, reveals and architraves.
	

	
	
	Duration
	5-6 weeks
	

	
	6: Practical completion stage
	Trades
	This is basically where all painting, installations and detailing have been completed and you’re effectively ready to move in.
	

	
	
	Duration
	7-8 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	Project size, project function, height of the building, building complexity, quality requirements
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	If the requirements of the job are altered, this will change the initially projected timeframes, especially where additional materials and labour must be organised.

	

	
	Labour availability
	The construction process sequence is very important when organising the required labour. For example, a plasterer should only be organised after all other trades have performed their tasks correctly – electricians and plumbers will not be able to access behind the walls as easily once the plasterer has put them up.

	

	
	Material availability
	You must liaise with sub-contractors and suppliers to ensure materials are delivered when the sub-contractor is ready to complete their work. Materials that are rare or difficult to source should be ordered well in advance.

	

	
	Weather
	Weather will affect the ability of trades to complete their jobs on time.

	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact Dial Before You Dig before undertaking any excavation to ensure that services will not be damaged during construction.

	

	
	Electricity
	Electricity may need to be disconnected from work zones prior to construction and temporary utilities installed for the duration of the construction process.

	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers.

	

	
	Waste disposal
	Set up a designated area for rubbish bins and waste removal. Check if permits are required to place bins on the street.

	

	
	Water connection
	Book in a plumber to perform any required disconnections prior to any demolition taking place.

	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	Section 40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	Section 41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	Section 308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☐	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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