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CPCCBC4007A 
Plan building or construction work 
ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	Participant Name
	Guangyu ZHU




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	Myles Walder

	Assessor Signature
	
	Unit Competence Determination Date
	30/03/2021


Theory Exam - CPCCBC4007A Plan building or construction work

	Assessment Summary - CPCCBC4007A Plan building or construction work
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Plan building or construction work


	THEORY EXAM INSTRUCTIONS

1. This exam will occur under standard assessment conditions.
1. An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
2. Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
3. Please fill in the details below, providing your name, signature and date of assessment.
1. Your signature acknowledges that this is your own work.
4. Assessors are to complete marking in pen of a different colour to the Participant.
5. If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
1. If a Participant changes their response in writing, they must put their initials next to the written change.
2. If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	Guangyu ZHU

	
	

	Participant signature
	
	
	

	Date
	4/03/2021



	Assessor name
	Myles Walder

	
	

	Assessor signature
	
	
	

	Date
	30/03/2021




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	45
	41
	Satisfactory
	Not Yet Satisfactory

	
	
	
	




	ASSESSOR COMMENTS

	Please refer to the following questions for correction:

Question 1 – Incorrect. Where do you find the detail regarding the construction requirements found in the drawings as an appendix to the contract?
Question 20 – You can’t excavate without the access established. What about setting up a temporary crossover?
Question 29 – That is not a Regulation. Try WHS Regulation 2011 for information regarding the need for WHS procedures
Question 43 – Please describe critical path



1. Name one (1) document you might read alongside the contract to identify the following aspects:
7. Material requirements
8. [bookmark: OLE_LINK1][bookmark: OLE_LINK2]Plant requirements
9. On-site labour requirements
10. Any unusual aspects of construction

	Answer
	· Specification

	



1. [bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	Queensland Building and Construction Commission Act 1991 (Qld)
Schedule 1B s-33
	The building contractor under a regulated contract must not, before starting to provide the contracted services at the building site, demand or receive a deposit under the contract of more than— (a) for a level 1 regulated contract (other than a contract mentioned in paragraph (c))—10% of the contract price; or (b) for a level 2 regulated contract (other than a contract mentioned in paragraph (c))—5% of the contract price; or (c) for a level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price—20% of the contract price. Maximum penalty—100 penalty units.

	




1. [bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Carpentry

	Installs flooring, wall frames, roof trusses, windows, external doors and frames, decking and steps; attends to joinery and mouldings.

	

	
	Plastering

	Installs internal linings.

	

	
	Waterproofing

	Prepares wet area surfaces.

	



1. [bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




1. [bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	As part of the project planning, the site supervisor would have read through the site files (including contract and specifications) to determine the type of labour required to carry out the construction of the project. 
Referring to the Gantt Chart, it is able to determine exactly when subcontractors need to be on site. Check that your contractors are available when you need them. Even if a contractor suits your requirements there is no point in employing them if they are not available to work in the timeframe required.

	



1. [bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	Advertising
Search from internet
	



1. [bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	come late or of a poor quality
	


1. [bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680.2.4-1997
	



1. [bookmark: _Ref351751][bookmark: OLE_LINK3][bookmark: OLE_LINK4]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	tower lift
	lifting lighting up high will drastically improve the lighting effects on stage.
	

	
	compressor
	An air compressor is a pneumatic device that converts power (using an electric motor, diesel or gasoline engine, etc.) into potential energy stored in pressurized air (i.e., compressed air). By one of several methods, an air compressor forces more and more air into a storage tank, increasing the pressure.
	




1. [bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	ladders
	ladders are one of the least stable but most commonly used tools for working at heights. 
	

	
	wheelbarrows
	A wheelbarrow is a small hand-propelled vehicle, usually with just one wheel, designed to be pushed and guided by a single person using two handles at the rear, or by a sail to push the ancient wheelbarrow by wind. ... Use of wheelbarrows is common in the construction industry and in gardening.
	




1. [bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	invoices and receipts
	


1. [bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Temporary electrical pole
Water tapping
Temporary fencing
Barricades
Waste bin

	



1. [bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	    
	True 
	
	
	
		False 
	
	




1. [bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




1. [bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





1. [bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	setting up a temporary crossover
	



1. [bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 2-section2
	Volume 1-sectionD
	




1. [bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	compliance assessment application
To be eligible for an out of hours construction approval:
1. The proposed construction works cannot be undertaken during the prescribed daytime or evening hours (6.30am to 6.30pm Monday to Saturday) due to legitimate reasons such as pedestrian or worker safety, health or traffic reasons; and
2. There must be a condition stipulated on a Council development approval that requires the applicant to notify or obtain approval from Council for proposed out of hours construction works. 
If both of these requirements are not met, Council cannot accept an out of hours construction application and as such, construction activities are to be conducted during the prescribed hours as per the Environmental Protection Act 1994 (EP Act).

	



1. [bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	· Lane or Road Closure Permit

	To temporarily close any part of a Brisbane City Council road including parking bays, you are required to obtain a Temporary Road Closure Certificate from Council. Any activity likely to impact the operation of the road network or traffic flow including any off-road activity that affects the flow of traffic will require a certificate.
	

	
	· Footpath Closure Permit

	Brisbane City Council supports work on Council property such as roads and footways as part of construction work or business operations. Council regulates these activities to ensure public health and safety.
Find out the different types of work require approval and how to apply using the Application/Notice to Work on Council Property. Note: there are separate requirements for footpath dining.

	



1. [bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




1. [bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	purchase order
	



1. [bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




1. [bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	supplier
	



1. [bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	Work Health and Safety Act 2011 S17
Schedule 3
	Management of risks 
A duty imposed on a person to ensure health and safety requires the person— 
(a) to eliminate risks to health and safety, so far as is reasonably practicable; and 
(b) if it is not reasonably practicable to eliminate risks to health and safety, to minimise those risks so far as is reasonably practicable.

	




1. [bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	[bookmark: _GoBack]WHS Regulation 2011
	


1. [bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheets (SDS)
	



1. [bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10
	



1. [bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




1. [bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




1. [bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	sub-contractors move to another location it can be difficult to ensure their return for the next stage of the project
	




1. [bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	If plaster board delivered before roof done, raining will damage the board. 
	



1. [bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




1. [bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





1. [bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
G
F
H
E
I
J				
D
C
B
A

	Answer
	

	



1. [bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

1. [bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




1. [bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




1. [bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





1. [bookmark: _Ref432123]Describe the critical path.

	Answer
	The ‘critical path’ is defined as the shortest completion time possible to complete a job. Critical path information:
· Sets out the build and its stages 
· Details and records the build timelines
· Shows when sub contractors are due on site and for how long 
· Structures the supply chain of materials 
· Allows for delays and other supply chain problems 
· Caters for things like inclement weather cycles, other unpredictable problems and issues causing deferment and changes in the timelines, deferring supply of materials and labour 
Depending on the path you take will depend on how much float is in the job. 
Delays in your critical path can cause an increase in time and money.

	



1. [bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




1. [bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	inclement weather cycles
other unpredictable problems
deferring supply of materials and labour
	



1. [bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




1. [bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	Take photos to support your report – it will be helpful in the event of a dispute with a neighbour.
	


1. [bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




1. [bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	If work is to affect neighbouring properties, you are required to compile a report on the condition of existing buildings and structures on adjacent site boundaries. 
	
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	PRACTICAL ASSESSMENT INSTRUCTIONS

55. The following practical assessment will require the Participant to complete work related activities.
56. The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
57. Please fill in the details below – providing your name, signature and date of assessment.
1. The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
58. The Assessor may substitute a Practical Task with an alternate task of equal value.
1. Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Guangyu ZHU

	
	

	Participant signature
	
	
	

	Date
	14/03/2021



	Assessor name
	Myles Walder

	
	

	Assessor signature
	
	
	

	Date
	30/03/2021





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
	
	

	Task 1 (Occasion 2)
	
	




	ASSESSOR COMMENTS

	


CPCCBC4007A
Plan building or construction work

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities:
59. Occasion 1: Residential projects
60. Occasion 2: Commercial projects

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
61. A construction program/schedule for a project showing:
1. The sequencing of the trades, etc.
2. Working and non-working days, etc.
62. Local authority construction commencement notices
63. Pre-construction site inspection reports or dilapidation reports
64. WHS policy

The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document.

	Resources required: 
Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. 

	Assessment of task

	Name of participant:
	Guangyu ZHU

	Name of observer:
	Di XIE

	Role of observer 
(Confirm suitability to sign)
	Assistant

	Email address of observer
	tonixd@hotmail.com

	Signature of observer:
	
	Date:
	14/03/2021
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1 Appraise contract documentation

	1. [bookmark: _Ref536514168]Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties.
		
	1. [bookmark: _Ref536514171]Determine availability of selected subcontractors to suit the job requirements. 
		
	1. [bookmark: _Ref536514174]Assess availability of materials and confirm with suppliers. 
		
	1. [bookmark: _Ref536514176]Identify site access requirements and limitations, taking action to facilitate entry. 
		
	1. [bookmark: _Ref536514185]Prepare documentation for authorities controlling construction work and determine project commencement date. 
		
	1. [bookmark: _Ref536514189]Implement procedures for controlling and recording site deliveries. 
		
	2 Construction operation strategies 

	1.3A.  [bookmark: _Ref536514201]Identify organisational strategies for implementing construction. 
		
	1.3B.  [bookmark: _Ref536514204]Implement procedures for recording the hire of plant and equipment. 
		
	1.3C.  [bookmark: _Ref536514207]Implement organisational WHS policies and procedures, including hazard and risk management.
		
	1.3D.  [bookmark: _Ref536514211]Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements.
		
	1.3E.  [bookmark: _Ref536514215]Follow procedures for the control of multiple projects. 
		
	3 Project schedule 

	1.4A.  [bookmark: _Ref536514218]Sequence construction operations. 
		
	1.4B.  [bookmark: _Ref536514221]Enter operation details into a manually prepared project schedule or computer-based software package.
		
	1.4C.  [bookmark: _Ref536514224]Define critical path of the project, revising as required.
		
	1.4D.  [bookmark: _Ref536514227]Adjust project timeframes to account for anticipated delays.
		
	4 Required resources

	1. [bookmark: _Ref536514241]Determine and document temporary services and site accommodation requirements.
		
	1. [bookmark: _Ref536514244]Determine and document plant requirements and availability, with reference to contract documentation.
		
	1. [bookmark: _Ref536514247]Determine and document on-site labour requirements, with reference to contract documentation. 
		
	5 Condition reports

	1. [bookmark: _Ref536514251]Complete reports on the condition of existing buildings and structures on adjacent site boundaries. 
		
	1. [bookmark: _Ref536514256]Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction.
		
	1. [bookmark: _Ref536514373]Effectively communicate using the following methods:
77. Telephone, facsimile, email and in writing 
78. Language/concepts appropriate to cultural differences
79. Non-verbal communication
		
	The Participant’s performance was:  Satisfactory     Not Satisfactory





	OBSERVER COMMENTS
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