On completing this task please see the following:
· The Practical Completion Checklist (please see attached)
· Excerpt from the contract showing the definition of Practical Completion (please see below)
· Screenshot to demonstrate the same, as shown below

Except from the contract showing the definition of Practical Completion as shown under Clause 17 of the final contract

17 PRACTICAL COMPLETION
17.1 Contractor's notice of anticipated Practical Completion
Not less than two (2) Business Days before the Day on which the Contractor anticipates bringing the Works to
Practical Completion, the Contractor must give to the Owner written notice of:
a) the Day on which the Contractor anticipates bringing the Works to Practical Completion; and
b) a final inspection of the Works between the Owner, or the Owner's Agent, and the Contractor at a time on
that Day set out in the notice.
17.2 Owner must notify Contractor if unable to attend final inspection
If the Owner, or the Owner's Agent, is unable to attend the final inspection of the Works at the time and Day set out in the Contractor's notice given in accordance with Clause 17.1, the Owner must:
a) immediately notify the Contractor in writing; and
b) arrange with the Contractor a final inspection of the Works at a mutually agreeable time, during usual business hours, on a Day before, or on, the Day set out in the Contractor's notice given in accordance with Clause 17.1.
17.3 Parties to attend final inspection
The Owner, or the Owner's Agent, and the Contractor must attend the final inspection of the Works at the time and Day set out in the Contractor's notice given in accordance with Clause 17.1, or as otherwise arranged in accordance with Clause 17.2.
17.4 Owner's failure to attend the final inspection
If the Owner, or the Owner's Agent, does not attend the final inspection of the Works in accordance with Clause 17.3, the Owner is deemed to have accepted that:
a) there are no defects in the Works; and
b) the Works are complete.
17.5 Contractor to give signed defects document to Owner in certain circumstances
If, at the final inspection of the Works, the Owner claims that there are minor defects in, or minor omissions from, the Works, the Contractor must give to the Owner, at that inspection, a defects document that:
a) lists any minor defects and minor omissions that the Contractor and the Owner agree exist;
b) states when the Contractor is to remedy the listed agreed minor defects and minor omissions;
c) lists any minor defects or minor omissions that the Owner claims exist, but that the Contractor does not agree
exist; and
d) is signed by or on behalf of the Contractor.
17.6 Contractor must remedy agreed minor defects and minor omissions
The Contractor must remedy any agreed minor defects and minor omissions in any defects document within the times stated in the defects document or, if necessary materials or labour are unavailable, within a reasonable period.
17.7 No Possession of the Works before payment
Unless the Owner has obtained the Contractor's prior written consent, the Owner must not take Possession of the Works, nor is the Owner entitled to the keys to the Works, prior to making full payment to the Contractor of the Contract Price.
17.8 Contractor to hand over Works on payment
On full payment by the Owner of the Contract Price, the Contractor must hand over the Works, including the keys to the Works, to the Owner or the Owner's Agent.
17.9 Payment of disputed amount into Holding Account
a) If the Owner wishes to take Possession of the Works but disputes any part of the Contract Price claimed by
the Contractor, the Owner may pay the disputed amount into a Holding Account. The Owner is to then give the Contractor a receipt showing the disputed amount has been deposited into the Holding Account, and pay any
undisputed amount to the Contractor. On receiving the receipt and payment (if any), the Contractor is to hand
over the Works, including the keys to the Works, to the Owner or the Owner's Agent.
b) You must ensure that any money received into the Holding Account under this Clause is released in accordance with, or in satisfaction of:
i) written instructions signed by the Contractor and the Owner;
ii) an order of the Tribunal;
iii) an order of a Court; or
iv) a written adjudication decision of an adjudicator.
17.10 Consequences of Owner taking Possession of the Works when not entitled to do so
If the Owner takes Possession of the Works when not entitled to do so under this Contract, the Works are deemed to have reached Practical Completion without any defects or omissions on the Day that the Owner takes Possession, and the Owner is liable to the Contractor for any loss or damage that the Contractor may incur or suffer as a result.
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