Theory Exam - CPCCBC4029B Apply construction information to the sales process

	Theory Exam - CPCCBC4029B Apply construction information to the sales process

CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.
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	Participant signature
	



	Assessor name
	Brett Stoward

	

	

	Assessor signature
	



	Date
	4/12/2018




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	· In Queensland, individuals and companies must hold a QBCC licence to carry out:
· Any building work valued over $3,300
· Building work valued over $1,100 where it involves Hydraulic Services Design

In NSW, individuals and companies must hold a NSWBCC licence to carry out:
· garage, carport and shed construction/erection (including kits)
· bathroom, kitchen or laundry renovations
· swimming pool building and structural landscaping
· screened, glass or pool enclosures
· atriums, conservatories
· house lifting (ie. permanently raising the height of an existing structure)
· removal and resiting of dwellings
· saunas and steam rooms.
Applicants must show at least 2 years relevant industry experience in a wide range of building construction work where the majority of the experience was obtained within 10 years of the date on which the application is made.
'Experience' means experience gained by the applicant as:
1. an employee of, OR
2. a holder of a supervisor certificate and as a nominated supervisor for the contractor licence held by, OR
3. a holder of an endorsed contractor licence contracted to, OR
4. a holder of a supervisor certificate in the capacity of a nominated supervisor for a contractor licence held by an individual, partnership or corporation contracted to,
Current qualification requirements
1. Certificate IV in Building and Construction (BCG40106 or CPC40108 Building or CPC40110 Building) or (BCG40206 or CPC40208 Contract Administration) or (BCG40306 or CPC40308 Estimating) or (BCG40506 or CPC40508 Site Management)

	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	Electrical contractor completes inquiry on behalf of client.

The Distribution Network Service Provider (e.g. Energex) will conduct the necessary network investigations and provide an indicative estimate of potential costs and timeframes for the client to make an informed decision within 20 business days

If the application is not expedited (e.g. by agreeing to the Model Terms and Conditions for Deemed Standard Connection Contracts), the Distribution Network will advise of a Network Connection Offer within 10 business days

The electrical contractor will submit an Electrical Work Request (EWR) to the Distribution Network Service Provider once the work is complete

A copy of the EWR will be sent to the client’s preferred electricity retailer

The Distribution Network Service Provider must adhere to timeframes for new connections (e.g. Energex will attend the property within 5 business days


The whole process takes approximately 25 days in total if process expediated it takes approximately takes 15 days

	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	Water approval application to Qld and urban – require to provide evidence for the connection

Standard connections for simple residential developments are usually completed within five (5) days



	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	· Section J of the Building Code of Australia mandates that new and refurbished buildings to meet energy efficiency performance standards

	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Lower gas emissions / artificial lighting & power, recyclable material
	

	
	Client benefit
	Long term savings
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Carpentry

	Installs flooring, wall frames, roof trusses, windows, external doors and frames, decking and steps; attends to joinery and mouldings
	

	
	Bricklaying
	Installs brick base (sub-base brickwork, dwarf walls and piers); installs walls
	

	
	Waterproofing

	Prepares wet area surfaces.

	

	
	Plastering
	Installs internal linings.

	

	
	Tiling
	Completes wall and floor tiling.

	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	3
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	4
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavations and other earthmoving machinery
	

	
	
	Duration
	It varies depending on soil test, site levelling and clearing 
	

	
	2: Slab or base stage
	Trades
	Concreting, Steelfixing, Bricklayers, water proofing and termite specialist
	

	
	
	Duration
	Approximately 1-2 Weeks
	

	
	3: Frame stage
	Trades
	Carpentry, electrical, plumbing, bricklaying
	

	
	
	Duration
	Approximatey 3-4 weeks
	

	
	4: Lockup stage
	Trades
	Carpantery, plumbing, electrical
	

	
	
	Duration
	Approximately 4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Plumber, electricians, tiling and carpanter
	

	
	
	Duration
	Approximately 5-6 weeks
	

	
	6: Practical completion stage
	Trades
	Painter and landscaping
	

	
	
	Duration
	Approximately 6-7 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	[bookmark: _GoBack]Project size and location
Project function
Height of the building
Building complexity
Quality requirement
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	If the requirements of the job are altered, this will change the initially projected timeframes, especially where additional materials and labour must be organised.
	

	
	Labour availability
	The construction process sequence is very important when organising the required labour. For example, a plasterer should only be organised after all other trades have performed their tasks correctly – electricians and plumbers will not be able to access behind the walls as easily once the plasterer has put them up.
	

	
	Material availability
	You must liaise with sub-contractors and suppliers to ensure materials are delivered when the sub-contractor is ready to complete their work. Materials that are rare or difficult to source should be ordered well in advance.

	

	
	Weather
	Weather will affect the ability of trades to complete their jobs on time.
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact Dial Before You Dig before undertaking any excavation to ensure that services will not be damaged during construction.

	

	
	Electricity
	Electricity may need to be disconnected from work zones prior to construction and temporary utilities installed for the duration of the construction process.
	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers.

	

	
	Waste disposal
	Set up a designated area for rubbish bins and waste removal. Check if permits are required to place bins on the street.

	

	
	Water connection
	Book in a plumber to perform any required disconnections prior to any demolition taking place.

	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	Work Health and Safety Regulation 2017 (NSW) Section 40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	Work Health and Safety Regulation 2017 (NSW) Section 41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	Work Health and Safety Regulation 2017 (NSW) Section 308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☐	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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