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CPCCBC4003A Select and prepare a construction contract, 
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 
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	THEORY EXAM INSTRUCTIONS

1. This exam will occur under standard assessment conditions.
1. An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
2. Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
3. Please fill in the details below, providing your name, signature and date of assessment.
1. Your signature acknowledges that this is your own work.
4. Assessors are to complete marking in pen of a different colour to the Participant.
5. If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
1. If a Participant changes their response in writing, they must put their initials next to the written change.
2. If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	YANZHONG ZHU

	
	

	Participant signature
	
	
	

	Date
	5/07/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	51
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	



	ASSESSOR COMMENTS

	



[bookmark: _Ref428791704][bookmark: _Ref527462137]Order the following elements of an agreement from 1 to 4.

	Answer
	Element Number
	Element
	
	
	2
	Acceptance
	

	
	4
	Consideration
	

	
	3
	Intention of legal consequences
	

	
	1
	Offer
	




[bookmark: _Ref428791707]When would an offer be considered to have lapsed?

	Answer
	-When the time for acceptance expire.
-If the offer is withdrawn before it is accepted.
-After a reasonable time in the circumstance.(Generally the greater the value of the contract, the longer life of the offer)
	



[bookmark: _Ref428791708]What happens to the offer if new terms are suggested?

	Answer
	New terms suggested are regarded as a counter offer which can be accepted or rejected.
	



[bookmark: _Ref428791713]What does it mean when a contract is supported by ‘valuable consideration’?

	Answer
	-One party promises to do something in return for a promise from another parties.
-Consideration is what each party gives to the other as the agreed price for the others’ promises.
-Usually the consideration is the payment of money.
	




[bookmark: _Ref528220703]Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

	Answer
	-Persons suffering from a mental disability
- Intoxicated individuals, senile persons.
	



· [bookmark: _Ref423505767][bookmark: _Ref527444202]Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

	Answer
	-Consent is an act of reason and deliberation
- A person who possesses and exercises sufficient mental capacity to make an intelligent decision demonstrate consent by performing an act recommended by another
-Consent is implied to every agreement.


-Apparent consent may be negated because of mistake, fraud, innocent misrepresentation, duress or undue influence, all of which are defences to the enforcement of the contract.
	



[bookmark: _Ref428790918]Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

	Answer
	QBCC base in Queensland monitors all about construction legal work, provide legal advice.
	



[bookmark: _Ref495585144]Under what laws are domestic building contracts regulated?

	Answer
	Under price change clause, means a provision of domestic building contract allowing for a change to be made to the contract price, but does not include a cost escalation clause.
	



[bookmark: _Ref495585145]Domestic building contracts must be put in writing once the work exceeds what value?

	Answer
	If the cost of domestic building work exceed $3300 it must be covered by a written contract.
	



[bookmark: _Ref495585147][bookmark: _Ref527985213]A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

	Answer
	-A lump sum contract for minor commercial work up to the value of $100000.
-A lump sum contract to be used for the construction only of commercial building work with or without a Principal’s agent.
	



[bookmark: _Ref495585148]Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

	Answer
	Contractor must give the owner a signed copy of the entire contract within 5 business day after entering the contract.
	



[bookmark: _Ref423502767]What are the benefits of having a written contract in place between parties?

	Answer
	-Making both parties seriously aware of the effects of the agreement, both when it comes to performance and nonperformance 
-Having tangible proof of what you and the other party agreed to  originally
-Knowing how disputes will be resolved.
-Enhancing the trust between each party by negotiating each others’ desires.
	



[bookmark: _Ref495585603]Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

	Answer
	Clauses
	Answers
	Definition
	
	
	1
	Acceptances
	1 - F
	A
	Provide specific reasons that allow the contract period to be adjusted
	

	
	2
	Cost adjustments
	2 - E
	B
	A provision for which remedies can be sought if breached
	

	
	3
	Extensions of time
	3 - A
	C
	Specifically outlines the tasks to be completed as part of the construction work
	

	
	4
	Payments
	4 - D
	D
	Outlines the requirements for deposits
	

	
	5
	Scope of work
	5 - C
	E
	Address the risk of rise/fall of expenses
	

	
	6
	Term
	6 - B
	F
	Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding
	




[bookmark: _Ref428786304]Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Contract estimate
	

	
		Contract request
	

	
		Preliminary agreement
	




[bookmark: _Ref424211634]True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

	Answer
		True 
	
	
	
		False 
	
	





[bookmark: _Ref428774552]Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

	Answer
	Contract name
	Description
	
	
	New home construction contracts
	For the construction of an entire home
	

	
	Natural disaster repairs contracts
	For domestic building projects not exceeding $3300
	

	
	Commercial building contracts
	A lump sum contracts to be used for the construction only of commercial building work with or without a Principle’s agent
	

	
	Commercial minor works contracts
	A lump sum for minor commercial work up to the value of $100000
	




[bookmark: _Ref424211517]Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

	Answer
	Commercial minor works contract
	



[bookmark: _Ref495650885]Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

	Answer
	Level 1- Renovation, Extension and Repair contracts
-For renovation, extension and routine repairs on existing homes for contracts $3301 to $19999
	


[bookmark: _Ref495653718]Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

	Answer
	Topics
	Definition
	
	
	Builder’s Licence
	You should only deal with a QBCC-licensed contractor. If you engage an unlicensed contractor, your building work may not be covered under the Queensland Home Warranty Scheme. Before committing, check the contractor’s licence and history via the Online Licence Search on the QBCC website or by calling the QBCC
	

	
	Contract price
	For contracts priced at $20,000 or more, the contract price,
if fixed, must be shown prominently on the first page of the contract schedule. If the contract price is not fixed, the method for calculating it, including any allowances, must be stated in the contract schedule. Allowances (items or services for which the price is not fixed when the contract is signed) should be kept to a minimum as the final cost often exceeds the estimate in the contract. The contract must also contain a warning about any provisions that may alter the contract price.
	

	
	Building approvals and inspections
	Building inspections and approvals are the responsibility of a building certifier. Mandatory building inspections may be required at certain stages of construction. The contractor must give you copies of any certificates of inspection as soon as practicable after they receive them from the certifier. You can check the certifier’s licence via QBCC’s Online Licence Search
	

	
	Practical completion and handover
	You are not required to pay the final contract payment until all of the contracted work has been completed in accordance with the contract including any plans and specifications, all legal requirements, and either without any defects or omissions, or with only minor defects or minor omissions that will not unreasonably affect occupation. If you believe there are any minor defects or
minor omissions, the contractor must give you a ‘defects document’(listing agreed and non-agreed matters). This document should be compiled by you and the contractor during a handover inspection. Check your contract to see if it imposes any extra requirements on the contractor for practical completion.
	

	
	Implied warranties
	Sections 19 - 26 of Schedule IB of the Act set out statutory
warranties deemed to be part of all regulated domestic building contracts, even if not stated in the contract. The warranty period is 6 years from completion, termination or cessation of the work for breaches resulting in structural defects; 1 year for all other breaches. Legal proceedings for any breach must be started within the warranty period or a further 6 months if the breach becomes apparent within the last 6 months of the warranty period.
	



· [bookmark: _Ref423503323][bookmark: _Ref423598528]Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Engineer specifications
	

	
		Plans, drawings and specifications
	

	
		Prime Cost Items Schedule
	

	
		Processes for applying for extensions of time
	

	
		Product catalogues
	

	
		Project timelines and schedules
	

	
		Provisional Sums Schedule
	

	
		Rise and fall calculations
	

	
		Site conditions report
	

	
		Soil and sedimentation report
	




[bookmark: _Ref428785642]What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

	Answer
	-Prime Cost item is 
· -An amount of money included in a contract sum to purchase a specified item such as tiles, taps, doors or bathroom fittings
· An agreed estimated amount is included at contract signing but the specific products are not selected until a later stage
· A builder must estimate the cost of such items at or above the lowest amount these items could reasonably cost
Like client got several options for different kinds of tile, the gap of price would be required to put on the final contract sum.

-Provisional Sum is
· An amount of money included in contract sum to cover work and/or materials, not detailed when entering the contract
· Typically builders will include a PS for site work costs
· The builder is legally required to take reasonable steps to ensure an accurate site works cost estimate but unforeseen events mean that the provisional sum is exceeded which is added to the contract sum
Like unforeseen events in earth work, hard rock or limestone take more cost over estimate required to be added on the contract sum.


	



[bookmark: _Ref428796325]Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

	Answer
	There is a risk that, during the course of a commercial contract, the costs of performing that contract will rise or fall from the costs initially estimated. Cost adjustment provisions address this risk by providing mechanisms for adjusting contract payment to reflect changes in costs, but they only apply to long-term costs and some specific costs (e.g. labour and materials, currency exchange rates for overseas-purchased goods, duties, taxes, shipping). 

	



[bookmark: _Ref495650899]True or False (Tick your response): Variations can be requested by both the client and the builder.

	Answer
		True 
	
	
	
		False 
	
	




· [bookmark: _Ref423508256][bookmark: _Ref527450478]How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

	Answer
	- All variations must be put in writing and agreed to in writing by both the contractor and the client, before work commences (unless the work is required urgently and it is not practical to produce a variation document before the work commences). Failure to fully and accurately document changes to the original contract is a frequent cause of disputes.
- Parties should establish any extra costs before alterations are made to the contract or plans. The contractor should also submit an extension of time and payment in accordance with the time stated in the variation document.


	




[bookmark: _Ref495652895]Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

	Answer
	-Fair Trading Act 1989 (Qld), Competition and Consumer Act 2010 (Cth)
	



[bookmark: _Ref495653465]Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

	Answer
	-Before entering into a credit contract, the credit provider must:
-Make reasonable inquiries about why you want to borrow the money
-Make reasonable inquiries about your financial situation
-Take reasonable steps to verify your financial situation
-Assess whether you can meet the financial obligations of the credit contract (and whether it will meet your needs)
-Determine that the credit contract is ‘not unsuitable’ for you

	



[bookmark: _Ref428776673]What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

	Answer
	Schedule 1B of the QBCC Act provides for a cooling off period, giving the consumer the option to withdraw from the contract within five days of receipt of the signed contract 

	




[bookmark: _Ref428779587]What are the maximum deposits recommended for a residential building project?

	Answer
	- The QBCC Act sets out maximum deposit percentages that must not be exceeded. If the contract for domestic building work is priced at $20,000 or more, the maximum deposit is 5%. If the contract price is more than $3,300 and less than $20,000, the deposit must not exceed 10%.
	



[bookmark: _Ref428794433]Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

	Answer
	-Deposit   5%
-Base stage   15%
-Frame stage   20%
-Enclosed stage    25%
-Fixing stage   20%
-Practical completion   15%
	



· [bookmark: _Ref423508227]You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

	Answer
	It’s not allowed to take priority to that job, because Once entering the contract, the date of commencement and stage completion need to be restricted followed, any contrary to the contract would cos penalty.
	

[bookmark: _Ref423515882][bookmark: _Ref423515982]
· [bookmark: _Ref423504803]Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

	Answer
	Breach
	Explanation
	
	
	Breach of condition under contract
	These are essential terms. If a condition is not fulfilled, the nature of the contract is drastically changed.

	

	
	Breach of warranty under contract
	If a warranty is not fulfilled, the nature of the contract is not drastically changed.
	




[bookmark: _Ref428793813]What does repudiation of a contract mean?

	Answer
	Repudiation occurs when a party to a contract is unwilling to perform their contractual obligations – through acknowledgement or their actions are totally inconsistent with their obligations under the contract
	



[bookmark: _Ref528068459]True or False (Tick your response): In the event of repudiation, the injured party has two options:
6. Continue with the contract
7. Accept the repudiation and move to terminate the contract

	Answer
		True
	
	
	
		False
	
	




[bookmark: _Ref528068460]Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

	Answer
	Because if the situation is not deemed to be a repudiation, by acting the terminate the contract the ‘injured’ party may themselves be repudiating the contract and could be liable to pay damages
	


[bookmark: _Ref428794305]What does ‘abandonment of contract’ mean?

	Answer
	Both parties have conducted themselves in such a way that the original construct is no longer valid. 

	



[bookmark: _Ref428793803]A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

	Answer
	- Where a party is unwilling to perform under the agreement (i.e. for reasons other than poor performance), this may be deemed a termination of ‘convenience’

- Where one party fails to meet the terms of the contract (e.g. due to poor performance)  the aggrieved party’s action may be deemed a termination for ‘cause’.

	



[bookmark: _Ref495653458]Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

	Answer
		Yes
	
	
	
		No
	
	



[bookmark: _Ref428795233]If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

	Answer
	-What must occur to perform the contract
-A reasonable time in which the contract must be completed
-A statement of the consequences of not performing in accordance with the notice.

	



[bookmark: _Ref528148821]True or False (Tick your response): Where the notice given (as per Q39. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

	Answer
		True
	
	
	
		False
	
	




[bookmark: _Ref428781925][bookmark: _Ref528152060]When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

	Answer
	Final Payment - Organise final payment of the project at practical completion and not at handover
- . Final payment can not be withheld as it is a contract breach.


	


[bookmark: _Ref428794091]Explain the concept ‘conditions for completion at the cost of the contractor’.

	Answer
	Defects after completion
The Contractor must make good defects or omissions in the work under this Contract which become apparent within 6 months of the Date of Practical Completion.
If there are any such defects or omissions, the Owner must give the Contractor written notice to make good such defects or omissions within the 6 month period
and must give the Contractor reasonable access to the Site for that purpose.
Subject to reasonable access being provided, the Contractor must within 28 calendar days of the notice being given rectify any defects notified to the Contractor during usual business hours.

	



[bookmark: _Ref495653464]Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

	Answer
	- a warranty against defects must state the period or periods within which a defect in the goods or services to which the warranty relates must appear if the consumer is to be entitled to claim the warranty;
- a warranty against defects must state who will bear the expense of claiming the warranty and if the expense is to be borne by the person who gives the warranty—how the consumer can claim expenses incurred in making the claim;
- a warranty against defects must state that the benefits to the consumer given by the warranty are in addition to other rights and remedies of the consumer under a law in relation to the goods or services to which the warranty relates.

	



[bookmark: _Ref428795566]Name one (1) person you should consult if you are considering ousting a contractor from a building site.

	Answer
	To learn more about ousting a contractor from a building site you must consult your contract or lawyer to understand your rights and obligations.

	



[bookmark: _Ref428795533]What document should you refer to if you are considering ousting a contractor from a building site?

	Answer
	Considering the far-reaching legal and economic consequences of ejecting you as the principal contractor or a sub-contractor, both owner and builder must be meticulous in applying the dismissal procedure delineated in the contract.
	




[bookmark: _Ref428776477]How should you handle a customer complaint?

	Answer
	1. Deal with the complaint immediately 
2. Stay calm
3. Identify the problem
4. Decide what can be done 
5. Arrange a second opinion to confirm your view
6. Keep records
7. Fix the problem

	



[bookmark: _Ref428780523]How do you reduce the risk of dispute?

	Answer
	1. Record all complaints 
2. Act promptly
3. Do what you say you’re going to do
4. Do not make unrealistic promises

	



[bookmark: _Ref428780789]What is the process for dispute resolution?

	Answer
	When negotiations between you and your client or trade contractor break down, and rectification work is not completed, there are options and procedures for resolving your dispute.
You should always refer to your contract first which outlines all contractual details in order to:
· Determining responsibility for defects
· Directing the contractor (where appropriate) to rectify defects or complete the works

	


· [bookmark: _Ref423599342]During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

	Answer
	Hi, 

Thanks for your patient and I have checked with the email of your concerns of the bathroom installations. 

And regarding to your concerns, I’ve checked the contract and the white goods and chattels selected list, and in case for that, I’ve also double checked the specifications and materials order and the receivable order sheets, there were not any mistakes or issues in that installation, everything is following by the contract plan. And as the legal signed contract, we can’t make any changes on that in case of more confusions and dispute. 

So, if you still get any troubles or questions on our contract or you want to change your ideas on your bathroom style, I’m more than happy to talk with that and may give you more ideas rather than to pay extra for modification.

Thank heaps for your time.

Regards,

Steve 
	


[bookmark: _Ref428787470]Where would you find any possible penalties associated with a build?

	Answer
	Client’s charging “liquidated damages” under a contract means there is a fixed sum of money which the builder agrees to pay the client, often in relation to late completion of the project.
	



[bookmark: _Ref528221530]Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

	Answer
	-It is obtained once the final inspection has been inspected and passed.


-Brisbane City Council must hold records of building approvals and certification information. The legislation also requires that an accredited building certifier must lodge the following documents with Council:
· Engagement notice and application details
· Decision notice, approved building plans and any other documentation that contributed to the plan approval
· Completion details such as certificates (including certificate of classification and inspection certificates) and any other documents relating to the certification and acceptance of the completed building work

	


· [bookmark: _Ref423598913]Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:
7. The land has been secured and paid for by the Clients.
7. Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.
7. Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured. 
7. Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list. 
7. The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.
7. The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.
7. Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build. 
7. The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.
7. The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.
7. The construction period excluding inclement weather and possible delays is 23 weeks
7. Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).
7. Prime costs are required for the solar hot water system and ducted air conditioning
7. Provide fictitious details for all other sections of the contract.
7. 18 solar panels are to be installed on the roof


	Answer
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	PRACTICAL ASSESSMENT INSTRUCTIONS

8. The following practical assessment will require the Participant to complete work related activities.
9. The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
10. Please fill in the details below – providing your name, signature and date of assessment.
1. The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
11. The Assessor may substitute a Practical Task with an alternate task of equal value.
1. Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	YANZHONG ZHU

	
	

	Participant signature
	
	
	

	Date
	5/07/2020



	Assessor name
	YING SHE

	
	

	Assessor signature
	
	
	

	Date
	5/07/2020





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
		
	Task 1 (Occasion 2)
		



	ASSESSOR COMMENTS

	


CPCCBC4003A Select and prepare a construction contract,
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. 

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
1. Copy of a contract issued to sub-contractor for your project with relevant AS code on the front
1. Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails)
1. Copy of HSE minimum requirements sent as contract condition
1. Construction contracts that have been developed, signed off, or contributed to by the candidate
1. Proof of correspondence with client regarding construction contract. Redact sensitive information as required.

The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment.

	Resources required: 
Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer.

	Assessment of task

	Name of participant:
	YANZHONG ZHU

	Name of observer:
	XING WANG

	Role of observer 
(Confirm suitability to sign)
	Supervisor

	Email address of observer
	Freedomotz@live.com

	Signature of observer:
	
	Date:
	5/07/2020
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	Q1.  [bookmark: _Ref495661944]Explain to the client:
17. Essential terms and elements of a valid contract 
18. Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements)
19. The range of documents that collectively make up a contract (including construction schedules, reports, specifications)
20. The importance of the contract to sales process 
21. Implications of legislation, regulations and codes of practice (including Australian Consumer Law)
		
	Q2.  [bookmark: _Ref495662059]Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit.
		
	Q3.  [bookmark: _Ref495662068]Ensure the pre-contract agreement is signed and processed according to organisational requirements.
		
	Q4.  [bookmark: _Ref527380121]Select appropriate contract and seek expert advice in the preparation of the contract, considering:
22. Contract rise and fall amounts
23. Schedule of progress payments
24. Processes for applying of extensions of time
		
	Q5.  [bookmark: _Ref495661995]Break down contract clauses/terms/conditions with the client, including:
25. Rights, liabilities and potential penalties of parties under the contract
26. Definitions of building work, common contract terms and procedures, considering – 
1. Practical completion and issuing a final certificate
2. Defects liability and completion at the cost of the contractor
3. Effect of ousting the contractor from the building or site
27. Cooling off periods
28. Provisional sum and prime cost allowances
29. Measures to be taken in the event of an anomaly in the rendering of the contract, considering – 
1. Variations
30. Circumstances that bring about a breach and termination of contract, considering – 
1. Unreasonable/vexatious notice
2. Abandonment of a contract
30. Methods for resolving contractual disputes
		
	Q6.  [bookmark: _Ref495662164]Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods:
31. Verbally using language/concepts appropriate to cultural differences
32. Non-verbal communication
33. Using technology (including telephone, facsimile, email)
34. In writing (including drafting responses to queries about contracts)
		
	The participant’s performance was:  Satisfactory     Not Satisfactory



	OBSERVER COMMENTS
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