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CPCCBC4003A Select and prepare a construction contract, 
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.
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CPCCBC4003A Select and prepare a construction contract, 
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	Emily Conlon

	
	

	Participant signature
	
	
	

	Date
	5/04/2022



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	51
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	



	ASSESSOR COMMENTS

	



[bookmark: _Ref428791704][bookmark: _Ref527462137]Order the following elements of an agreement from 1 to 4.

	Answer
	Element Number
	Element
	
	
	2
	Acceptance
	

	
	4
	Consideration
	

	
	3
	Intention of legal consequences
	

	
	1
	Offer
	




[bookmark: _Ref428791707]When would an offer be considered to have lapsed?

	Answer
	- When the time for acceptance expires;
- If the offer is withdrawn before it is accepted; or
- After a reasonable time in the circumstances (generally the greater the value of the contract the longer life of the offer) 
	



[bookmark: _Ref428791708]What happens to the offer if new terms are suggested?

	Answer
	If new terms are suggested they are regarded as a counter offer which can be accepted or rejected. 
	



[bookmark: _Ref428791713]What does it mean when a contract is supported by ‘valuable consideration’?

	Answer
	- One party promises to do something in return for a promise from another party. 
- Consideration is what each party gives to the other as the agreed price for the other’s promises
- Usually the consideration in the payment of money 
	




[bookmark: _Ref528220703]Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

	Answer
	- Persons suffering from a mental disability
- Intoxicated individuals 
	



Q1.  [bookmark: _Ref423505767][bookmark: _Ref527444202]Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

	Answer
	Consent is an act of reason and deliberation. Parties must mutually assent to the proposed objectives and terms of a contract in order for it to be enforceable. The manifestation of the common intent of the parties is discerned from their conduct or verbal exchanges.
There will be no binding contract without the real consent of the parties. Apparent consent may be negated because of mistake, fraud, innocent misrepresentation, duress or undue influence, all of which are defences to the enforcement of the contract.  
	



[bookmark: _Ref428790918]Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

	Answer
	QBCC
-Licensing contractors
- Educating contractors about their legal rights and responsibilities
- Education consumers about their rights and obligations
- Handling disputes fairly and equitably
- Protecting homeowners against loss through the Queensland Home Warranty Scheme 
- Implementing and enforcing legislative reforms and, where necessary, prosecuting people not complying with the law.  
	



[bookmark: _Ref495585144]Under what laws are domestic building contracts regulated?

	Answer
	-Queensland Building and Construction Commission Act 1991
- Building Act 1975
- Building Industry Fairness (Security of Payment) Act 2017 
	



[bookmark: _Ref495585145]Domestic building contracts must be put in writing once the work exceeds what value?

	Answer
	$3,300
	



[bookmark: _Ref495585147][bookmark: _Ref527985213]A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

	Answer
	The QBCC Act requires any commercial work over $10,000 must be in writing before work starts. 
	



[bookmark: _Ref495585148]Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

	Answer
	5 Business Days 
	



[bookmark: _Ref423502767]What are the benefits of having a written contract in place between parties?

	Answer
	When there is no written contract in place between parties it can lead to disputes. It is important to full document and complete a compliant building contract to ensure that home owners receive the finished product they envisioned and builders get paid on time.  
	



[bookmark: _Ref495585603]Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

	Answer
	Clauses
	Answers
	Definition
	
	
	1
	Acceptances
	1 - F
	A
	Provide specific reasons that allow the contract period to be adjusted
	

	
	2
	Cost adjustments
	2 - E
	B
	A provision for which remedies can be sought if breached
	

	
	3
	Extensions of time
	3 - A
	C
	Specifically outlines the tasks to be completed as part of the construction work
	

	
	4
	Payments
	4 - D
	D
	Outlines the requirements for deposits
	

	
	5
	Scope of work
	5 - C
	E
	Address the risk of rise/fall of expenses
	

	
	6
	Term
	6 - B
	F
	Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding
	




[bookmark: _Ref428786304]Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Contract estimate
	

	
		Contract request
	

	
		Preliminary agreement
	




[bookmark: _Ref424211634]True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

	Answer
		True 
	
	
	
		False 
	
	





[bookmark: _Ref428774552]Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

	Answer
	Contract name
	Description
	
	
	HIA Small Works Contract
	Designed for domestic building works that do not affect the footings or foundations. It can also be used for smaller alteration and renovation projects. 
	

	
	Master Builders Commercial Minor Works Contract
	A lump sum contract for minor commercial work up to the value of $100,000
	

	
	QBCC New Home Construction Contract
	For the construction of an entire home. 
	

	
	Master Builders Commercial Building Contract 
	A lump sum contract to be used for the construction only of commercial building work with or without a principals agent. 
	




[bookmark: _Ref424211517]Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

	Answer
	Master Builders Commercial Minor Works Contract 
	



[bookmark: _Ref495650885]Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

	Answer
	QBCC Level 1 – Renovation, Extension and Repair Contract – For renovations, extensions and routine repairs on existing homes for contracts $3,301 to $19,999. 
	


[bookmark: _Ref495653718]Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

	Answer
	Topics
	Definition
	
	
	Builder’s Licence
	You should only deal with a QBCC-licensed contractor. If you engage an unlicensed contractor, your building work may not be covered under the Queensland Home Warranty Scheme. Before committing, check the contractor’s license and history via the QBCC Online Search or by call QBCC. 
	

	
	Contract price
	For contracts priced at $20,000 or more, the contract price, if fixed, must be shown prominently on the first page of the contract schedule. If the contract price is not fixed, the method for calculating it, including any allowances, must be stated in the contract schedule. Allowances (items or services for which the price is not fixed  when the contract is signed) should be kept to a minimum as the final cost often exceeds the estimate in the contract. The contract must also contain a warning about any provisions that may alter the contract price.  
	

	
	Building approvals and inspections
	Building approvals and inspections are the responsibility of a building certifier who may be engaged by you or, more commonly your builder. Mandatory building inspections may be required at certain stages of construction. If your contractor has engaged a building certifier for certain certification functions, you can ask the certifier (via a notice given to your contractor) to perform additional certifying functions which will be at your expense and must be carried out by the certifier within agreed timeframes. The contractor must give you copies of any certificates of inspection as soon as practicable after they receive them from the certifier. You can also ask the certifier, by written notice, for copies of any inspection documentation and the certifier must provide the documents within 5 business days. You can check a certifier’s licence via QBCC’s OnLine Licence Search.  
	

	
	Practical completion and handover
	You are not required to pay the final contract payment until all of the contracted work has been completed in accordance with the contract including any plans and specifications, all legal requirements, and either without any defects or omissions, or with only minor defects or minor omissions that will not unreasonably affect occupation. If you believe there are any minor defects or minor omissions, the contractor must give you a ‘defects document’ (listing agreed and non-agreed matters). This document should be compiled by you and the contractor during a handover inspection. Check your contract to see if it imposes any extra requirements on the contractor for practical completion.
	

	
	Implied warranties
	Schedule IB of the Act sets out statutory warranties which are deemed to be part of all regulated domestic building contracts, even if not stated in the contract. The warranty period is 6 years from completion, termination or cessation of the work for breaches resulting in structural defects; 1 year for all other breaches. Legal proceedings for any breach must be started within the warranty period or a further 6 months if the breach becomes apparent within the last 6 months of the warranty period.
	



Q2.  [bookmark: _Ref423503323][bookmark: _Ref423598528]Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Engineer specifications
	

	
		Plans, drawings and specifications
	

	
		Prime Cost Items Schedule
	

	
		Processes for applying for extensions of time
	

	
		Product catalogues
	

	
		Project timelines and schedules
	

	
		Provisional Sums Schedule
	

	
		Rise and fall calculations
	

	
		Site conditions report
	

	
		Soil and sedimentation report
	




[bookmark: _Ref428785642]What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

	Answer
	Prime Cost – An amount of money included in the contract sum to purchase a specified item such as tiles, taps, doors or bathroom fittings. An agreed estimated amount is included at contract signing but the specific products are not selected until a later stage. A building must estimate the cost of such items at or above the lowest amount these items could reasonably cost. 
E.g. if a client selects a more expensive door than allowed by the PC item, say a $500 door compared with a $440 PC amount, a variation will be required to cover the additional $60. If the PC item varies, so will the final contract sum. 
Provisional Sum – An amount of money included in contract sum to cover work and/or materials, not detailed when entering the contract. Typically builders will include a PS for site work costs. The builder is legally required to take reasonable steps to ensure an accurate site works cost estimate but unforeseen events mean that the provisional sum is exceeded which is added to the contract sum.
E.g. a building site may seem sand and clean with minimal siteworks required, however, there may be large limestone rocks/tree trunks concealed below the surface which only emerge once siteworks commence, causing cost overrun.  

	



[bookmark: _Ref428796325]Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

	Answer
	They only apply to long-term costs and some specific costs such as labour and materials, currency exchange rates for over-seas purchased goods, duties, taxes and shipping. 
	



[bookmark: _Ref495650899]True or False (Tick your response): Variations can be requested by both the client and the builder.

	Answer
		True 
	
	
	
		False 
	
	




Q3.  [bookmark: _Ref423508256][bookmark: _Ref527450478]How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

	Answer
	-A Variation in writing
- You to issue an ‘extension on time’ form – essentially asking the client to grant you an extension of the contract period to allow for delays caused by variations
- The specific reasons for extension of time are set out in the general conditions on the building contract and include reasons such as: inclement weather and delays caused by the owner, such as changes in the scope of works. 
- You should be familiar with the general contract conditions to you know what time extensions you are entitled to over the contract period. 

	




[bookmark: _Ref495652895]Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

	Answer
	Fair Trading Act 1989 Qld, applies to all parties involved in the contract. 
	



[bookmark: _Ref495653465]Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

	Answer
	- Make reasonable inquires about why you want to borrow the money
- Make reasonable inquiries about your financial institution 
- Take reasonable steps to verify your financial situation 
- Assess whether you can meet the financial obligations of the credit contract (and whether it will meet your needs) 
- Determine that the credit contract is ‘not unsuitable’ for you  
	



[bookmark: _Ref428776673]What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

	Answer
	You may withdraw from the contract within 5 business days after the day you receive copies of both the signed contract (including any plans and specifications) and this guide. However, there are costs for home owners in withdrawing (generally $100 plus any out of pock expenses reasonably incurred  by the contractor up to the time of withdrawal). The client must advise the contractor in writing that they are withdrawing under the cooling-off provisions in section 35 of schedule 1B of the QBCC Act.  
	




[bookmark: _Ref428779587]What are the maximum deposits recommended for a residential building project?

	Answer
	If the contract for domestic building work is priced at $20,000 or more, the maximum deposit is 5%. If the contract price is more than $3,300 and less than $20,000m the deposit must not exceed 10%.
	



[bookmark: _Ref428794433]Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

	Answer
	Deposit – 5%
Base stage – 15%
Frame stage – 20%
Enclosed stage – 25%
Fixing stage – 20%
Practical completion - 15%

	



Q4.  [bookmark: _Ref423508227]You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

	Answer
	No, I would not accept the deposit. As the residential contract is over $20,000 a maximum deposit of 5% is only allowed.  
	

[bookmark: _Ref423515882][bookmark: _Ref423515982]
Q5.  [bookmark: _Ref423504803]Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

	Answer
	Breach
	Explanation
	
	
	Breach of condition under contract
	These are essential terms. If a condition is not fulfilled, the nature of the contract is drastically changed. 
	

	
	Breach of warranty under contract
	If a warranty is not fulfilled, the nature of the contract is not drastically changed. 
	




[bookmark: _Ref428793813]What does repudiation of a contract mean?

	Answer
	Repudiation occurs when a party to a contract is unwilling to perform their contractual obligations – through acknowledgement or their actions are totally inconsistent with their obligations under the contract. 
	



[bookmark: _Ref528068459]True or False (Tick your response): In the event of repudiation, the injured party has two options:
· Continue with the contract
· Accept the repudiation and move to terminate the contract

	Answer
		True
	
	
	
		False
	
	




[bookmark: _Ref528068460]Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

	Answer
	As if the situation is not deemed to be repudiation, by acting to terminate the contract the ‘injured’ party may themselves be repudiating the contract and could be liable to pay damages.  
	


[bookmark: _Ref428794305]What does ‘abandonment of contract’ mean?

	Answer
	Where both parties have conducted themselves in such a way that the original construct is no longer valid. 
	



[bookmark: _Ref428793803]A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

	Answer
	Convenience – Where a party is unwilling to perform under the agreement (i.e. for reasons other than poor performance), this is deemed a termination of ‘convenience’.
Cause – Where one party fails to meet the terms of the contract (e.g. due to poor performance) the aggrieved party’s action may be deemed a termination for ‘cause’. 
	



[bookmark: _Ref495653458]Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

	Answer
		Yes
	
	
	
		No
	
	



[bookmark: _Ref428795233]If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

	Answer
	-What must occur to perform the contract
- A reasonable time in which the contract must be completed
- A statement of the consequences of not performing in accordance with the notice
	



[bookmark: _Ref528148821]True or False (Tick your response): Where the notice given (as per Q38. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

	Answer
		True
	
	
	
		False
	
	




[bookmark: _Ref428781925][bookmark: _Ref528152060]When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

	Answer
	Once practical completion is reached the final progress payment becomes due. Final payment can not be withheld as it is a contract breach. The builder has a contractual obligation to repair any minor defects, but this may not necessarily happen before handover although most builders would attempt to do so. 
	


[bookmark: _Ref428794091]Explain the concept ‘conditions for completion at the cost of the contractor’.

	Answer
	The contractor must make good defects or omissions in the work under this Contract which become apparent within 6 months of the Date of Practical Completion. 
If there are any such defects or omissions, the Owner must give the Contractor written notice to make good such defects or omissions with the 6 month period and must give the Contractor reasonable access to the site for that purpose. 
Subject to reasonable access being provided, the Contractor must within 28 calendar days of the notice being given rectify any defects notified to the Contractor during usual business hours. 
	



[bookmark: _Ref495653464]Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

	Answer
	Persons name (business address, phone number, email etc). 
	



[bookmark: _Ref428795566]Name one (1) person you should consult if you are considering ousting a contractor from a building site.

	Answer
	Lawyer 
	



[bookmark: _Ref428795533]What document should you refer to if you are considering ousting a contractor from a building site?

	Answer
	The dismissal procedure delineated in the contract. 
	




[bookmark: _Ref428776477]How should you handle a customer complaint?

	Answer
	- Deal with the complaint immediately
- Stay calm
- Identify the problem
- Decide what can be done
- Arrange a second opinion to confirm your view
- Keep Records 
- Fix the Problem 
	



[bookmark: _Ref428780523]How do you reduce the risk of dispute?

	Answer
	- Record all complaints
- Act promptly
- Do what you say you are going to do
- Do not make unrealistic promises 
	



[bookmark: _Ref428780789]What is the process for dispute resolution?

	Answer
	1.Always refer to your contract first which outlines all contractual details in order to:
- Determining responsibility for defects
- Directing the contractor (where appropriate) to rectify defects or complete the works
2.Seek legal advice to investigate your options before taking any of the below steps. This is particularly important if you intend to terminate the contract. 
3.QBCC or other building associations can assist you in reaching amicable solution with your building contract breakdown. 
4. The Queensland Civil and Administrative Tribunal provides cost effective dispute resolution for domestic building disputes of a contractual nature. The tribunal will hear any disagreement between yourself and your licensed contractor and may require the QBCC to provide a technical report.  
	


Q6.  [bookmark: _Ref423599342]During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

	Answer
	Dear Client, 

Thank you for your email. 

Please refer to the attached Contract and white goods and chattels list selected by yourself, the bath installed is what was selected. 

If you wish to discuss further, please do not hesitate to contact me. 

Kind Regards, 
Emilu Conlon 
	


[bookmark: _Ref428787470]Where would you find any possible penalties associated with a build?

	Answer
	There is an express term in the contract. 
	



[bookmark: _Ref528221530]Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

	Answer
	The final certificate is certification by the contract administrator that a construction contract has been fully completed. It is issued at the end of the defects liability period and has the effect of releasing all remaining money due to the contractor, including any remaining retention. 
Approvals for building work must be obtained from a building certifier, who can be either a local government building certifier or private certifier. 
To prepare and keep all Site Report and Inspections, write a summary of the overall condition of the site and stage of the building project. Make this summary short, no longer than three or four sentences and easy to read and always keep them within your other documents on-site.
One item you will receive prior to practical completion, is the Building Code Assessment Summary (similar to a Certification or Classification) from the Building Certifier which grants the right of occupancy to the building owners/users. The project sponsor and building owner receive a copy of this document, which must be kept available for inspection.
You should always provide the client with all certificate of inspection (including where appropriate, the ‘final’ certificate) prior to receiving the final payment. This can also be a mandatory requirement of your contract, so its important to be aware of the contract conditions. 
   
	


Q7.  [bookmark: _Ref423598913]Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:
· The land has been secured and paid for by the Clients.
· Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.
· Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured. 
· Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list. 
· The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.
· The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.
· Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build. 
· The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.
· The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.
· The construction period excluding inclement weather and possible delays is 23 weeks
· Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).
· Prime costs are required for the solar hot water system and ducted air conditioning
· Provide fictitious details for all other sections of the contract.
· 18 solar panels are to be installed on the roof


	Answer
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Emily Conlon

	
	

	Participant signature
	
	
	

	Date
	9/04/2022



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
		
	Task 1 (Occasion 2)
		



	ASSESSOR COMMENTS

	


CPCCBC4003A Select and prepare a construction contract,
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. 

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· Copy of a contract issued to sub-contractor for your project with relevant AS code on the front
· Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails)
· Copy of HSE minimum requirements sent as contract condition
· Construction contracts that have been developed, signed off, or contributed to by the candidate
· Proof of correspondence with client regarding construction contract. Redact sensitive information as required.

The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment.

	Resources required: 
Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer.

	Assessment of task

	Name of participant:
	Emily Conlon

	Name of observer:
	Amy Cowling

	Role of observer 
(Confirm suitability to sign)
	Project Administrator Manager 

	Email address of observer
	Amy.cowling@seecivil.com.au

	Signature of observer:
	
	Date:
	9/04/2022
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1.A.  [bookmark: _Ref495661944]Explain to the client:
· Essential terms and elements of a valid contract 
· Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements)
· The range of documents that collectively make up a contract (including construction schedules, reports, specifications)
· The importance of the contract to sales process 
· Implications of legislation, regulations and codes of practice (including Australian Consumer Law)
		
	1.B.  [bookmark: _Ref495662059]Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit.
		
	1.C.  [bookmark: _Ref495662068]Ensure the pre-contract agreement is signed and processed according to organisational requirements.
		
	1.D.  [bookmark: _Ref527380121]Select appropriate contract and seek expert advice in the preparation of the contract, considering:
· Contract rise and fall amounts
· Schedule of progress payments
· Processes for applying of extensions of time
		
	1.E.  [bookmark: _Ref495661995]Break down contract clauses/terms/conditions with the client, including:
· Rights, liabilities and potential penalties of parties under the contract
· Definitions of building work, common contract terms and procedures, considering – 
· Practical completion and issuing a final certificate
· Defects liability and completion at the cost of the contractor
· Effect of ousting the contractor from the building or site
· Cooling off periods
· Provisional sum and prime cost allowances
· Measures to be taken in the event of an anomaly in the rendering of the contract, considering – 
· Variations
· Circumstances that bring about a breach and termination of contract, considering – 
· Unreasonable/vexatious notice
· Abandonment of a contract
· Methods for resolving contractual disputes
		
	1.F.  [bookmark: _Ref495662164]Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods:
· Verbally using language/concepts appropriate to cultural differences
· Non-verbal communication
· Using technology (including telephone, facsimile, email)
· In writing (including drafting responses to queries about contracts)
		
	The participant’s performance was:  Satisfactory     Not Satisfactory



	OBSERVER COMMENTS

	Emily was competent in all tasks completed. 
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