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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Hamilton Hayden

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	For any building work valued over $3,300
For building work valued over $1,100 where it involves hydraulic services design.
For building work of any value which involves: drainage, plumbing, gas fitting, termite management, fire protection, completed residential building inspection, building design – low rise, medium rise and open, or site classification. 
	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	1. Have the electrical contractor contact the distribution network to see if supply is available.
2. If supply is not available, have the distribution network advise the cost and timeframe to make it available. (approx. 20 days to received answer)
3. If supply is available, have the electrical contractor enter into an agreement with the distribution network service provider. (approx. 10 days to received network connection offer).
4. The electrical contractor will submit an Electrical Work Request (EWR) to the distribution network once the work is complete. 
5. A copy of the EWR will be sent to the clients electricity retailer.
6. After work is complete, the distribution network service provider will visit the premises to inspect the work. (They typically need 5 days to do this).



	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	1. Check the contractual or legal requirements.
2. Submit a Water Approval application to the local water utility provider.
3. Once approval is given, have the plumbing contractor make the connection.
4. Notify the Local Water Utility Provider that the connection has been made so that they can inspect if necessary.

Standard connections for simple residential developments are usually completed in 5 days.

	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	Section J
	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Lower environmental damage through choice of building materials etc. or emissions via operations of the structure.
	

	
	Client benefit
	Lower energy costs for running the asset.
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Excavation
	Prepares the site for building by grubbing and excavating the foundations
	

	
	Electrician
	Arranges electricity to be connected; places wiring for lighting and power cables, fixes switches, installs power points, wires electrical systems.
	

	
	Plumbing
	Organises water supply; installs pipes and drains, installs roof and guttering, fits taps etc. ensures that downpipes and the swer is connected.
	

	
	Gas Fitting
	Places gas pipes to appliances
	

	
	Concreting
	Installs formwork and boxing; pours concrete (e.g. slabs).
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	3
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	4
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Demolition, Soil Testing, Civil Contractor
	

	
	
	Duration
	Varies depending on the site
	

	
	2: Slab or base stage
	Trades
	Excavation, Steel Fixer, Concretor
	

	
	
	Duration
	1 – 2 weeks
	

	
	3: Frame stage
	Trades
	Plumber, Electrical, Carpenter, Roofer, Insulation
	

	
	
	Duration
	3 – 4 weeks
	

	
	4: Lockup stage
	Trades
	Glazer, Carpenter, Electrician, Plumbing 
	

	
	
	Duration
	4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Joinery, Tiler, Fixings and Fittings 
	

	
	
	Duration
	5-6 weeks
	

	
	6: Practical completion stage
	Trades
	Decorator
	

	
	
	Duration
	7-8 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	Project size and location
Project Function
Height of the building
Building complexity
Quality Requirements
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	Can change construction methodology (different materials, labour, plant) and/or the program.
	

	
	Labour availability
	Different trades need to be sequenced so that personnel are used efficiently, i.e. painter not on site waiting for plasterer to finish.
Other major construction jobs in the area could be soaking up the available labour.
	

	
	Material availability
	Material is to be sequenced so that it is on site when it is needed, but not too early where it clogs the site or can be damaged by weather or construction works.
	

	
	Weather
	Weather can delay works, wind will stop cranes, rain will stop outdoor works.
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact dial before you dig to avoid any underground services
	

	
	Electricity
	Disconnect any previous power supply to the work zones and provide any needed temporary power
	

	
	Neighbours
	Advance notice of construction dates and contact numbers
	

	
	Waste disposal
	Set up designated rubbish bins and waste removal. Check if permits required to place bins on the street
	

	
	Water connection
	Book in a plumber to perform any required disconnections prior to demolition.
	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	Section 40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	Section 41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	[bookmark: _GoBack]Section 308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☐	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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