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CPCCBC4029B 
Apply construction information to the sales process
ASSESSMENT SUMMARY

The assessment activities for CPCCBC4029B Apply construction information to the sales process cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	Participant Name
	Bernadette Mau




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	

	Assessor Signature
	
	Unit Competence Determination Date
	Click here to enter a date.
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	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Bernadette Mau

	
	

	Participant signature
	
	
	

	Date
	19/02/2022



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	18
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	


	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	A building licence must be obtained in the following circumstances:
1.Any building work valued over $3,300
2.Building work valued over $1,100 where it involves Hydraulic Services       Design
3.Building work of any value where it involves:
      >Drainage
      >Plumbing and Drainage
      >Gas Fitting
      >Termite Management – Chemical
      >Fire Protection
      >Completed Residential Building Inspection
      >Building Design – Low Rise, Medium Rise and Open
      >Site Classification

	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	The electrical contractor will be able to advise if supply is available.
If the premise does not have supply available, the electrical contractor would complete an enquiry on the client’s behalf
The Distribution Network Service Provider would conduct the necessary network investigations and provide an indicative estimate of potential costs and timeframes for the client to make an informed decision within 20 business days

If there is supply available, the electrical contractor will need to enter into a Network Connection Agreement with the Distribution Network Service Provider
If the application is not expedited (e.g. by agreeing to the Model Terms and Conditions for Deemed Standard Connection Contracts), the Distribution Network will advise of a Network Connection Offer within 10 business days

After agreeing to the connection offer, the electrical contractor will prepare the premises for connection.
The electrical contractor will submit an Electrical Work Request (EWR) to the Distribution Network Service Provider once the work is complete
A copy of the EWR will be sent to the client’s preferred electricity retailer
Once all forms are received, the Distribution Network Service Provider will visit the premises to perform the requested work
The Distribution Network Service Provider must adhere to timeframes for new connections (e.g. Energex will attend the property within 5 business days)

	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	To connect or disconnect from the water and sewerage network or alter network infrastructure, you need to submit a Water Approval application
to Queensland Urban Utilities.
The Water Approval Process works in conjunction with the Council development assessment process, and applications do not need to be submitted at the same time.
Water and sewerage connection approvals are customised for all scales of development from a new house to a large factory or multi-stage residential sub-division
Where developers are proposing to connect to water and sewerage services, councils will require evidence that a connection is available 
Generally the evidence required, and therefore the relative timing of the two approvals, will depend on the complexity of the proposed development and the likely availability of services
Standard connections for simple residential developments are usually completed within five (5) days

	



[bookmark: _Ref496611496]Identify the Volume and Parts of the NCC which outline energy efficiency requirements for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	

	
	Volume 2 - Parts 2.6 & 3.12
	Volume 1 - Part J
	





[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Using sustainable building solutions such as recycled or durable low maintenance materials, energy efficiency solutions eg glazing, low voc paint etc would benefit the environment as there would be less waste & harmful chemicals used which are causing environmental hazards.  
	

	
	Client benefit
	The client would own an environmentally friendly building which would have long term savings and be a unique selling point if they wished to sell.    
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	
	True 
	
	
	
	
	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Excavation
	Prepares the site for building by removing existing  vegetation & footings.
	

	
	Electrician
	Arranges electricity to be connected & fixes all electrical requirements
	

	
	Plumbing
	Organises water supply, installs drains & pipes, installs roof & guttering, fits taps, toilets, hot water systems & ensures downpipes fitted & sewer connected.
	

	
	Gas Fitter
	Connects gas pipes to appliances
	

	
	Concreting
	Installs formwork & boxing and pours concrete.
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	3
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	4
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavation
	

	
	
	Duration
	Varies according to amount of work that needs to be undertaken to clear site
	

	
	2: Slab or base stage
	Trades
	Concreting, Plumber, Steel fixing
	

	
	
	Duration
	Approx 1-2 weeks
	

	
	3: Frame stage
	Trades
	Carpenter, Electrician, Plumber
	

	
	
	Duration
	Approx 3-4 weeks
	

	
	4: Lockup stage
	Trades
	Carpenter, Electrician, Plumber, Bricklayer
	

	
	
	Duration
	Approx 4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Carpenter, Electrician, Plumber, Bricklayer, Waterproofer, Tiler
	

	
	
	Duration
	Approx 5 -6 weeks
	

	
	6: Practical completion stage
	Trades
	Carpenter, Electrician, Plumber, Tiler, plasterer, Painter, Landscaper
	

	
	
	Duration
	Approx 7-8 weeks 
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	1. Project size
2. Project function
3. Height of the building 
4. Building complexity
5. Location
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	If the build requirements are changed then this will affect the timeframe of the build eg ordering extra materials & organising sub contactors
	

	
	Labour availability
	If a sub contractor has not been organised to start their part of the project when necessary then this will hold up other sub contractors with their part of the build. 
	

	
	Material availability
	If materials are not ordered in time for when the sub contractor is ready to start work this will delay the build.
	

	
	Weather
	Inclement weather will affect the ability of workers to complete their tasks on time. 
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact Dial Before You Dig before undertaking any excavation to ensure that services will not be damaged. 
	

	
	Electricity
	Electricity may need to be disconnected to work zones prior to construction & temporary utilities installed for duration of construction
	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers 
	

	
	Waste disposal
	Set up a designated area for rubbish bins & waste removal. Check if permits required to place bins on street.
	

	
	Water connection
	Organise a plumber to perform any required disconnections prior to commencement of demolition.
	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	
	Contractor
	

	
	
	Local Government
	

	
	
	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	
	Subcontractors
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Bernadette Mau

	
	

	Participant signature
	
	
	

	Date
	19/02/2022



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
		
	Task 1 (Occasion 2)
		



	ASSESSOR COMMENTS

	


CPCCBC4029B
Apply construction information to the sales process

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to apply construction information during the sales process in order to develop the customer’s knowledge of construction processes and the effects on the contract and building timelines. 

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· RFI and relevant correspondence with client
· A variation, price and acceptance by the client

The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document.

	Resources required: 
Two (2) sales contracts.

	Assessment of task

	Name of participant:
	Bernadette Mau

	Name of observer:
	Sekona Mau

	Role of observer 
(Confirm suitability to sign)
	Director

	Email address of observer
	sekona@gryphonscaffolding.com.au

	Signature of observer:
	
	Date:
	28/02/2022
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1.A.  [bookmark: _Ref496598588][bookmark: _Ref495661944]Identify and explain to the customer the approvals required before starting construction, including:
· Statutory approvals 
· Sustainability requirements
· Insurance covers
		
	1.B.  [bookmark: _Ref495662059]Identify and explain to the customer the stages and timeframes of construction, including:
· Main trade components
· Construction process sequence (including approximate duration)
		
	1.C.  [bookmark: _Ref495662068]Identify and explain to the customer potential industry conditions that can affect construction times.
		
	1.D.  [bookmark: _Ref495661995]Identify and explain to the customer site establishment requirements before starting construction.
		
	1.E.  [bookmark: _Ref495662164]Establish site access arrangements with the client.
		
	1.F.  [bookmark: _Ref496598868]Effectively communicate using the following methods:
· Verbally using language/concepts appropriate to cultural differences
· Non-verbal communication
· Active listening and responding to client questions
		
	The participant’s performance was:  Satisfactory     Not Satisfactory



	OBSERVER COMMENTS
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