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CPCCBC4007A 
Plan building or construction work 
ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	Participant Name
	




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	

	Assessor Signature
	
	Unit Competence Determination Date
	Click here to enter a date.
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	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	Caitlin Reid

	
	

	Participant signature
	
	
	

	Date
	13/08/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	45
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	




	ASSESSOR COMMENTS

	


Q1.  Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Building Approvals
	



Q2.  [bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	Building and Construction Commission Act 1991 (Qld) Section 33
	(T1) The building contractor under a regulated contract must not, before starting to provide the contracted services at the building site, demand or receive a deposit under the contract of more than—
(a)for a level 1 regulated contract (other than a contract mentioned in paragraph (c))—10% of the contract price; or (b)for a level 2 regulated contract (other than a contract mentioned in paragraph (c))—5% of the contract price; or
[bookmark: sch.1B-sec.33-ssec.3-def.deposit](c)for a level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price—20% of the contract price. Maximum penalty—100 penalty units. (2) In this section, a reference to the contract price for a contract includes, for a cost-plus contract, a reference to the estimated amount for the contract. (3)In this section— deposit, for a regulated contract, includes any payment for domestic building work demanded or received by the building contractor prior to the contracted services commencing at the building site, including, for example, any insurance premium paid under part 5.

	




Q3.  [bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Electrician
	Arranges electricity to be connected, places wiring for lighting and power cables, fixes switches, installs power points, wires electrical systems 
	

	
	Concreter
	Installs formwork and boxing, pours concrete, finishes concrete, cures concrete
	

	
	Carpenter
	Installs flooring, wall frames, roof trusses, windows, external doors and frames, decking and steps, attends to joinery and mouldings
	



Q4.  [bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




Q5.  [bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	You need to confirm the subcontractor or supplier for the job and lock them in via an agreement, if not your project will run out of the time period given and other subcontractors or suppliers may be delayed as well
	



Q6.  [bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	Advertising in the local newspaper or word of mouth through people you know
	



Q7.  [bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	Lead time on delivery and access to the correct amount of material needed
	


Q8.  [bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680.0
	



Q9.  [bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Ride on Road Roller
	A ride on road roller is a compacting engineering vehicle, used to compress soil, gravel or asphalt
	

	
	360 Degree Excavator
	An excavator, sometimes known as a digger or mechanical shovel, is used for everything from trenching, material handling and digging foundations to forestry, landscaping, mining and even river dredging
	




Q10.  [bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Ladder 
	A ladder is used for climbing up and down to reach a higher level safely
	

	
	Wheelbarrow
	A wheelbarrow is used for a variety of things such as moving rocks, mulch, plants, large shrubs etc from one spot to another 
	




Q11.  [bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	Written confirmation that the items have been designed, constructed and tested in compliance with applicable WHS legislation and an inspection record of the equipment from when it first arrived on site including photos  
	


Q12.  [bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Temporary fencing, temporary electrical pole, water tapping, waste bin, seepage barriers 
	



Q13.  [bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	    
	True 
	
	
	
		False 
	
	




Q14.  [bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




Q15.  [bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





Q16.  [bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	Ensuring the access is clear of any dirt piles or other items
	



Q17.  [bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 1 section 2.0.1
	Volume 2 Part 3.9
	




Q18.  [bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Out of Hours Construction; required is a site specific construction noise management plan, a copy of the letter that will be provided to the premises/residents whom are likely to be affect which must include after hours contact, date and times the construction activity will take place and the type of construction activity to take place
	



Q19.  [bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Foot Path Closure
	Site plan showing the location of proposed works and how pedestrians will navigate around proposed footpath in use, approved pans, site photos and traffic management, submitted to your local council 
	

	
	Plumbing Permit
	A floor plan of the proposed building showing any proposed plumbing fixtures, if the proposed work involves installing sanitary drainage you must also provide a site classification report of the premises and design work showing the  articulation of sanitary drainage for the premises, submitted to your local council
	



Q20.  [bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




Q21.  [bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	A purchase order
	



Q22.  [bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




Q23.  [bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	The Supplier
	



Q24.  [bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	Work Helath and Safety Act 2011 (QLD) section 17-18
	A duty imposed on a person to ensure health and safety
requires the person—
(a) to eliminate risks to health and safety, so far as is
reasonably practicable; and
(b) if it is not reasonably practicable to eliminate risks to
health and safety, to minimise those risks so far as is
reasonably practicable
	




Q25.  [bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	Work Health and Safety Regulation 2011 (QLD)
	


Q26.  [bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheet
	



Q27.  [bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10
	



Q28.  [bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




Q29.  [bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




Q30.  [bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	Subcontracting for multiple nearby jobs, keeps the subcontractor busy and your projects running smooth, for example, a carpenter can do a frame for one house, move to another house the next day, this keeps the carpenter busy and moving quick, while also allowing the other trades to move at the same pace, keeping everyone busy and projects on time
	




Q31.  [bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	Having an electrical and plumber fit off sequenced on the same days helps because the electrical work needs to be finished before the painting but the plumbing needs to be completed prior to the floor finishing job
	



Q32.  [bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




Q33.  [bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





Q34.  [bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
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B
A

	Answer
	

	



Q35.  [bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

Q36.  [bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




Q37.  [bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




Q38.  [bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





Q39.  [bookmark: _Ref432123]Describe the critical path.

	Answer
	The critical path is nodes 2, 4, 5, 6 this path has the most critical part of concrete pouring and curing, which can halt an entire job is not well prepared in advance 
	



Q40.  [bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




Q41.  [bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	Weather, lack of materials and if a subcontractor cancels their contract last minute
	



Q42.  [bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




Q43.  [bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	In case any disputes came into factor later down the track
	


Q44.  [bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




Q45.  [bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	If any damage has occurred through the construction process 
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Caitlin Reid

	
	

	Participant signature
	
	
	

	Date
	13/08/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
	
	

	Task 1 (Occasion 2)
	
	




	ASSESSOR COMMENTS

	


CPCCBC4007A
Plan building or construction work

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities:
· Occasion 1: Residential projects
· Occasion 2: Commercial projects

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· A construction program/schedule for a project showing:
· The sequencing of the trades, etc.
· Working and non-working days, etc.
· Local authority construction commencement notices
· Pre-construction site inspection reports or dilapidation reports
· WHS policy

The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document.

	Resources required: 
Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. 

	Assessment of task

	Name of participant:
	Caite Reid

	Name of observer:
	Brendon Joynson

	Role of observer 
(Confirm suitability to sign)
	Project Manager 

	Email address of observer
	Brendon.joynson@wcq.com.au

	Signature of observer:
	
	Date:
	13/08/2020
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1 Appraise contract documentation

	1.1A.  [bookmark: _Ref536514168]Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties.
		
	1.1B.  [bookmark: _Ref536514171]Determine availability of selected subcontractors to suit the job requirements. 
		
	1.1C.  [bookmark: _Ref536514174]Assess availability of materials and confirm with suppliers. 
		
	1.1D.  [bookmark: _Ref536514176]Identify site access requirements and limitations, taking action to facilitate entry. 
		
	1.1E.  [bookmark: _Ref536514185]Prepare documentation for authorities controlling construction work and determine project commencement date. 
		
	1.1F.  [bookmark: _Ref536514189]Implement procedures for controlling and recording site deliveries. 
		
	2 Construction operation strategies 

	1.2A.  [bookmark: _Ref536514201]Identify organisational strategies for implementing construction. 
		
	1.2B.  [bookmark: _Ref536514204]Implement procedures for recording the hire of plant and equipment. 
		
	1.2C.  [bookmark: _Ref536514207]Implement organisational WHS policies and procedures, including hazard and risk management.
		
	1.2D.  [bookmark: _Ref536514211]Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements.
		
	1.2E.  [bookmark: _Ref536514215]Follow procedures for the control of multiple projects. 
		
	3 Project schedule 

	1.3A.  [bookmark: _Ref536514218]Sequence construction operations. 
		
	1.3B.  [bookmark: _Ref536514221]Enter operation details into a manually prepared project schedule or computer-based software package.
		
	1.3C.  [bookmark: _Ref536514224]Define critical path of the project, revising as required.
		
	1.3D.  [bookmark: _Ref536514227]Adjust project timeframes to account for anticipated delays.
		
	4 Required resources

	1.4A.  [bookmark: _Ref536514241]Determine and document temporary services and site accommodation requirements.
		
	1.4B.  [bookmark: _Ref536514244]Determine and document plant requirements and availability, with reference to contract documentation.
		
	1.4C.  [bookmark: _Ref536514247]Determine and document on-site labour requirements, with reference to contract documentation. 
		
	5 Condition reports

	1.5A.  [bookmark: _Ref536514251]Complete reports on the condition of existing buildings and structures on adjacent site boundaries. 
		
	1.5B.  [bookmark: _Ref536514256]Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction.
		
	1.5C.  [bookmark: _Ref536514373]Effectively communicate using the following methods:
· Telephone, facsimile, email and in writing 
· Language/concepts appropriate to cultural differences
· Non-verbal communication
		
	The Participant’s performance was:  Satisfactory     Not Satisfactory





	OBSERVER COMMENTS

	Caite shows a great knowledge of planning building or construction work
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