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CPCCBC4007A 
Plan building or construction work


	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Caitlin Hamilton

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	45
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Project Plan Specifications
	



[bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	NSW Home Building Act 1989 - No 147  Part 2 Division 1 Section 8 

	Maximum deposit in NSW Building Law is 10%.  If the work is required to be covered under the Home Building Compensation Scheme, it is illegal for the contractor to ask for a deposit or other payment under the contract unless the cover has been taken out, and a certificate of the cover is given to you  Maximum penalty: 1,000 penalty units in the case of a corporation and 200 penalty units in any other case.
	




[bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Electrician
	Arranges electricity to be conntected, places wiring for lighting and power cables. Fixes switches, installs power points, wires electrical systems.
	

	
	Plumber
	Organises water supply. Installs pipes and drains, installs roof and guttering, fits taps, hot water systems and toilets. Ensure downpipes are fitted and the sewer is connected.
	

	
	Concreter
	Installs formwork and boxing, pours concrete (slabs)
	



[bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




[bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	Planning of plant and subcontractor availability for a job is critical to ensure programme is met and minimise delay to the job and cost. 
Trades must be available and planned accordingly for tasks i.e you can’t have painters in if plasterers have not completed their activities. 
	



[bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	· Phone around to find out who has good supplies
· Liaise with known suppliers that are resourceful and reliable


	



[bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	Supply Vs Demand
Transport / Shipping / Importing delays
	


[bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZ 1680 Part 0 2009 Interior Lighting – safe movement F4.4
	



[bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Excavator
	Excavation of the site, levelling.
	

	
	Elevated Work Platform
	Roofing / trusses, where scaffold is unable or unsafe to use.
	




[bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Ladder
	Access to work at height
	

	
	Wheelbarrow
	Move heavy materials around site easily
	




[bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	1. Condition report
2. Written confirmation that the items have been designed, constructed and tested in compliance with applicable WHS legislation and relevant Australian Standards, and will be supplied with the necessary safe-use information in English

	


[bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Temporary Electricity Pole
Fencing / barriers
Waste Bins
Tiger strips on overhead powerlines
Water tapping

	



[bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




[bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





[bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	· Ensure there is adequate room for trucks to stop and use lifting equipment such as forklifts from the side of the road onto the site.
· Excavation to ensure access is allowed

	



[bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 2 Part 2.5
	Volume 1 Section D
	




[bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Out of Hours permit, Noise Management Plan. Minimum of 10 working days required for council to assess and process the application. 
	



[bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Electricity Supply Permit
	AGL, Endeavour Energy, Origin and or Council potentially.
	

	
	Water Supply Permit
	Sydney Water
	



[bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	Purchase Order
	



[bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	The supplier
	



[bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	Work Health & Safety Act 2011 (QLD) 
Section 17-18
	This Act places duties on various individuals and parties within the workplace. The section indicates that risks should be identified and eliminated so far as reasonably practicable.
	




[bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	Work Health & Safety Act 2011
	


[bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheet
	



[bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10
	



[bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	Ability to use resources across multiple jobs to complete similar activities, saves time required for travel. Shared resources of plant and equipment reduces cost and time. I.e they can lay concrete while the concrete is curing at another site.
	




[bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	Construction operation must be sequenced for a successful construction and is your obligation under WHS Act, Regulations and Codes of Practice under common law.
A plasterer should be organised after all other trades have performed their tasks correctly. 

	



[bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




[bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





[bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
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[bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Excel, Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

[bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





[bookmark: _Ref432123]Describe the critical path.

	Answer
	The ‘critical path’ is defined as the shortest completion time possible to complete a job. Sets out the build and its stages. Details and records build timelines. 
Eg 1-> 2 -> 3 -> 4-> 5-> 6->
	



[bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	Delivery Delay from suppliers
Equipment breakdown
Inclement weather.

	



[bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




[bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	You should take photographs of site boundaries with neighbouring properties so all parties are made aware of the site status before work commences. This ensurfes you can easily identify if any damage has occurred through the construction process or if there is a dispute.
	


[bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




[bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	[bookmark: _GoBack]If there is damage to their properly as a result of construction process.
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