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Material Inspection Checklist

	Inspected by:
	Lucy Muston 

	Date:
	Dates as per date delivered below. 



	#
	Material
	Date delivered
	Quantity
	Quality
	Comment

	1. 
	Machinery fuel & consumables
	17/05/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Fuel and consumables delivered on time and in required quantities. Quality check confirmed compliance with specifications. Adequate buffer stock available to prevent disruptions to machinery operation.

	2. 
	Soil testing services booked
	30/05/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Soil testing conducted as scheduled. Results received and classification confirmed. No issues identified affecting project requirements.

	3. 
	Trucks for material export
	01/07/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Trucks arrived as scheduled on 01/07/2024. Capacity and condition checked meeting project requirements. No delays anticipated for material export.

	4. 
	Pipes, pits, and manhole materials
	
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	All materials delivered as scheduled. Checked for damage and compliance with specifications. No issues reported.

	5. 
	Bedding material (gravel, sand)
	26/05/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Early delivery received to allow for site preparation. Material quantity and quality verified; meeting required standards.

	6. 
	Backfill material (crusher dust, compacted fill)
	Ongoing deliveries as needed
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Deliveries scheduled in batches based on progress. First batch received 27/05/2024, with subsequent deliveries aligned with work sequence.

	7. 
	Hydraulic pipework, fittings, valves
	27/05/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	All components delivered on time. Inspection confirmed correct sizes and specifications. No defects noted.

	8. 
	Bedding material (sand, aggregate)
	26/05/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Arrived a day early to facilitate preparation. Material quality checked meeting grading requirements.

	9. 
	Concrete cutting tools & supplies
	28/05/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	All tools and supplies received before the scheduled start date. Equipment tested and ready for use. 

	10. 
	Reinforcement steel & formwork
	07/06/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Delivery received on time. Steel checked for correct grade and dimensions. Formwork inspected for defects, all in good condition. 

	11. 
	Concrete for piers
	As per pour sequence (First pour on 10/06/2024)
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Concrete delivery scheduled in line with construction progress. Slump test and quality checks to be performed before each pour.

	12. 
	Damp Proof Membrane & Reinforcement Mesh
	14/06/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Both the damp proof membrane and reinforcement mesh have been successfully delivered. The materials are on-site and ready for installation. Ensure proper storage and protection from the weather until installation.

	13. 
	Concrete Supply
	 As per pour plan (scheduled with bulk earthworks)
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	The concrete has been delivered as per the pour plan. Confirm that all preparations are complete and ready for the pour. Check the quality and quantity of the concrete to ensure it meets specifications before proceeding.

	14. 
	Blocks & Mortar
	28/06/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	The blocks and mortar have been delivered as scheduled. Ensure all materials are stored properly to avoid damage from weather or exposure. Ready for use in the construction of the blockwork and engaged piers.

	15. 
	Corefill Concrete
	As per pour dates (scheduled)
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Corefill concrete is scheduled for delivery according to the pour dates. Verify the delivery timing to ensure alignment with the pour schedule and confirm material readiness for placement.

	16. 
	Steel Beams, Rafters, Bracing
	08/07/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	The steel beams, rafters, and bracing have been delivered as scheduled. Ensure they are inspected for quality and stored in a safe location to avoid damage. Ready for installation according to the project timeline.

	17. 
	Purlins & Outriggers
	08/07/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Purlins and outriggers have arrived as planned. Confirm that the materials are ready for use and stored properly until installation begins.

	18. 
	Roofing Sheets & Insulation
	22/07/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Roofing sheets and insulation have been delivered. Ensure proper handling and storage to protect from weather and physical damage. Ready for installation according to the roof framing schedule. (Alternative roofing material as per variation)

	19. 
	Louvers & Door Frames
	23/07/2024 
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Louvers and door frames have been delivered as scheduled. Inspect the materials for any damage and ensure they are stored safely and securely until installation. Ready for fitting into the external façade.

	20. 
	Door Hardware 
	23/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Door hardware updated as per revised construction drawings. All components delivered in correct quantities and specifications. Installation to proceed as scheduled. 

	21. 
	Hose taps and fittings 
	23/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Hose taps and fittings have been delivered as scheduled. Inspect all components to ensure they are complete and undamaged. Store securely in a dry area until installation begins.

	22. 
	Electrical conduits and cables
	23/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Electrical conduits and cables have been delivered as scheduled. Inspect for any damage and confirm quantities match the requirements. Store in a secure and dry area until installation begins.

	23. 
	DB-XX, Emergency Lighting & Accessories
	22/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Distribution board (DB-XX), emergency lighting, and accessories have arrived on time. Verify all components are accounted for and in good condition. Ensure proper storage to prevent damage before fit-off.

	24. 
	Lockers (supplied by client) 
	19/08/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Lockers are to be delivered before the specified date to allow for installation as per schedule. Coordinate with the client to confirm delivery timing and inspect upon arrival to ensure all units are complete and undamaged. Store securely until installation begins.

	25. 
	Base Course & Concrete for Footpaths
	29/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Base course material and concrete have been delivered as scheduled. Ensure proper storage and handling to maintain material integrity. Ready for use in footpath construction.

	26. 
	750mm Rock for Protection Channel
	29/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Rock for the protection channel has arrived on time. Confirm the required quantity and proper placement for installation.

	27. 
	Topsoil, Turf & Landscaping Materials
	30/07/2024
	 Met agreed amount.
 Agreed amount not met.
 Enough buffer
	Met agreed:
 Dimensions
 Colour
 Weight
	Landscaping materials, including topsoil and turf, have been delivered as planned. Store appropriately to prevent contamination or drying out before installation. Ensure coordination with the landscaping team for timely placement.
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