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🛠 Project: 6x6 Colorbond Shed Installation
📍 Location: 16 Sheehan Street, Rockhampton
📅 Estimated Duration: 7–10 days
💲 Labour Rate: $33.50/hour
🔨 Total Labour Hours: 50 hrs
💲 Material Cost: $32,360

🗓 Detailed Project Schedule
	Day
	Task
	Duration (hrs)
	Labour Cost
	Notes

	Day 1
	Site preparation (clearing, levelling)
	5 hrs
	$167.50
	Remove debris, level ground, mark corners

	Day 2
	Excavation & formwork
	6 hrs
	$201.00
	Dig foundations, install formwork for slab

	Day 3
	Concrete slab pour
	6 hrs
	$201.00
	Pour and finish reinforced concrete

	Day 4
	Slab curing, delivery check, framing prep
	3 hrs
	$100.50
	Light work while slab cures; inspect material delivery

	Day 5
	Wall frame assembly
	7 hrs
	$234.50
	Erect side and rear walls, secure to slab

	Day 6
	Roof trusses and sheeting
	7 hrs
	$234.50
	Install rafters and Colorbond roof sheeting

	Day 7
	Cladding, guttering, flashings
	6 hrs
	$201.00
	Wall cladding, waterproofing elements

	Day 8
	Doors, windows, internal finishing (if any)
	5 hrs
	$167.50
	Install roller/sliding doors, add optional internals

	Day 9
	Electrical/lighting prep (optional)
	3 hrs
	$100.50
	Placeholder if power included—licensed sparky needed

	Day 10
	Final inspection & site clean-up
	2 hrs
	$67.00
	Quality check, cleanup, removal of debris



💰 Cost Summary
	Item
	Cost

	Labour (50 hrs @ $33.50/hr)
	$1,675.00

	Materials (Colorbond, slab, fittings)
	$32,360.00

	Total Estimated Cost
	$34,035.00
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