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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Everett Putney

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work in Queensland.

	Answer
	· Any building work valued over $3,300
· Building work valued over $1,100 where it involves Hydraulic Services Design
· Building work of any value where it involves:
· Drainage
· Plumbing and Drainage
· Gas Fitting
· Termite Management – Chemical
· Fire Protection
· Completed Residential Building Inspection
· Building Design – Low Rise, Medium Rise and Open
· Site Classification

	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes, assuming the site is in South East Queensland.

	Answer
	· Your electrical contractor will be able to advise if supply is available
· Should the premise not have supply available, the electrical contractor can complete an enquiry on the client’s behalf
· The Distribution Network Service Provider (e.g. Energex) will conduct the necessary network investigations and provide an indicative estimate of potential costs and timeframes for the client to make an informed decision within 20 business days
· If there is supply available, the electrical contractor will need to enter into a Network Connection Agreement with the Distribution Network Service Provider
· If the application is not expedited (e.g. by agreeing to the Model Terms and Conditions for Deemed Standard Connection Contracts), the Distribution Network will advise of a Network Connection Offer within 10 business days
· After agreeing to the connection offer, the electrical contractor will prepare the premises for connection
· The electrical contractor will submit an Electrical Work Request (EWR) to the Distribution Network Service Provider once the work is complete
· A copy of the EWR will be sent to the client’s preferred electricity retailer
· Once all forms are received, the Distribution Network Service Provider will visit the premises to perform the requested work
· The Distribution Network Service Provider must adhere to timeframes for new connections (e.g. Energex will attend the property within 5 business days)


Using Energex in our local area - this process has taken up to 25 weeks noting most of our sites require a Transformer to be delivered. Connected and energised. DNSPs are extremely volatile in their processes and they can change at the drop of a hat to suit their workload.

	


[bookmark: _Ref496611484]Name two (2) types of approvals that may be sought for the building approval stage.

	Answer
	Water approval application
Electrical supply permit

	



[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes, assuming the site is in South East Queensland.

	Answer
	· If you would like to connect or disconnect from the water and sewerage network or alter network infrastructure, you need to submit a Water Approval application
· On the Sunshine Coast, this application is submitted to UNITY WATER
· The Water Approval Process works in conjunction with the Council development assessment process, and applications do not need to be submitted at the same time
· Water and sewerage connection approvals are customised for all scales of development from a new house to a large factory or multi-stage residential sub-division
· Where developers are proposing to connect to our water and sewerage services, councils will require evidence that a connection is available 
· Generally the evidence required, and therefore the relative timing of the two approvals, will depend on the complexity of the proposed development and the likely availability of services
· Standard connections for simple residential developments are usually completed within five (5) days
UNITY WATER applications at the DA stage can take 6 weeks for approval. Private works applications require at least 25 business days

	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	Section J
	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Less power consumption to warm/cool the building due to energy efficient building practices such as insulation
	

	
	Client benefit
	Less power consumption to cool/heat the building and can fall into a certain energy efficient star rating which can be attractive to buyers
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Electrical
	Responsible for all electrical items on site such as lighting, power supply, lighting fixtures
	

	
	Mechanical
	Responsible for all mechanical items on site such as AC, intake/fresh air, mechanical switch boards/controls
	

	
	Plumbing/Hydraulic
	Responsible for all hydraulic/sanitary items on site such as water, sewerage, plumbing fixtures
	

	
	Concreter
	Pours and finishes concrete in accordance with plans (falls, broom finish, colour etc.)
	

	
	Formworker (commercial)
	Installs and signs off on formwork for major concrete poured to ensure alignment with plans
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	1
	Floor frame
	

	
	6
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	2
	Set out
	

	
	9
	Painting
	

	
	5
	Electrical wiring
	

	
	4
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	3
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavation, surveyor, soil testing
	

	
	
	Duration
	varies
	

	
	2: Slab or base stage
	Trades
	Concreter, steel fixer, surveyor, plumber, electrician, mechanical (if under slabs required), pest control
	

	
	
	Duration
	1-2 weeks depending on the size
	

	
	3: Frame stage
	Trades
	surveyor, plumber, electrician, mechanical, carpenter (any further in wall services required – data/NBN for example)
	

	
	
	Duration
	3-4 weeks depending on the size
	

	
	4: Lockup stage
	Trades
	Windows/doors, garage door, internal lining and all fitout trades
	

	
	
	Duration
	4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	All fitout trades: plumber, electrician, mechanical, carpenter
	

	
	
	Duration
	5-6 weeks
	

	
	6: Practical completion stage
	Trades
	Painter, carpenter, flooring, cleaners, landscapers
	

	
	
	Duration
	7-8
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	size
function
height of the project
complexity
quality required (finishes)
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	If the requirements of the job are altered, this will change the initially projected timeframes, especially where additional materials and labour must be organised
	

	
	Labour availability
	The construction process sequence is very important when organising the required labour. For example, a plasterer should only be organised after all other trades have performed their tasks correctly – electricians and plumbers will not be able to access behind the walls as easily once the plasterer has put them up
	

	
	Material availability
	You must liaise with sub-contractors and suppliers to ensure materials are delivered when the sub-contractor is ready to complete their work. Materials that are rare or difficult to source should be ordered well in advance.

	

	
	Weather
	Weather will affect the ability of trades to complete their jobs on time.

	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact Dial Before You Dig before undertaking any excavation to ensure that services will not be damaged during construction.

	

	
	Electricity
	Electricity may need to be disconnected from work zones prior to construction and temporary utilities installed for the duration of the construction process.

	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers.

	

	
	Waste disposal
	Set up a designated area for rubbish bins and waste removal. Check if permits are required to place bins on the street.

	

	
	Water connection
	Book in a plumber to perform any required disconnections prior to any demolition taking place.

	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations 2011 (Qld) that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	Access & Egress
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	Site facilities
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	Signage
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Queensland Building and Construction Commission
	

	
	☐	Subcontractors
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