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CVM Building Extension Projects

ID Task Name Duration  [Start Finish % Complete |Predecesso|Resource Names  |»qg August 2020 | september 2020 | October 2020 | November 2020
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150 Muster Building Extension 144days Mon 2/03/20 Wed 16/09/20 18%
156 Design and Engineering 45 days Sun 24/05/20 Fri 24/07/20 30% |
157 Architectural 40 days Sun 24/05/20 Fri 17/07/20 0% Dezign El its ]
161 IFC Design 5 days Mon 13/07/20 Fri 17/07/20 0% 181,177,1 Dezign Elements ‘__D}zign Elements
162 Civil, Structural, Hydraulics 45 days Mon 25/05/20  Fri 24/07/20 50% Patcol
164 100% civil/structural design 8 days Tue 30/06/20 Thu9/07/20 75% Patcol tcol
165 100% Hydraulic Design 8 days Tue 30/06/20 Thu9/07/20 88% Patcol tcol
166 IFC Civil/structural/Hydraulic design 5 days Fri 10/07/20 Thu 16/07/20 0% 164,165 Patcol col
167 Building Compliance assessment 5 days Mon 20/07/20 Fri 24/07/20 0% 157,166 Patcol col
168 Electrical 25 days Fri 19/06/20 Thu 23/07/20 19% BRS 1
169 100% Detailed Design 5 days Tue 7/07/20 Mon 13/07/20 80% 177 BRS S
170 100% Lighting Design 2 days Tue 7/07/20 Wed 8/07/20 0% 177 BRS
172 100% Power Layout 2 days Mon 20/07/20 Tue 21/07/20 0% 161 BRS BRS
173 Final Load Demand Calcs (With HVAC Finalised) 10days  Tue 7/07/20 Mon 20/07/20 0% 177 BRS RS
174 IFC Design 2 days Wed 22/07/20 Thu23/07/20 0% 169,170,1BRS S
175 HVAC 11 days Fri 26/06/20 Fri 10/07/20 50% Air Construct T
177 100% HVAC Design + Electrical Loads Odays  Tue7/07/20  Tue7/07/20  100% Air Construct 7/07
178 IFC Design 4 days Tue 7/07/20 Fri 10/07/20 50% 177 Air Construct *#MI‘UCt
179 Fire Detection Systems 24 days Tue 16/06/20 Fri 17/07/20 0% FSI
181 100% Design (With Final ligting and HVAC ceiling 2 days Thu 9/07/20 Fri 10/07/20 0% 180,170 FsI i—L
plans)
182 IFC Design 5 days Mon 13/07/20 Fri 17/07/20 0% 181 FsI ES|
183 Construction Phase 69 days Mon 15/06/20 Wed 16/09/20 14% I
184 Building Construction 63 days Mon 15/06/20  Tue 8/09/20 14% MM 1
185 Off-Site Building Fabrication 25 days Fri 19/06/20 Thu 23/07/20 44% MM )
189 NDT Testing 1day Tue 7/07/20 Tue 7/07/20 0% 187FF MIM
190 Painting of Steelwork 3 days Wed 8/07/20  Fri 10/07/20 0% 189 MIM
191 Building Framing 3 days Mon 13/07/20 Wed 15/07/20 0% 190 MIM
192 Flooring Joists, decking, coverings 2 days Thu 16/07/20  Fri 17/07/20 0% 191 MIM
193 External Walls - Cement Fibre Sheeting 1day Mon 20/07/20 Mon 20/07/20 0% 192 MIM
194 Roofing 1day Tue 21/07/20 Tue 21/07/20 0% 193 MIM
195 Insulation 1day Wed 22/07/20 Wed 22/07/20 0% 194 MIM
196 External Windows, doors 1day Tue 21/07/20 Tue 21/07/20 0% 193 MIM
197 Misc items 2 days Wed 22/07/20 Thu23/07/20 0% 194 MIM
202 Civil Works 17 days Thu 25/06/20 Fri 17/07/20 69% MM
207 Concrete Curing (5 days) 5 days Thu 2/07/20 Wed 8/07/20 100% 206 MM
208 Measure and fab posts 7 days Thu 9/07/20 Fri 17/07/20 25% 207 MIM
209 Buildings landed at Site 12 days Fri 10/07/20 Sat 25/07/20 0% MM
210 Crane Lift Study Completed and Approved 1day Fri 10/07/20 Fri 10/07/20 0% 185FS-2 wSurelift
211 Site Notice Issued 1day Tue 21/07/20 Tue 21/07/20 0% 185FS-3 d BMA
212 Crane set-up onsite 1day Fri 24/07/20 Fri 24/07/20 0% 185,202 Surelift
213 Landing modular buildings at Site 1day Sat 25/07/20  Sat25/07/20 0% 202,212 MIM
214 Site Building Works 25 days Mon 27/07/20  Fri 28/08/20 0% MM | I,
215 External wall cladding at module joints 2 days Mon 27/07/20 Tue 28/07/20 0% 209 MM MJM
216 Roof connection and flashings 2 days Mon 27/07/20 Tue 28/07/20 0% 209 MM MJM
217 Internal wall framing and partitions 3 days Wed 29/07/20 Fri31/07/20 0% 215,216 MIM MJM
235 HVAC Install 41 days Mon 13/07/20  Fri 4/09/20 0% Air Construct |
237 Supply of Air Conditioning Units 20days Mon 13/07/20 Thu6/08/20 0% 175 Air Construct ‘*Mmstrud
253 Internal Fit-Out 23 days Fri 31/07/20 Tue 1/09/20 0% BMA | I
254 Procure Furntiture, IT equipment, Misc packages 20 days  Fri31/07/20 Fri 28/08/20 0% 157,255SFBMA _ﬂ‘\
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