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CPCCBC4007A 
Plan building or construction work


	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.
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	ASSESSOR COMMENTS

	


Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Project plan specifications
	



[bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	In Quesnland: Queensland building and construction commission Act 1991 Section 33

	· The building contract must not demand or receive a deposit under the contract of more than:
-Level 1: 10% of contract price
- Level 2: 5% of contract price
Level 1 and 2 under which the value of off – site work is more than 50% of the contract price 20 % of the contract price

Maximum Penalty: 100 penalty points

	




[bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Electrician
	Arranges electricity to be connected; places wiring for lighting and power cables; Fixes switches, installs power points, wires electrical systems.

	

	
	Plumbing
	Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected.

	

	
	Concreting
	Installs formwork and boxing; pours concrete (e.g. slabs).

	



[bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




[bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	Its important to understand under the contract time line and cost involved in the construction. Its important to know that subcontractor or plant available at the time when they require otherwise it will impact the whole programme cost and completion time.
	



[bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	· Phone around to find out who has good supplies
· Liaise with known suppliers that are resourceful and reliable

	



[bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	Working in a new area
Imported material

	


[bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680
	



[bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Excavator
	Prepares the site for building by removing all vegetation and excavating footings
	

	
	Roller
	To smooth the surface or compaction
	




[bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Cut saw
	To cut tiles or concrete slab
	

	
	wheelbarrow
	To transport material onsite
	




[bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	· Records of the invoices and receipts associated with the hire of plant
· Inspect plant/equipment with the hire company upon arrival to site and record the details of the inspection. 

	


[bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Temporary electrical pole or power box

Water tapping

Temporary fencing

Barricades 

Waste bin

	



[bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




[bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





[bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	· Check if excavation works need to be undertaken to enable access for machinery. 
· If this is the case, barriers may be required for additional protection of footpaths against water, mud and soil.

	



[bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 2 – 2.5 safe movement and access
	Volume 1 SECTION D ACCESS AND EGRESS
	




[bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Application required to apply for the out of hour permit for construction activities and the time frame 

It takes up to 10 working days for the application to be approved
	



[bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Lane or Road Closure Permit  
	LOCAL COUNCIL OR STATES ROAD
	

	
	Water
	[bookmark: _GoBack]Sydney water
	



[bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	Purchasing process - purchase order book  form
	



[bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	Supplier
	



[bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	Sections 17-18 of the  Work Health and Safety Act 2011
	The Work Health and Safety Act 2011 (Qld) places duties on various individuals and parties within the workplace. Sections 17-18 of the Act indicates that risks should be identified and eliminated, so far as is reasonably practicable (or otherwise minimised so far as is reasonably practicable).

	




[bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	WHS Regulation 2017 NSW

Part 2.3 cessation of unsafe work
	


[bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	SDS 
	



[bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10
	



[bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	Its time saving and cost saving if we use the same subcontractor on multiple project

Such as earthworks on multiple project site required

Concreting works on multiple site
	




[bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	It needs to be sequenced to hire required equipment labour and plant.

To ensure tradies and other workers can complete their task
	



[bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




[bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





[bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
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[bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Excel
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

[bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





[bookmark: _Ref432123]Describe the critical path.

	Answer
	1 – 2 – 4 – 5 – 6 – 7 -8 - 9
	



[bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	Poor Project management
Delivery delays
Approval delays
Equipment breakdown

	



[bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




[bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	To support your report 
This will ensure the information is accurate in case of dispute.
	


[bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




[bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	May include damage to the property as a result of construction process
	



Page 4 of 16	CSTC Pty Ltd_0699_v1-3_02/05/2019

CSTC Pty Ltd_0699_v1-3_02/05/2019	Page 3 of 16
image2.png
Enquiries,
orders

Wait
bricks.

Clear
site

o)

Wait
concrote





image3.png




image4.png




image5.png
Enquiries,

vaitbrcs oy Load bricks

3

Clear site.

concrete

T





image1.png




