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CPCCBC4007A 
Plan building or construction work


	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Miljan Tepic

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	


[bookmark: _GoBack]
	Date
	26/09/2019




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	45
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Project Plan Specifications
	



[bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	QBCC Act 1991 Schedule 1B
Section 33
	Must not receive deposit under contract of more than:
-for level 1: 10% of contract sum
-for level 2: 5% of contract sum
-level 1 or 2 under which the value of off-site work is more than 50% of the contract price 20% of contract price

Maximum penalty: 100 penalty points
	




[bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Plumbing
	Organises water supply, installs pipes and drains, installs roof guttering, taps and toilets, sewer connections.
	

	
	Concreting
	Installs formwork and pours concrete.
	

	
	Carpentry
	Installs flooring, wall frames, roof trusses, windows, external doors and frames, decking and steps and other joinery.
	



[bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




[bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	It is important in order to be able to adequately resource a project. Understanding availability will allow you to plan and progress a project accordingly and also find out if you may have resourcing issues in which case you may need to find alternative subcontractors or plant to ensure your project is resourced for completion in a timely manner.
	



[bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	-Find a local supplier by utilising online resources such as Google, Yellow Pages etc.
-Attend industry events and exhibitions to find suppliers and examine their products.
-Word of mouth from industry contacts.

	



[bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	-Material manufacture. Some materials are held in high stock while others are made on demand with lead time becoming a major factor.
-Material location. Some materials are stored locally while others are interstate or overseas.
	


[bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680
	



[bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Excavator
	Levelling the site to achieve grades and levels. Digging trenches to lay plumbing and other services.
	

	
	Crane
	Used to lift materials and supplies onto site; lift elements in place such as beams and pre-cast panels etc.
	




[bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Ladder
	Used to access areas difficult from floor levels. I.e. ceilings, roofs etc.
	

	
	Wheelbarrow
	Used to move items and material around site. I.e. soil, aggregates etc.
	




[bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	-Invoices
-Receipts
-Inspection records
	


[bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	-Power
-water
-fencing
-barricades
-seepage barriers

	



[bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




[bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





[bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	Traffic control.
	



[bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 2: Section 2.5 & 3.9
	Volume 1: Section D
	




[bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Brisbane City Council – compliance assessment for out of hours construction approval.
Required documentation includes a site-specific Construction Noise Management Plan and a copy of the notification letter to be provided to affected residents.
Minimum of 10 working days is required for assessment of application.
	



[bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Building approval
	Approving body is Council
Docs: Development application, plans, specifications etc.
	

	
	Sydney Water building plan approval
	Approval body is Sydney Water
Docs: application and plans
	



[bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	Purchase order
	



[bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	Supplier
	



[bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	Schedule 2E
	Environmental Protection Regulation 2008 (Qld) Waste handlers must submit waste tracking information when transporting regulated waste or waste residues.
	




[bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	Work Health and Safety Act 2011 NSW
	


[bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheet (SDS)
	



[bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10
	



[bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	Major advantage is saving time by utilising the same subcontractor and not needing to look for new subcontractors.
	




[bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	The construction process sequence is very importance when organising the required labour as some work cannot be completed unless certain work occurs beforehand. For example, a plasterer should only be organised after all other trades have performed their tasks correctly including electricians and plumbers otherwise they will not be able to access behind the walls as easily once the plasterer has put them up.
	



[bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




[bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





[bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
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[bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

[bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





[bookmark: _Ref432123]Describe the critical path.

	Answer
	The ‘critical path’ – the longest sequence of activities in a project (which determines the shortest possible completion time if all events are to be completed)

	



[bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	-Breakdowns i.e. plant
-Poor project management
-Inclement weather
	



[bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




[bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	If work is to affect neighbouring properties, you are required to compile a report on the condition of existing buildings and structures on adjacent site boundaries. Photos will provide evidence for your report which will be helpful in the event of a dispute with a neighbour.

	


[bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




[bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	Condition reports should be forwarded onto owners of adjacent buildings prior to commencing construction. That way, all parties are aware of the site status before work commences and can easily identify if any damage has occurred through the construction process.
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