PRACTICAL ACTIVITY 2


DEVELOPMENT APPLICATION REPORT

Document submissions required prior to commencement of construction:

16(a) Implement Protection Measures 
20(a) Transport Noise Corridor Design 
22) Construction Management Plan (Minor) 
25(a) Submit Earthworks Drawings 
33(a) Submit Plan of Subdivision 
33(b) Lodge Notated Plan 
34(a) Submit Site Drainage Drawings 
36) Water Approval 

Meetings required prior to commencement of construction:

16(a) Implement Protection Measures 
22) Construction Management Plan (Minor) 
31(a) Arrange Refuse Collection 
37) Service Conduits and Mains 

Inspections and approvals required during construction:

1) Approved Drawings and Documents 
3) Overall Height - Survey Certification 




























PRACTICAL ACTIVITY 3

Contract Variation                                                                   Date: 06/03/2022

Variation details:

The construction of a pointed brick fence at the front end of the house, approximately 43m long x 1.5m heigh with engaged piers every 2m.

Works to be completed:

· Pointed brick fence 43m in length x 1.5m in height
· Engaged piers every 2m
· Concrete footing 43m x 0.6m x0.4m
· Stater bars at every engaged pier


Cost:

Pointed brick fence with engaged piers: $8452.5 + GST

Concrete Footings with stater bars: $4945 + GST

Total variation cost: $13397.5 + GST

Delays:

I estimate that the variation works will delay contractual works for a minimum of minimum of 6 working days subject to delivery of materials and any other unforeseen circumstances.












Date and Signature:

06/03/2022
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