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	Construction Scope of Work:
	Concrete footpath entering the BESS fence area adjacent to main entrance sliding gate

	Proposed Date of Works:
	Friday 26th and Saturday 27th September 2025

	Scope
	Friday 26th – Site Establishment, excavation and formwork
Saturday 27th – Concrete pour, smooth and level and demobilise site

	Job Durations:
	2 days

	Location:
	305 Swanbank Road Swanbank 4306 QLD

	Area:
	North-West corner of the fenced BESS Area

	Contractor Support
	DM Coastal undertaking the scope of works.
New worker to contact Project HSE Specialist to complete the site induction.
Attend Prestart Meeting at 06:30 am.

	Personnel:
	· Contractor Supervisor
· Contractor Excavator Operator
· Contractor Carpenter (x2)
· Contractor Concreter (x2)
· Concrete Delivery Driver
· Contractor Concrete Tester

	Plant & Machinery:
	Excavator.
Concrete Truck.
Tipper Truck and Trailer.
Rammer Compactor.

	Construction materials
	Suppliers – Boral (DMG) or Hy-tec Concrete Boral (DMG).
Wet concrete approximate total volume is 6 cubic metres. Approximate Delivery time 07:00am.
Reinforced Steel mesh.

	Concrete Area
	13m (length) x 3m (width) x 0.15m (Thickness)

	Hazardous Chemical
	Wet mix concrete SDS
Concrete Form Release Agent SDS

	Waste Disposal
	Wash Bay 01 - Concrete wastage or wash down

	Applicable HSE Documentations
	Safety Management Plan
Construction Environmental Management Plan
Vehicle Movement Plan
SWMS Conduit Installation In Ground
SWMS Excavator Operation
SWMS Concreting
SWMS Excavation
Excavation Permit
Hazchat

	Design Drawing
	SBK-DRW-2025-008

	Performance Task Monitoring
	SWMS Observation YUR1020
Inspection and Test Plan

	

	Job Planning completed by 

	NAME: Sooty Phomsouvanh
	Date: 19/09/2025
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