


Physical Resources Costing Form

Instructions to the Assessor
The candidate will review the construction drawings and specifications from Task 1. They will then use this Physical Resources Costing Form to document the required physical resources, their prices, and their costs in completing the building.

Instructions to the Candidate
Use this Physical Resources Costing Form to document the required physical resources, their prices, and their costs in completing the building.
Ensure you have completed all fields in this form before submitting it to your assessor.

	PHYSICAL RESOURCES COSTING FORM

	[bookmark: _Hlk41586099]Candidate name
	Noreen Abu-Obeid

	Workplace/organisation
	Knights Construction

	Date of inspection
	30/12/2022



Details of the Building and Construction Project
	Workplace/organisation
	Knights Construction

	Name of building and construction project
	Sandgate Road, Nundah

	Type of project 
	X Residential building
 Commercial building

	State/territory
	QLD
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Section 1 – Physical Resources Required
	Equipment (Add rows as needed to account for all equipment needed in completing the building)

	Concrete pump $5405

	Site bin $2760

	Scaffolding $2167

	Storage on site $560




	Machinery (Add rows as needed to account for all equipment needed in completing the building)

	Crane $2485

	Excavator – excavation $3398

	Excavator – grader $1410




	Other Plant for Hire (Add rows as needed to account for all equipment needed in completing the building)

	Blaster $1105

	Compactor $780

	TOTAL for Equipment, Machinery and other Plant for Hire is $20070




Section 2 – Physical Resource Usage Details
(Duplicate tables to account for all equipment, machinery, and other plant for hire identified)
	Equipment: Concrete pump

	Limitations (Add rows as needed to account for all limitations of equipment)

	Used for concrete slabs

	Footpaths

	Has a medium flow rate

	Flexible hose pump

	 Enhanced mobility

	Reaches 30-50ft

	Conditions of Use (Add rows as needed to account for all conditions of use of equipment)

	Over 18

	Have high risk work license

	Small scale construction

	Operational Costs (Add rows as needed to account for all operational costs of use of equipment)

	Associated Cost
	Cost

	Slurry charge
	$20

	Pump rate
	$840

	Operator wage $235 per hour x 8 hrs
	$     $1880

	Schedule of Usage (Add rows as needed to account for all instances of using equipment)

	Date
	Time

	1 days
	8 Hrs per day

	Price of Hiring
	$2200

	Price of Transporting to Construction Site
	$465



	Equipment: Skip Bins

	Limitations (Add rows as needed to account for all limitations of equipment)

	Dropped on site in an allocated space within the property and does not interfere with the walkway

	To be collected at the end of the period hired for

	Conditions of Use (Add rows as needed to account for all conditions of use of equipment)

	You can dump household rubbish, green waste, office and commercial waste, concrete, bricks. Cardboard and shed cleanouts, bathroom renovations can also be disposed of in the bins

	No hazardous waste like car tyres or paint tins,no flammables like gas bottles or petrol cans, motor parts can be disposed of in skip bins

	No asbestos in the bins 

	Operational Costs (Add rows as needed to account for all operational costs of use of equipment)

	Associated Cost
	Cost

	Skip bin 6 cubm $690 per day x 4 days
	$2760

	Schedule of Usage (Add rows as needed to account for all instances of using equipment)

	Date
	Time

	4 skip bins
	Replaced when full

	Price of Hiring
	$2760

	Price of Transporting to Construction Site
	Inclusive in above price



	Equipment: Scaffolding

	Limitations (Add rows as needed to account for all limitations of equipment)

	2.5 m platform width

	Aluminium with ladder included

	4 x 200mm wheels with 450mm extension

	Has guardrails and handrails

	Conditions of Use (Add rows as needed to account for all conditions of use of equipment)

	Includes instructions, diagrams for ease of users for reference

	Follow and erect using the erection procedure manual 

	Is lockable, tamper proof, secure and easy to erect and use

	Operational Costs (Add rows as needed to account for all operational costs of use of equipment)

	Associated Cost
	Cost

	Tag 
	$11

	Return to depot
	$88

	Schedule of Usage (Add rows as needed to account for all instances of using equipment)

	Date
	Time

	3 weeks
	8 Hrs per day

	Price of Hiring
	$1980

	Price of Transporting to Construction Site
	$88



	Equipment: Storage on site

	Limitations (Add rows as needed to account for all limitations of equipment)

	Front opening with shelves and can access tools at top and bottom easily

	Top can be used as workbench

	Constructed with non combustible 2mm heavy duty steel

	Conditions of Use (Add rows as needed to account for all conditions of use of equipment)

	For storing hand and power tools

	New security system 

	Mobile on 2 fixed and 2 swivel casters with concealed door hinges and screw cups in doors

	50mm hole in floor to allow for power lead to be run in for recharging power tools overnight while locked

	Operational Costs (Add rows as needed to account for all operational costs of use of equipment)

	Associated Cost
	Cost

	nil
	

	Schedule of Usage (Add rows as needed to account for all instances of using equipment)

	Date
	Time

	days
	Hrs per day

	60
	8 hr days

	Price of Hiring
	$475

	Price of Transporting to Construction Site
	$85




	Machinery : Crane

	Limitations (Add rows as needed to account for all limitations of equipment)

	Lifting capacity for trusses to be lifted safely – can lift heavy trusses 

	Increased safety and efficient use in lifting heavy trusses into place

	Ensure you are clear of any hazards on site such as trees, power lines etc to reduce risk of accident or injury 

	Ensure safe and clear access

	Conditions of Use (Add rows as needed to account for all conditions of use of equipment)

	Over 18

	Have high risk work license and operated by experienced personnel

	Operational Costs (Add rows as needed to account for all operational costs of use of equipment)

	Associated Cost
	Cost

	Fuel cost 
	$40

	Maintenance cost 
	$15

	Operator wage 
	$      $280

	Schedule of Usage (Add rows as needed to account for all instances of using equipment)

	Date
	Time

	2 days
	4 Hrs per day

	Price of Hiring
	$2025

	Price of Transporting to Construction Site
	$125




	Machinery : Excavator 

	Limitations (Add rows as needed to account for all limitations of equipment)

	Canopies are removable if work required in confined spaces

	Diesel powered

	Comes with various attachments eg) mud buckets, augers, rock breakers, rubber tracks and rock grab and ripper

	Ensure code of practice for excavator use is followed

	Conditions of Use (Add rows as needed to account for all conditions of use of equipment)

	Over 18

	Have high risk work license

	For earthworks, drainage preps, site cutting and prep, plumbing and electrical works, land clearing for build, moving dirt, dig for retainer wall

	To include site cut and fill for 1001-1250mm fall across house, cut break-up and dump existing driveway and trenching

	Do not operate on slopes greater than 70%

	Operational Costs (Add rows as needed to account for all operational costs of use of equipment)

	Associated Cost
	Cost

	Fuel cost 
	$150

	Maintenance cost 
	$50

	Operator wage 
	        $750

	Schedule of Usage (Add rows as needed to account for all instances of using equipment)

	Date
	Time

	3 days
	8 Hrs per day

	Price of Hiring
	$2323

	Price of Transporting to Construction Site
	$125





	Machinery: Excavator Grader 

	Limitations (Add rows as needed to account for all limitations of machinery)

	Usually difficult to operate hence best to wet hire

	Include cutting edges, end bits, adapters, teeth, grader blades and overlays

	Ensure code of practice for excavator use is followed

	Conditions of Use (Add rows as needed to account for all conditions of use of machinery)

	Over 18

	High risk licence holder

	Precision required

	Operational Costs (Add rows as needed to account for all operational costs of use of machinery)

	Associated Cost
	Cost

	Fuel cost 
	$42

	Maintenance cost 
	$15

	Operator wage 
	$250

	Schedule of Usage (Add rows as needed to account for all instances of using machinery)

	Date
	Time

	1 day
	8 hrs day

	Price of Hiring
	$1018

	Price of Transporting to Construction Site
	$85






	Other Plant for Hire: Compactor

	Limitations (Add rows as needed to account for all limitations of other plant for hire)

	2.5T smooth drum

	Petrol driven with operating weight of 2490kg and travels at 8.7Kph

	For finishing driveway

	For compacting soil and gravel

	Can only be used on flat solid ground

	Conditions of Use (Add rows as needed to account for all conditions of use of other plant for hire)

	Has dual drive drums and articulated steering

	Front drum vibrates with rear static and ensures a perfect finish and a flush finish right to the edges

	Has a pressurized water sprinkler system

	No certification required to operate this machine, must be competent to do so and follow the ‘Duty of care’ responsibility on the employee who will run this machine – instructions on its usage is provided

	Operational Costs (Add rows as needed to account for all operational costs of use of other plant for hire)

	Associated Cost
	Cost

	Fuel cost
	$42

	Maintenance 
	$15

	Schedule of Usage (Add rows as needed to account for all instances of using other plant for hire)

	Date
	Time

	2 days
	8 hrs day

	Price of Hiring
	$598

	Price of Transporting to Construction Site
	$125




	Other Plant for Hire: Blaster 

	Limitations (Add rows as needed to account for all limitations of other plant for hire)

	Is portable and quickly assembled

	An air compressor is required to operate the machine

	Height 1145mm and length 930mm

	Requires 165-350cfm compressor

	Weight is 135kgs

	Conditions of Use (Add rows as needed to account for all conditions of use of other plant for hire)

	Emits fine spray of mist around the medial to control dust and suppresses up to 97% of airborne particles

	Can be used on steel, hardwood, aluminium, concrete, brick and masonry

	Require suitable hearing protections, protective gloves, eye protection wear and protective mask required

	Operational Costs (Add rows as needed to account for all operational costs of use of other plant for hire)

	Associated Cost
	Cost

	Maintenance 
	$15

	Schedule of Usage (Add rows as needed to account for all instances of using other plant for hire)

	Date
	Time

	2 days
	8 hrs day

	Price of Hiring
	$1005

	Price of Transporting to Construction Site
	$85




END OF PHYSICAL RESOURCES COSTING FORM
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