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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Debbie Cremer

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	1/12/2018




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	Where the building work is:
1 Valued over $3300
2 Valued over $1100 and includes hydraulic services design
[bookmark: _GoBack]3 Any value involving drainage, plumbing & drainage, gas fitting, chemical termite management, fire protection, completed residential building inspection, low rise, medium rise and open building design, site classification
	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	To arrange for electricity supply to site in Queensland you must take the following steps.

Engage an electrical contractor to identify whether there is electricity available to the site. If there is not then the following steps will be taken:

1 Electrical contractor will complete an enquiry on the client’s behalf
2 Distribution Network Service (DNS) Provider will investigate and advise the estimated cost and timeframe of connection. The client then has 20 business days to respond.

If there is electrical supply to the site, the electrical contractor will apply for a Network Connection Agreement with the DNS Provider. The DNS Provider will advise of a connection offer within 10 business days.

After the offer has been received and agreed to the electrical contractor will complete any work required to ready the premises for electrical connection then submit an Electrical Work Request to the DNS Provider. Within 5 days, the DNS Provider will attend the site and perform the requested work.

If circumstances outside of the DNS Providers control arise e.g. network availability, access requirements, traffic control requirements, timeframes may be longer. 
	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	To arrange for water connection to your site, you must submit a Water Approval application to Queensland Urban Utilities (if in South East QLD), pay the required fee and provide evidence that a connection is available. Once the application has been assessed a Water Approval will be issued. The Water Approval Process will generally take 5 days for a standard connection to a simple residential development. Water approvals are customised for all scales of developments therefore the approval timeframe is dependent on the complexity of the development and availability of services. 
	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	Section J of the Building Code of Australia
	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Reduces emissions, waste and pollution into the environment. Minimises the use of water reducing the risk of water shortages. Using renewable and recycled resources reduces the amount of materials going into landfill. Minimises land degradation and encourages a healthy landscape and environment. Less pressure on our natural resources.  
	

	
	Client benefit
	Cost saving on heating and cooling, energy and water usage. Increased value of the property.  Health benefits by using safer building materials and breathing cleaner air. Increased noise protection and healthier environment creating better quality of life.
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Electrician
	Arranges Electricity connection and supply. Wires hours for electricity. Installs lights and electrical fittings. Tests electrical system
	

	
	Plumbing
	Arranges water and sewerage connection and supply. Lays drainage pipes, drains, fits downpipes and roof guttering. Installs bathroom, toilet, kitchen & laundry fixtures and fittings. Installs hot water system. 
	

	
	Excavation
	Clears block of vegetation. Cut and fill where required to level slopes. Digs footings.
	

	
	Painting
	Paints external and internal cladding.
	

	
	Carpentry
	Installs roof trusses, wall, floor and window frames, architraves and cornices. Hangs internal and external doors and windows. Fits cabinetry and joinery. Builds decks, steps and paths.
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	3
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	4
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavation, soil testers
	

	
	
	Duration
	Varies depending on the amount of work required
	

	
	2: Slab or base stage
	Trades
	Form workers, steel fixers, concreters, plumbers, pest control
	

	
	
	Duration
	Approximately 1 to 2 weeks
	

	
	3: Frame stage
	Trades
	Carpenters, electricians, plumbers, plasterers, gas fitters, water proofers, bricklayers
	

	
	
	Duration
	Approximately 3 to 4 weeks
	

	
	4: Lockup stage
	Trades
	Carpenters, cabinet makers, plumbers, electricians
	

	
	
	Duration
	Approximately 4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Carpenters, cabinet makers, plumbers, electricians, tilers, painters, landscapers
	

	
	
	Duration
	Approximately 5 to 6 weeks
	

	
	6: Practical completion stage
	Trades
	Certifier
	

	
	
	Duration
	Approximately 7 to 8 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	Inclement weather, availability of materials, availability of labour, variations – changes, issues with permit approvals 
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	Time taken in re-pricing the change and studying any impacts the change may have on other elements of the work. Organising additional materials, trades, labour. Potentially will need to go back to council for further approvals or permits. 
	

	
	Labour availability
	Insufficient labour on site will mean the job is slower. Using unskilled labour could result in slowing down the job and having to do re-work. Trades must be sequenced correctly so as not to have trades standing around waiting for others to finish and potentially leaving and going to other jobs.
	

	
	Material availability
	Materials to be sourced in advance with availability and lead time confirmed so that they will be delivered when trades are ready for them. Staging of delivery’s so materials are not sitting on site for too long leading to the risk of theft.
	

	
	Weather
	Inclement weather will hinder or halt trades from completing their tasks. Time spent on trades preparing for a weather event and cleaning up afterwards. Ground conditions may be such that work cannot be carried out until they have returned to normal. Materials & equipment may get wet or damages and need replacing or wait until dry.
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Locate any underground services and document so as not to damaged – call Dial Before You Dig.
	

	
	Electricity
	Engage an electrician to disconnect electricity from work zones if required. Temporary electrical supply for construction installed. 
	

	
	Neighbours
	Advise neighbouring properties of start and forecasted finish dates of the project and probable daily start and finish times. Provide them with contact numbers and answer any other questions they may have.
	

	
	Waste disposal
	Establish an area for off road waste and recycle bins if possible or find out process for having bins on the street. Have waste management plan in place for containment and removal of the waste safely and environmentally friendly 
	

	
	Water connection
	Engage a plumber to disconnect plumbing if required
	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	Section 40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	Section 41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	Section 308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☒	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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