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CPCCBC4007A 
Plan building or construction work 
ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	Participant Name
	Jessica Landers




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	

	Assessor Signature
	
	Unit Competence Determination Date
	Click here to enter a date.
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	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	Jessica Landers

	
	

	Participant signature
	
	
	

	Date
	17/03/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	45
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	




	ASSESSOR COMMENTS

	


Q1.  Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Specification 
	



Q2.  [bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	Queensland Building and Construction Commission Act 1991 – Division 2
	33 Deposits (1) The building contractor under a regulated contract must not, before starting to provide the contracted services at the building site, demand or receive a deposit under the contract of more than— (a) for a level 1 regulated contract (other than a contract mentioned in paragraph (c))—10% of the contract price; or (b) for a level 2 regulated contract (other than a contract mentioned in paragraph (c))—5% of the contract price; or (c) for a level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price—20% of the contract price. Maximum penalty—100 penalty units.
	




Q3.  [bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Excavation
	Prepares the site for building by removing all vegetation and excavating footings
	

	
	Electrician
	Arranges electricity to be connected; places wiring for lighting and power cables; Fixes switches, installs power points, wires electrical systems
	

	
	Plumbing
	Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected
	



Q4.  [bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




Q5.  [bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	Building works require each of the trades to attend on the dates as outlined in the ghant chart. If a certain trade isn’t available, it could delay the project and completion for the works. 
	



Q6.  [bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	Online search
Advertising
	



Q7.  [bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	Location of materials – long lead time if they are to be imported from overseas

If a material is commonly available EG pine then it will be readily available.
	


Q8.  [bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NSZ 1680
	



Q9.  [bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Tower Lift
	Allows working at heights
	

	
	Generator
	Provides temporary power
	




Q10.  [bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Ladders
	Reaching inaccessibly areas
	

	
	Wheelbarrow
	Moving materials around site
	




Q11.  [bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	Keep records of the invoices and receipts associated
	


Q12.  [bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Temporary electrical pole
Water tapping
Temporary fencing
Barricades
Waste bin

	



Q13.  [bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	    
	True 
	
	
	
		False 
	
	




Q14.  [bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




Q15.  [bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





Q16.  [bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	Ensure there is adequate room for trucks to stop and use lifting equipment such as forklifts from the side of the road onto the site
	



Q17.  [bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 2 – Part 2.5 
	Volume 1 – D3.2 
	




Q18.  [bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Operational Works/Compliance Assessment SmartForm.
A site-specific Construction Noise Management Plan

A minimum of 10 working days is required for Council to assess an application. This applies once all documentation is received and providing no further information or changes are required
	



Q19.  [bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Lane or Road Closure Permit
	Complete the online application for temporary road occupation form and upload your supporting documents. Alternatively, you can download the form and complete it.

Prepare the necessary supporting documents and attachments required for your online application (as Word, PDF or JPG files). This may include:
Traffic Management Plan for temporary lane/road closure (required

Brisbane City Council)
	

	
	Footpath Closure Permit
	Complete the Application/notice to Work on Council Property online form, and:
 

	upload your supporting documents
	pay the application fee using Visa or MasterCard  Prepare the attachments required for your online application as Word, PDF or JPG files.  Attachments may include:
 

site plan sketch (required):
identifying the location of the proposed work
relevant dimensions of any proposed temporary structures
location and extent of any proposed earthworks (cut, trench and/or filling)
how pedestrians will navigate around the proposed footway use
	
	
approved plans (optional)
site photos (optional)
traffic management plan (optional)

Brisbane City Council
	



Q20.  [bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




Q21.  [bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	Purchase Order
	



Q22.  [bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




Q23.  [bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	Supplier
	



Q24.  [bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	WHS Act, WHS Regulation Part 1.2
	If this regulation requires an assessment of risks to health and

safety associated with a hazard, task, thing or circumstance,

an assessment of risks associated with a class of hazards,

tasks, things or circumstances may be conducted if—

(a) all hazards, tasks, things or circumstances in the class

are the same; and

(b) the assessment of risks for the class does not result in

any worker or other person being exposed to a greater,

additional or different risk to health and safety than if

the risk assessment were carried out in relation to each
individual hazard, task, thing or circumstance
	




Q25.  [bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	Work Health and Safety Regulation 2011 (Qld) Section 40: The Section 40: The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	


Q26.  [bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheets (SDS)
	



Q27.  [bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10m2
	



Q28.  [bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




Q29.  [bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




Q30.  [bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	You should try to minimise skilled labour from moving off-site when there is work to be done on nearby constructions. This can save a great deal of time, as the subcontractors can work on the next job while waiting for another to complete.
	




Q31.  [bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	If a tiler attends site to do their works and the plastering has not been completed they are unable to undertake their works. 
	



Q32.  [bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




Q33.  [bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





Q34.  [bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
G
F
H
E
I
J
D
C
B
A

	Answer
	

	



Q35.  [bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

Q36.  [bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




Q37.  [bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




Q38.  [bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





Q39.  [bookmark: _Ref432123]Describe the critical path.

	Answer
	The ‘critical path’ – the longest sequence of activities in a project (which determines the shortest possible completion time if all events are to be completed)

Depending on the path you take will depend on how much float is in the job

Delays in your critical path can cause an increase in time and money
	



Q40.  [bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




Q41.  [bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	Supply chain delays
Weather delays
Subcontractor delays attending site to undertake works 
	



Q42.  [bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




Q43.  [bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	It will be helpful in the event of a dispute with a neighbour 
	


Q44.  [bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




Q45.  [bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	All parties are aware of the site status before work commences and easily identify if any damage has occurred through the construction process. 
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Jessica Landers

	
	

	Participant signature
	
	
	

	Date
	17/03/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
	
	

	Task 1 (Occasion 2)
	
	




	ASSESSOR COMMENTS

	


CPCCBC4007A
Plan building or construction work

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities:
· Occasion 1: Residential projects
· Occasion 2: Commercial projects

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· A construction program/schedule for a project showing:
· The sequencing of the trades, etc.
· Working and non-working days, etc.
· Local authority construction commencement notices
· Pre-construction site inspection reports or dilapidation reports
· WHS policy

The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document.

	Resources required: 
Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. 

	Assessment of task

	Name of participant:
	

	Name of observer:
	

	Role of observer 
(Confirm suitability to sign)
	

	Email address of observer
	

	Signature of observer:
	
	Date:
	Click here to enter a date.
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1 Appraise contract documentation

	1.1A.  [bookmark: _Ref536514168]Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties.
		
	1.1B.  [bookmark: _Ref536514171]Determine availability of selected subcontractors to suit the job requirements. 
		
	1.1C.  [bookmark: _Ref536514174]Assess availability of materials and confirm with suppliers. 
		
	1.1D.  [bookmark: _Ref536514176]Identify site access requirements and limitations, taking action to facilitate entry. 
		
	1.1E.  [bookmark: _Ref536514185]Prepare documentation for authorities controlling construction work and determine project commencement date. 
		
	1.1F.  [bookmark: _Ref536514189]Implement procedures for controlling and recording site deliveries. 
		
	2 Construction operation strategies 

	1.2A.  [bookmark: _Ref536514201]Identify organisational strategies for implementing construction. 
		
	1.2B.  [bookmark: _Ref536514204]Implement procedures for recording the hire of plant and equipment. 
		
	1.2C.  [bookmark: _Ref536514207]Implement organisational WHS policies and procedures, including hazard and risk management.
		
	1.2D.  [bookmark: _Ref536514211]Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements.
		
	1.2E.  [bookmark: _Ref536514215]Follow procedures for the control of multiple projects. 
		
	3 Project schedule 

	1.3A.  [bookmark: _Ref536514218]Sequence construction operations. 
		
	1.3B.  [bookmark: _Ref536514221]Enter operation details into a manually prepared project schedule or computer-based software package.
		
	1.3C.  [bookmark: _Ref536514224]Define critical path of the project, revising as required.
		
	1.3D.  [bookmark: _Ref536514227]Adjust project timeframes to account for anticipated delays.
		
	4 Required resources

	1.4A.  [bookmark: _Ref536514241]Determine and document temporary services and site accommodation requirements.
		
	1.4B.  [bookmark: _Ref536514244]Determine and document plant requirements and availability, with reference to contract documentation.
		
	1.4C.  [bookmark: _Ref536514247]Determine and document on-site labour requirements, with reference to contract documentation. 
		
	5 Condition reports

	1.5A.  [bookmark: _Ref536514251]Complete reports on the condition of existing buildings and structures on adjacent site boundaries. 
		
	1.5B.  [bookmark: _Ref536514256]Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction.
		
	1.5C.  [bookmark: _Ref536514373]Effectively communicate using the following methods:
· Telephone, facsimile, email and in writing 
· Language/concepts appropriate to cultural differences
· Non-verbal communication
		
	The Participant’s performance was:  Satisfactory     Not Satisfactory





	OBSERVER COMMENTS
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