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CPCCBC4003A Select and prepare a construction contract, 
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.
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	Theory Exam
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	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for CPCCBC4003A
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	Outcome for CPCCBC4016A
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	 Not Yet Competent

	Outcome for CPCCBC4032A
	 Competent
	 Not Yet Competent
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	Unit Competence Determination Date
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CPCCBC4003A Select and prepare a construction contract, 
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	Bianca Krieger 

	
	

	Participant signature
	
	
	

	Date
	21/02/2022



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	51
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	



	ASSESSOR COMMENTS

	



[bookmark: _Ref428791704][bookmark: _Ref527462137]Order the following elements of an agreement from 1 to 4.

	Answer
	Element Number
	Element
	
	
	2
	Acceptance
	

	
	4
	Consideration
	

	
	3
	Intention of legal consequences
	

	
	1
	Offer
	




[bookmark: _Ref428791707]When would an offer be considered to have lapsed?

	Answer
	When the time for acceptance expires;
If the offer is withdrawn before it is accepted; or
After a reasonable time in the circumstances (generally the greater the value of the contract, the longer the life of the offer)

	



[bookmark: _Ref428791708]What happens to the offer if new terms are suggested?

	Answer
	New terms suggested are regarded as a counter offer that can be accepted or rejected 
	



[bookmark: _Ref428791713]What does it mean when a contract is supported by ‘valuable consideration’?

	Answer
	One party promises to do something in return for a promise from another party
Consideration is what each party gives to the other as the agreed price for the other’s promises
Usually the consideration is the payment of money

	




[bookmark: _Ref528220703]Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

	Answer
	. persons suffering from a mental disability, intoxicated individuals
	



Q1.  [bookmark: _Ref423505767][bookmark: _Ref527444202]Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

	Answer
	A person with full mental capacity and understanding of the binding contract whom is in agreement with terms
	



[bookmark: _Ref428790918]Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

	Answer
	 Queensland Building and Construction Commission (QBCC) - providing information, advice and regulation to ensure the maintenance of proper building standards and remedies for defective building work.
	



[bookmark: _Ref495585144]Under what laws are domestic building contracts regulated?

	Answer
	QBCC 
	



[bookmark: _Ref495585145]Domestic building contracts must be put in writing once the work exceeds what value?

	Answer
	$3,300 (incl.)
	



[bookmark: _Ref495585147][bookmark: _Ref527985213]A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

	Answer
	$10,000 - The QBCC Act requires that commercial contracts for building work valued at over $10,000 must be in writing before work starts. If the building work is valued at $10,000 or less, the contract must be in writing before the work is completed.
	



[bookmark: _Ref495585148]Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

	Answer
	5
	



[bookmark: _Ref423502767]What are the benefits of having a written contract in place between parties?

	Answer
	Home owners receive the finished product they envisioned
Builders get paid and paid on time
	



[bookmark: _Ref495585603]Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

	Answer
	Clauses
	Answers
	Definition
	
	
	1
	Acceptances
	1 - F
	A
	Provide specific reasons that allow the contract period to be adjusted
	

	
	2
	Cost adjustments
	2 - E
	B
	A provision for which remedies can be sought if breached
	

	
	3
	Extensions of time
	3 - A
	C
	Specifically outlines the tasks to be completed as part of the construction work
	

	
	4
	Payments
	4 - D
	D
	Outlines the requirements for deposits
	

	
	5
	Scope of work
	5 - C
	E
	Address the risk of rise/fall of expenses
	

	
	6
	Term
	6 - B
	F
	Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding
	




[bookmark: _Ref428786304]Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Contract estimate
	

	
		Contract request
	

	
		Preliminary agreement
	



[bookmark: _Hlk96325009]
[bookmark: _Ref424211634]True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

	Answer
		True 
	
	
	
		False 
	
	





[bookmark: _Ref428774552]Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

	Answer
	Contract name
	Description
	
	
	New home construction contracts

	For the construction of the entire home
	

	
	Level 1 – Renovation, Extension and Repair contracts

	For renovations, extensions and routine repairs on existing homes for contracts $3,301 to $19,999

	

	
	Commercial building contract 
	A lump sum contract to be used for the construction only of commercial building work with or without a principals agent 
	

	
	Commercial Cost Plus Contract
	A cost plus contract for sue on commercial building projects, where a lump sum price cannot be established, however a fair and reasonable estimate is given 
	




[bookmark: _Ref424211517]Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

	Answer
	Commercial Minor works contract 
	



[bookmark: _Ref495650885]Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

	Answer
	Natural disasters repairs contract – maximum value of works $3,300
	


[bookmark: _Ref495653718]Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

	Answer
	Topics
	Definition
	
	
	Builder’s Licence
	You should only deal with a QBCC-licensed contractor. If you engage an unlicensed contractor, your building work may not be covered under the Queensland Home Warranty Scheme.
	

	
	Contract price
	For contracts priced at $20,000 or more, the contract price, if fixed, must be shown prominently on the first page of the contract schedule. If the contract price is not fixed, the method for calculating it, including any allowances, must be stated in the contract schedule. Allowances (items or services for which the price is not fixed when the contract is signed) should be kept to a minimum as the final cost often exceeds the estimate in the contract. The contract must also contain a warning about any provisions that may alter the contract price
	

	
	Building approvals and inspections
	Building approvals and inspections are the responsibility of a building certifier who may be engaged by you or, more commonly, your builder. Mandatory building inspections may be required at certain stages of construction. If your contractor has engaged a building certifier for certain certification functions, you can ask the certifier (via a notice given to your contractor) to perform additional certifying functions which will be at your expense and must be carried out by the certifier within agreed timeframes. The contractor must give you copies of any certificates of inspection as soon as practicable after they receive them from the certifier. You can also ask the certifier, by written notice, for copies of any inspection documentation and the certifier must provide the documents within 5 business days. You can check a certifier’s licence via QBCC’s OnLine Licence Search.
	

	
	Practical completion and handover
	Building approvals and inspections are the responsibility of a building certifier who may be engaged by you or, more commonly, your builder. Mandatory building inspections may be required at certain stages of construction. If your contractor has engaged a building certifier for certain certification functions, you can ask the certifier (via a notice given to your contractor) to perform additional certifying functions which will be at your expense and must be carried out by the certifier within agreed timeframes. The contractor must give you copies of any certificates of inspection as soon as practicable after they receive them from the certifier. You can also ask the certifier, by written notice, for copies of any inspection documentation and the certifier must provide the documents within 5 business days. You can check a certifier’s licence via QBCC’s OnLine Licence Search.
	

	
	Implied warranties
	Schedule IB of the Act sets out statutory warranties which are deemed to be part of all regulated domestic building contracts, even if not stated in the contract. The warranty period is 6 years from completion, termination or cessation of the work for breaches resulting in structural defects; 1 year for all other breaches. Legal proceedings for any breach must be started within the warranty period or a further 6 months if the breach becomes apparent within the last 6 months of the warranty period.
	



Q2.  [bookmark: _Ref423503323][bookmark: _Ref423598528]Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Engineer specifications
	

	
		Plans, drawings and specifications
	

	
		Prime Cost Items Schedule
	

	
		Processes for applying for extensions of time
	

	
		Product catalogues
	

	
		Project timelines and schedules
	

	
		Provisional Sums Schedule
	

	
		Rise and fall calculations
	

	
		Site conditions report
	

	
		Soil and sedimentation report
	




[bookmark: _Ref428785642]What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

	Answer
	Prime cost is the cost of an item that is not yet known.
Provisional Sum is the cost of carrying out the work required which is not know.

Prime cost example: cost of carpet that is to be installed into the property

Provisional Sum example: cost of the labour / trade to install the carpet into the property 
	



[bookmark: _Ref428796325]Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

	Answer
	long-term costs and some specific costs (e.g. labour and materials, currency exchange rates for overseas-purchased goods, duties, taxes, shipping).
	



[bookmark: _Ref495650899]True or False (Tick your response): Variations can be requested by both the client and the builder.

	Answer
		True 
	
	
	
		False 
	
	




Q3.  [bookmark: _Ref423508256][bookmark: _Ref527450478]How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

	Answer
	Issue an extension of time form asking the client to grant you an extension of the contract period.
Specific reasons for an extension of time are set out in the general conditions of the building contract and include reasons such as: inclement weather and delays caused by the owner, such as changes in the scope of works
	




[bookmark: _Ref495652895]Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

	Answer
	Fair Trading Act 1989
(1) This Act applies to and in relation to— (a) persons carrying on business within Queensland; or (b) bodies corporate incorporated or registered under the law of Queensland; or (c) persons ordinarily resident in Queensland; or (d) persons otherwise connected with Queensland. (2) Subject to subsection (1), this Act extends to conduct, and other acts, matters and things, occurring or existing outside or partly outside Queensland (whether within or outside Australia)
	



[bookmark: _Ref495653465]Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

	Answer
	Make reasonable inquiries about why you want to borrow the money
make reasonable inquiries about your financial situation
Take reasonable steps to verify your financial situation
Assess whether you can meet the financial obligations of the credit contract (and whether it will meet your needs)
Determine that the credit contract is ‘not unsuitable’ for you
	



[bookmark: _Ref428776673]What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

	Answer
	enable you to cancel your contract if you are not satisfied with it, and you act quickly.
	




[bookmark: _Ref428779587]What are the maximum deposits recommended for a residential building project?

	Answer
	. If the contract for domestic building work is priced at $20,000 or more, the maximum deposit is 5%. If the contract price is more than $3,300 and less than $20,000, the deposit must not exceed 10%.
	



[bookmark: _Ref428794433]Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

	Answer
	Deposit 5%
Base stage 15%
Frame stage 20%
Enclosed stage 25%
Fixing stage 20%
Practical completion 15%
	



Q4.  [bookmark: _Ref423508227]You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

	Answer
	The maximum deposit that can be collected at the deposit stage as per QBCC Act is 5%, therefore deposit cannot be more than $27,500
	

[bookmark: _Ref423515882][bookmark: _Ref423515982]
Q5.  [bookmark: _Ref423504803]Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

	Answer
	Breach
	Explanation
	
	
	Breach of condition under contract
	If a condition is breached, the aggrieved party can elect to discharge the contract and sue for damages

	

	
	Breach of warranty under contract
	If a warranty is breached, the aggrieved party cannot elect to terminate or discharge the contract – they may only seek damages
	




[bookmark: _Ref428793813]What does repudiation of a contract mean?

	Answer
	Rejection of a proposal or idea
	



[bookmark: _Ref528068459]True or False (Tick your response): In the event of repudiation, the injured party has two options:
· Continue with the contract
· Accept the repudiation and move to terminate the contract

	Answer
		True
	
	
	
		False
	
	




[bookmark: _Ref528068460]Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

	Answer
	it does not automatically lead to a termination of the agreement, nor does it release the other party from their liabilities
	


[bookmark: _Ref428794305]What does ‘abandonment of contract’ mean?

	Answer
	parties both have conducted themselves in such a way that the original contract is no longer valid. Both parties may mutually agree to do this, or it can become part of a claim.

	



[bookmark: _Ref428793803]A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

	Answer
	Cause is when one party stops work because of a deficiency in performance by the other party.

Convenience is when the owner stops work for reasons other than a deficiency in performance by the contractor. Because a termination for convenience is not the result of poor performance, the law may provide the aggrieved contractor with significant rights against the breaching owner
	



[bookmark: _Ref495653458]Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

	Answer
		Yes
	
	
	
		No
	
	



[bookmark: _Ref428795233]If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

	Answer
	· What must occur to perform the contract
· A reasonable time in which the contract must be completed
· A statement of the consequences of not performing in accordance with the notice

	



[bookmark: _Ref528148821]True or False (Tick your response): Where the notice given (as per Q38. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

	Answer
		True
	
	
	
		False
	
	




[bookmark: _Ref428781925][bookmark: _Ref528152060]When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

	Answer
	The owner is required to pay the final contract payment at practical completion stage.
This could affect the defects and omissions as the final payment can not be withheld as it is part of the contract, meaning the building party could potentially take longer to rectify defects and omissions. 
	


[bookmark: _Ref428794091]Explain the concept ‘conditions for completion at the cost of the contractor’.

	Answer
	The Contractor must make good defects or omissions in the work under this Contract which become apparent within 6 months of the Date of Practical Completion.
If there are any such defects or omissions, the Owner must give the Contractor written notice to make good such defects or omissions within the 6 month period
and must give the Contractor reasonable access to the Site for that purpose.
Subject to reasonable access being provided, the Contractor must within 28 calendar days of the notice being given rectify any defects notified to the Contractor during usual business hours.

	



[bookmark: _Ref495653464]Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

	Answer
	You are entitled to a replacement or refund for a major failure and compensation for any other reasonably foreseeable loss or damage. You are also entitled to have the goods repaired or replaced if the goods fail to be of acceptable quality and the failure does not amount to a major failure
	



[bookmark: _Ref428795566]Name one (1) person you should consult if you are considering ousting a contractor from a building site.

	Answer
	Lawyer 
	



[bookmark: _Ref428795533]What document should you refer to if you are considering ousting a contractor from a building site?

	Answer
	Contract
	




[bookmark: _Ref428776477]How should you handle a customer complaint?

	Answer
	Deal with the complaint immediately 
Stay calm
Identify the problem
Decide what can be done 
Arrange a second opinion to confirm your view
Keep records
Fix the problem
	



[bookmark: _Ref428780523]How do you reduce the risk of dispute?

	Answer
	Getting your contract right at the start of your business relationship will mean fewer problems later on
	



[bookmark: _Ref428780789]What is the process for dispute resolution?

	Answer
	 try and resolve your dispute directly with the other party by contacting them, holding a face-to-face meeting or writing to them. Some traders and companies have complaints processes in place or are part of an industry scheme that can resolve disputes.
Once you have reached agreement, you should write to the other party confirming your agreement. It is recommended that all parties sign the agreement and keep a copy.
If however, you are unable to reach a satisfactory outcome you can either choose to:
· invite the other party to attend mediation which is a way of settling a dispute without legal action. The Department of Justice provides a free mediation service through its Dispute Resolution Centres, or
· apply to QCAT to resolve your dispute. Claims must be lodged within six years of the incident happening.

	


Q6.  [bookmark: _Ref423599342]During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

	Answer
	Good evening,

Thank you for your email. 

I have reviewed the contract we have for your property, cross checking specifications, material order and order sheets. I can confirm that details installed within the property are as per the agreed materials in the contract and no error has been made. 

Should you require anything further, please let us know 

Kind regards,
Bianca 
	


[bookmark: _Ref428787470]Where would you find any possible penalties associated with a build?

	Answer
	Queensland Building and Construction Commission Act 1991
	



[bookmark: _Ref528221530]Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

	Answer
	must be obtained from a building certifier (formerly known as a ‘building surveyor/inspector’), who can be either a local government building certifier or a private certifier.

 Brisbane City Council must hold records of building approvals and certification information. The legislation also requires that an accredited building certifier must lodge the following documents with Council:
· Engagement notice and application details
· Decision notice, approved building plans and any other documentation that contributed to the plan approval
· Completion details such as certificates (including certificate of classification and inspection certificates) and any other documents relating to the certification and acceptance of the completed building work


	


Q7.  [bookmark: _Ref423598913]Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:
· The land has been secured and paid for by the Clients.
· Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.
· Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured. 
· Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list. 
· The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.
· The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.
· Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build. 
· The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.
· The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.
· The construction period excluding inclement weather and possible delays is 23 weeks
· Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).
· Prime costs are required for the solar hot water system and ducted air conditioning
· Provide fictitious details for all other sections of the contract.
· 18 solar panels are to be installed on the roof


	Answer
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	

	
	

	Participant signature
	
	
	

	Date
	Click here to enter a date.



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
		
	Task 1 (Occasion 2)
		



	ASSESSOR COMMENTS

	


CPCCBC4003A Select and prepare a construction contract,
CPCCBC4016A Administer a construction contract & 
CPCCBC4032A Apply contract law to sales processes

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. 

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· Copy of a contract issued to sub-contractor for your project with relevant AS code on the front
· Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails)
· Copy of HSE minimum requirements sent as contract condition
· Construction contracts that have been developed, signed off, or contributed to by the candidate
· Proof of correspondence with client regarding construction contract. Redact sensitive information as required.

The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment.

	Resources required: 
Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer.

	Assessment of task

	Name of participant:
	

	Name of observer:
	

	Role of observer 
(Confirm suitability to sign)
	

	Email address of observer
	

	Signature of observer:
	
	Date:
	Click here to enter a date.
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1.A.  [bookmark: _Ref495661944]Explain to the client:
· Essential terms and elements of a valid contract 
· Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements)
· The range of documents that collectively make up a contract (including construction schedules, reports, specifications)
· The importance of the contract to sales process 
· Implications of legislation, regulations and codes of practice (including Australian Consumer Law)
		
	1.B.  [bookmark: _Ref495662059]Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit.
		
	1.C.  [bookmark: _Ref495662068]Ensure the pre-contract agreement is signed and processed according to organisational requirements.
		
	1.D.  [bookmark: _Ref527380121]Select appropriate contract and seek expert advice in the preparation of the contract, considering:
· Contract rise and fall amounts
· Schedule of progress payments
· Processes for applying of extensions of time
		
	1.E.  [bookmark: _Ref495661995]Break down contract clauses/terms/conditions with the client, including:
· Rights, liabilities and potential penalties of parties under the contract
· Definitions of building work, common contract terms and procedures, considering – 
· Practical completion and issuing a final certificate
· Defects liability and completion at the cost of the contractor
· Effect of ousting the contractor from the building or site
· Cooling off periods
· Provisional sum and prime cost allowances
· Measures to be taken in the event of an anomaly in the rendering of the contract, considering – 
· Variations
· Circumstances that bring about a breach and termination of contract, considering – 
· Unreasonable/vexatious notice
· Abandonment of a contract
· Methods for resolving contractual disputes
		
	1.F.  [bookmark: _Ref495662164]Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods:
· Verbally using language/concepts appropriate to cultural differences
· Non-verbal communication
· Using technology (including telephone, facsimile, email)
· In writing (including drafting responses to queries about contracts)
		
	The participant’s performance was:  Satisfactory     Not Satisfactory
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