Electronic Call Forward Sheet 
	Site address
	123 ABC Residential street, QLD

	Project name
	123 ABC Residential street, QLD


	Client
	Big Boss
	Surveyor
	Mr Sur



	
	Provider details *Names have been removed due to confidentiality reasons *
	

	Task
	Date required
	Supplier
	Contractor
	Contact info

	Stage

	Demolish existing kitchen and make good
Dismantling the existing storage, slab platform including supporting walls, wall tiles, flooring, sink etc. at all levels as required carefully and disposing off and clearing away the debrisSlabs to be chased to allow for new plumbing

	5/3/23
	
	Demolition labour
	3399

	Plumbing rough in
	7/3/23
	
	Plumber
	0456

	Electrical rough in
	7/3/23
	
	Electrician
	0789

	Kitchen 
Elevation
Bench
Drawers
Spice rack
Brushed stainless steel laminate
Ducting
Overheads
Shelves
Caesarstone bench top
Island
Sink cupboard
Paint
Cabinetry - Blum Tandembox antaro h. Fronted pull-out C - DQC5JY, D - DQC69A, DQCB6M
Urbane Castella 192mmCTC handle

	5/3/23
	Kitchen supplier
	
	2216

	Butlers Pantry
Door sink cupbard
Bins
Dishwasher
Drawers
Shelves
Overheads
Paint
	5/3/23
	Kitchen supplier
	
	2216

	L shaped laundry 2450x2520x2550mm or expressed as 2.45m x 2.52m x 2.55m with 4 door laundry tub unit with 1 adj shelf with bench at 1000mm H
40mm Caesarstone organic white top running wall to wall below laundry shute cupboard and 20mm thick splashback 150mm height
4 door overhead cupboard with 2 adj shelves and dorrs hanging down as finger pull above dryer and washing machine openings with flat pull out shelves and 1 of blum soft close drawer below
2 door Tall broom storage cupboard to right side with 1 of blum soft close drawer below 1 0f internal adj shelf
Brushed stainless steel laminate kick face
Single door cupboard 600x600mm on opposite wall 1000mm height bench top.
All internals 16mm white HMR with 1mm ABS PVCedge.  All fronts in 18mm white sating with 2 pac satin finish
Dryer and washing machine panels, bottoms in 32mm MDF with 2pac finish
	6/3/23
	Laundry supplier
	
	2219

	Island & laundry - franke ancona single bowl undermount sink – anx 110-48
Pantry - franke ancona double bowl undermount sink - anx 120
Island & pantry - mizu drift mk2 gooseneck sink mixer pull-out
Laundry - mizu soothe square gooseneck sink mixer

	8/3/23
	Plumbing supplier
	
	2218

	Building works – wet areas, walls, ceiling, doors/windows
	10/3/23
	     
	Carpenter
	1456

	Plaster works and finish
	17/3/23
	     
	Plasterer
	1457

	Waterproofing
	19/3/23
	     
	Waterproofer
	1234

	Cabinets installation, skirting/architraves installation, benchtop , kitchen, laundry, pantry installation
	28/3/23
	     
	Carpenter
	1456

	New timber look tile flooring 
Kitchen – timber look tiles to match floors 1200x x230mm
Laundry and kitchen - ceramic tile splashback - Snow Brillo Tile Sc19 A7615, Amber Tiles To Match Cabinets. 130mmx130mm
Brushed stainless steel laminate kick face
130 sqm
	20/4/23
	Tile supplier
	
	2214

	Tiling
	28/4/23
	     
	Tiler
	1234

	Beacon Herman 1 light pendant
14 watt led tape and recess led profile under overhead cupboards
Single phase underground power connection from existing supply point. 
Led light strip under island bench
Cooktop isolation switch
	28/4/23
	Electrical supplier
	
	2212

	Electrical fit off
	1/5/23
	
	Electrician
	0789

	Plumbing fit off
	1/5/23
	     
	Plumber
	0456

	New fixed glass window to suit existing opening width frame
1800x600mm
Colour to match exiting and tinted to client requirement (customized)
New Triple Slider With Screens To Match Existing Profile & Colour
2710x2100mm
Slider with reversed opening with screen to match existing profile and colour
1810mmx2100mm


	2/5/23
	Window supplier
	
	2222

	Accessories fit off
	3/5/23
	
	Carpenter
	1456

	Caulking
	3/5/23
	
	Carpenter
	1456

	Screen installation
	4/5/23
	
	Carpenter
	1456
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