


Core4 AUS
121 Newmarket Road
Windsor
QLD 4030
Date 11/04/2024

Dear Jessica,
I am writing to inform you that due to the recent delays in material procurement Core4 are issuing an extension of time request in regard to section 15.2 in the signed contract. Current finish date regarding item 9 in the contract is 01/05/2024 but Core4 would require 5 more days to allow for full completion of works on the 06/05/2024.
Kind Regards
Michael Trott
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Michael Trott

Estimator/Project manager


