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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Henry Erratt

	

	

	Participant signature
	



	Assessor name
	Brett Stoward

	

	

	Assessor signature
	



	Date
	4/12/2018




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	Building work of any value where it involves (In NSW):
· Drainage
· Plumbing and Drainage
· Gas Fitting
· Termite Management – Chemical
· Fire Protection
· Completed Residential Building Inspection
· Building Design – Low Rise, Medium Rise and Open
· Site Classification

	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	· Your electrical contractor will be able to advise if supply is available.
· Should the premise not have supply available, the electrical contractor can complete an enquiry on the client’s behalf
· The Distribution Network Service Provider (e.g. Energex) will conduct the necessary network investigations and provide an indicative estimate of potential costs and timeframes for the client to make an informed decision within 20 business days
· If there is supply available, the electrical contractor will need to enter into a Network Connection Agreement with the Distribution Network Service Provider
· If the application is not expedited (e.g. by agreeing to the Model Terms and Conditions for Deemed Standard Connection Contracts), the Distribution Network will advise of a Network Connection Offer within 10 business days
· After agreeing to the connection offer, the electrical contractor will prepare the premises for connection
· The electrical contractor will submit an Electrical Work Request (EWR) to the Distribution Network Service Provider once the work is complete
· A copy of the EWR will be sent to the client’s preferred electricity retailer
· Once all forms are received, the Distribution Network Service Provider will visit the premises to perform the requested work
· The Distribution Network Service Provider must adhere to timeframes for new connections (e.g. Energex will attend the property within 5 business days)

	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	· Submit a Water Approval application
· The Water Approval Process works in conjunction with the Council development assessment process, and applications do not need to be submitted at the same time
· Water and sewerage connection approvals are customised for all scales of development from a new house to a large factory or multi-stage residential sub-division
· Where developers are proposing to connect to our water and sewerage services, councils will require evidence that a connection is available 
· Generally the evidence required, and therefore the relative timing of the two approvals, will depend on the complexity of the proposed development and the likely availability of services
· Standard connections for simple residential developments are usually completed within five (5) days

	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	Section J of the Building Code of Australia
	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	[bookmark: _Hlk531686262]Answer
	Topics
	Definition
	
	
	Environmental benefit
	Reduce greenhouse emissions through sustainably sourced materials and energy efficient construction.
	

	
	Client benefit
	Long term cost saving e.g. energy efficiency, saving on electricity bills.
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Excavation
	Prepares the site for building by removing all vegetation and excavating footings.
	

	
	Electrician
	Arranges electricity to be connected; places wiring for lighting and power cables; Fixes switches, installs power points, wires electrical systems.
	

	
	Plumbing
	Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected.
	

	
	Steelfixing
	Installs reinforcing steel to improve the strength of concrete.
	

	
	Concreting
	Installs formwork and boxing; pours concrete (e.g. slabs).
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	3
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	4
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavation
	

	
	
	Duration
	varies
	

	
	2: Slab or base stage
	Trades
	Steelfixing
Concreting
Brick Layers
Plumbing
Warterproofing
Termite treatment
	

	
	
	Duration
	1-2 weeks
	

	
	3: Frame stage
	Trades
	Carpentry
Brick Laying
Electricians
Plumbing
Gas fitting
	

	
	
	Duration
	3-4 weeks
	

	
	4: Lockup stage
	Trades
	Carpentry
Waterproofing
Plastering
Plumbing
Electrical

	

	
	
	Duration
	4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Electricians
Plumbing
Tiling

	

	
	
	Duration
	5-6 weeks
	

	
	6: Practical completion stage
	Trades
	Painting
Landscaping
	

	
	
	Duration
	7-8 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	Project size
Project function
Height of the building
Building complexity
Quality requirements (e.g. appearance, finishes)
Location

	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	If the requirements of the job are altered, this will change the initially projected timeframes, especially where additional materials and labour must be organised.
	

	
	Labour availability
	The construction process sequence is very important when organising the required labour. For example, a plasterer should only be organised after all other trades have performed their tasks correctly – electricians and plumbers will not be able to access behind the walls as easily once the plasterer has put them up.
	

	
	Material availability
	You must liaise with sub-contractors and suppliers to ensure materials are delivered when the sub-contractor is ready to complete their work. Materials that are rare or difficult to source should be ordered well in advance.
	

	
	Weather
	Weather will affect the ability of trades to complete their jobs on time.
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact Dial Before You Dig before undertaking any excavation to ensure that services will not be damaged during construction.
	

	
	Electricity
	[bookmark: _GoBack]Electricity may need to be disconnected from work zones prior to construction and temporary utilities installed for the duration of the construction process.
	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers.
	

	
	Waste disposal
	Set up a designated area for rubbish bins and waste removal. Check if permits are required to place bins on the street.
	

	
	Water connection
	Book in a plumber to perform any required disconnections prior to any demolition taking place.
	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☐	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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