


Project Start Preparation Template
Project Information
	Target start date
	5/3/2023

	Target end date
	5/5/2023

	Location
	QLD


Approval Conditions
The conditions that the project must meet before work can begin.
	Local government body relevant to the building and construction project
	Brisbane City Council, QLD

	Approval conditions
	It is responsible for enforcing building regulations and standards, issuing building permits, conducting inspections and ensuring that all construction projects comply with the relevant codes and regulations.  They are also responsible for ensuring that any development within their jurisdiction is consistent with the local scheme.  The approval conditions would need to meet the below:

1. Planning Approval: A planning approval may be required before you can start construction. This approval confirms that your proposed development complies with the Brisbane City Plan 2014.
2. Building Approval: Once you have planning approval, you will need to obtain building approval. This approval confirms that your proposed construction meets the minimum standards of the Building Code of Australia.
3. Site Works Approval: If your proposed development involves excavation or any other works that may affect the stability of the site, you may need to obtain Site Works Approval.
4. Plumbing Approval: If your proposed development involves any new or modified plumbing works, you will need to obtain plumbing approval from the Council.
5. Electrical Approval: If your proposed development involves any new or modified electrical works, you will need to obtain electrical approval from the Council.
6. Operational Works Approval: If your proposed development involves works that are not covered by the above approvals, you may need to obtain operational works approval.





	Local regulatory body relevant to the building and construction project
	Queensland Planning Act 2016
Water Supply Services Legislation Amendment Act 2014
Building Act 1975
Building Regulations 2021
NCC
Development code part 3.4 – pool safety barrier and gate
Work Health and Safety Act
QDC MP4.4 Noise Category – Transport Noise
Environmental protection regulation 2019 and Environmental Protection Act 1994

	Approval conditions
	Development Approval granted for the carrying out of "Building Work"in accordance with this
Footings with allowable bearing pressure
Footings will be placed centrally under walls and columns
Integrates land use planning and planning for water and sewerage infrastructure and includes a distributor-retailer’s connection policy. The Bill makes minor amendments to the current process for making or amending a water netserv plan, including  clarifying requirements about public consultation and endorsement by participating local governments and  the Planning Minister before its adoption by the distributor-retailer.
Building Act 1975 will inform us what building work is accepted development, and the requirements as per Act. 
It provides who is responsible for carrying out the building assessment work and building applications
It provides for the giving of final inspection certificates and inspection documentation 
It makes provision for fire safety
It provides matters for swimming pool safety and fencing
It provides for the designation of land as a transport noise corridor
The process under the Building Regulation 2021 is that where an appointed competent person issues a Non-compliance Notice, the certifier must then follow-up and issue their own certificate and the builders obligation to ensure stage complies with development approval
A building, plumbing or drainage solution will comply with the NCC if it satisfies the Performance Requirements, which are the mandatory requirements of the NCC. The Performance Requirements are also supported by General Requirements.
There are three ways to comply with the NCC's Performance Requirements. These include Performance Solution and Deemed-to-Satisfy (DTS) Solution
Australian Standard AS 1926.1 and AS 1926.2 and fence which is not a permanent structure, has at least one gate, otherwise complies with this part and is securely fixed to resist reasonably foreseeable actions to which it may be subjected.
WHS Act includes safety in design report covering:
Safe material handling and lifting
Handling hazardous material
Compliance of materials to match specifications
Reducing trip, slips, fall hazards
Safe use of equipment to comply with procedures
Safe and suitable equipment and PPE
Formwork erection and use
Scaffolding erection and its use
Temporary bracing installation
Excavations outside property boundaries or near services
Worker training
Use of suitably qualified tradesmen/women/contractors/subcontractors
Safe undertaking of compliance inspections
Ensure construction loads no exceeded

QDC MP4.4 Noise category – the Construction elements must comply with the requirements set out in Table 4 of SEG report and to ensure habitable rooms of particular residential buildings located in transport noise corridors are designed and constructed to reduce the extent to which transport noise intrudes into those rooms. 
Environmental protection regulation 2019 and Act 1994 manages and monitors environmental risk through a range of assessment, compliance, investigation, enforcement activities and waste management to protect our environment and ensuring no harm to the nature and environment around and within the construction site.





Variations to the Project
Variations must be determined based on a comparison against original/initial versions of documents.
	Variations to the scope of works
	Date of access to site and date of completion

	Variations to the contractual terms agreed upon with client
	The Date for giving possession of the site is changed from the original date of 25/02/2023 to new date of 5/03/2023 therefore the site access and commencement of the Project will be moved to the new date of 5/03/2023

The Date for Practical Completion is therefore pushed forward from the original date of 24/04/2023 to new date of 5/05/2023 


	Variations to the arrangements agreed upon with client
	The Date for giving possession of the site is changed from the original date of 25/02/2023 to new date of 5/03/2023 therefore the site access and commencement of the Project will be moved to the new date of 5/03/2023
The Date for Practical Completion is therefore pushed forward from the original date of 24/04/2023 to new date of 5/05/2023 


	Changes to construction drawings
	nil

	Changes to construction specifications
	nil
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