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	Site address
	Crn Monmudoo BLD and South Sea Islander way
	Project name
	Maroochydore private Hospital

	Client
	HopScotch
	Surveyor
	Crux




	
	
	Dates
	Provider details
	

	
	Task
	Ref #
	Notice date
	Date required
	Supplier
	Contractor
	Contact info
	Instructions

	
	Stage
	

	1. 
	Piling
	1
	01/01/2024
	15/01/2024
	Capoorn
	Capoorn
	Craig
	

	2. 
	Structure
	2
	01/04/2024
	30/04/2024
	Holcim
	TK Formbuild
	Chase
	

	3. 
	Façade Install
	3
	03/02/2025
	28/02/2025
	Fitout Glass
	Fitout Glass
	Ashley
	

	4. 
	Fitout
	4
	01/05/2025
	30/05/2025
	Boral
	Apex
	Mark
	

	5. 
	Lockup
	5
	03/02/2026
	28/02/2026
	Apex and Fitout
	Apex and Fitout
	Mark and Ashley
	

	6. 
	Roof on
	6
	03/02/2026
	28/02/2026
	Undercover roofing
	Undercover roofing
	Mitch
	

	7. 
	Landscaping
	7
	21/06/2026
	30/06/2026
	Landscape solutions
	Landscape solutions
	Jack B
	

	8. 
	PC
	8
	18/11/2026
	30/11/2026
	McNab
	McNab
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