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	Site address
	Lavarack Barracks, Townsville
	Project name
	EST09310 Lavarack Barracks New Locker Storage Building for 1st Military Police Battalion 

	Client
	Augility 
	Surveyor
	BMW Surveying Services 




	
	
	Dates
	Provider details
	

	
	Task
	Ref #
	Notice date
	Date required
	Supplier
	Contractor
	Contact info
	Instructions

	
	Stage
	

	1. 
	Bulk Earthworks – Site Cut
	1
	03/05/2024
	23/05/2024
	Civil Contractor 
	Mites Constructions
	Address: 7-9 Truscott St, Garbutt QLD 4814
Phone: (07) 4775 6044
	To commence works. 

	2. 
	Civil Works – Stormwater Drainage
	2
	09/05/2024
	29/05/2024
	Civil Contractor
Hydraulics Contractor
	Mites Constructions

Plumbwell 

	Mites Constructions: Address: 7-9 Truscott St, Garbutt QLD 4814
Phone: (07) 4775 6044

Plumbwell: 
Address: Hyde Park QLD 4812
Phone: 07 47 242 400 

	To commence works. 

	3. 
	Inground Services (Hydraulics)
	3
	09/05/2024
	29/05/2024
	Hydraulics Contractor
	Plumbwell 

	Address: Hyde Park QLD 4812
Phone: 07 47 242 400 

	To continue with works.  

	4. 
	Foundations – Bored Piers
	4
	21/05/2024 
	10/06/2024 
	Civil Contractor 
	Mites Constructions
	Address: 7-9 Truscott St, Garbutt QLD 4814
Phone: (07) 4775 6044
	To continue on with work required. 

	5. 
	Slab on Ground & Footings
	5
	N/A- completed by us. 
	17/06/2024 
	Concrete Works – completed by us 
	A. Gabrielli Constructions 
	Address: 336 Woolcock Street, Garbutt QLD 4814 
Phone: 07 4725 1100 
	To complete concrete works. 

	6. 
	Blockwork & Engaged Piers
	6
	12/06/2024 
	02/07/2024 
	Blockwork Contractor 
	Mascrete 
	Address: Hermit Park 4812

Phone: 0418 779 497 
	To commence works. 

	7. 
	Structural Steel & Roof Framing
	7
	20/06/2024 
	10/07/2024 
	Structural Steel Contractor 

Roofing Contractor 
	Norfab

VP Roofing & Home improvements 
	Norfab-
 Address: 1/61-67 Enterprise St, Bohle QLD 4818 
Phone: (07) 4725 7750

VP Roofing: 
Address: 
45 Pilkington St, Garbutt QLD 4814
Phone: 07 4779 1102 
	To commence Structural steel and roofing works. 

	8. 
	External Façade & Doors
	8
	05/07/2024
	25/07/2024 
	Carpentry Contractor 
	MST Constructions 
	Address: 137 Crocodile Cres, Mount St John QLD 4818

Phone: 07 4774 8750
	To commence works External façade and doors. 

	9. 
	Hydraulic Rough-in / Fit Off
	9
	05/07/2024
	25/07/2024 
	Plumbing Contractor 
	Plumbwell 
	Address: Hyde Park QLD 4812
Phone: 07 47 242 400 

	To complete Hydraulic rough-in / fit off. 

	10. 
	Electrical rough-in / fit off 

	10
	05/07/2024
	25/07/2024
	Electrical Contractor
	Waltlec Industries 
	Address: 22 Hugh Ryan Dr, Garbutt QLD 4814

Phone: 07 4725 5621 
	To commence works for Electrical rough-in / fit off. 

	11. 
	Lockers Installation 

	11
	N/A – Completed by us 
	20/08/2024
	Locker’s installation- completed by us. 
	A. Gabrielli Constructions Pty Ltd 
	Address: 336 Woolcock Street, Garbutt QLD 4814 
Phone: 07 4725 1100
	To install Lockers. 

	12. 
	Civil works and Landscaping 
	12
	15/07/2024
	01/08/2024 
	Civil Contractor 

Landscaping Contractor 
	Mites Constructions

Landscaping and Irrigation Specialists 

	Mites: 
Address: 7-9 Truscott St, Garbutt QLD 4814
Phone: (07) 4775 6044

LIS: 
Adress: 75 Northern Link Ct, Shaw QLD 4818

Phone: 0419 029 739 
	To commence Civil and Landscaping works. 
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