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BSBPMG407A 
Apply risk management techniques 
ASSESSMENT SUMMARY

The assessment activities for BSBPMG407A Apply risk management techniques cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	Participant Name
	STACEY LUI




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	

	Assessor Signature
	
	Unit Competence Determination Date
	Click here to enter a date.
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	Assessment Summary - BSBPMG407A Apply risk management techniques
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	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	STACEY LUI

	
	

	Participant signature
	
	
	

	Date
	5/07/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	16
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	




	ASSESSOR COMMENTS

	


[bookmark: _Ref20907937]Describe a project below. Conduct a SWOT analysis for the project. Identify at least two (2) points per area. 

	Project description
	Commercial Freezer roof upgrade- Darnley Island, Torres Strait.



	Answer
	Area
	Detail
	
	
	S
	Qualified and experienced staff
Local knowledge of site
	

	
	W
	Remote site = inability to quickly order missing materials
Haven’t completed many projects similar to this one

	

	
	O
	More thorough check of materials before commencement of job to ensure ALL materials are on site
Project team to clarify plans with engineers on areas that are not clear prior to commencement

	

	
	T
	Weather may cause delays
Material delays due to COVID

	





[bookmark: _Ref514160814]Consider the project you identified in Q1. For each of the areas identified in the table below, identify one (1) risk that may arise.

	Answer
	Area
	Project risk
	
	
	Environmental
	Site is close to ocean, and rubbish/debris could end up in ocean.
	

	
	Finance
	Progress claims could be delayed due to materials being delayed.
	

	
	Human resources
	Carpenter is not local, he could need to return home.
	

	
	Legal
	Injury/death on site
	

	
	Technology
	Phone lines go down and unable to communicate with engineers/ suppliers etc.
	




[bookmark: _Ref514164767]Using ticks, identify whether each of the risk analysis methods listed below is either ‘qualitative’ or ‘quantitative’. 

	Answer
	Qualitative
	Quantitative
	Method
	
	
			Analyses expected monetary value
	

	
			Considers likelihood of occurrence and impact on projective objectives
	

	
			Ranks risks
	



Refer to the Risk Matrix below when responding to Q4. 

	Matrix
	A:
Catastrophic
	B:
Major
	C:
Moderate
	D:
Minor
	E:
Insignificant

	1: Almost certain
	E
	E
	H
	H
	M

	2: Likely
	E
	H
	H
	M
	M

	3: Occasionally
	H
	H
	M
	M
	L

	4: Unlikely
	H
	M
	M
	L
	L

	5: Rare
	M
	M
	L
	L
	L



	E: Extreme
	H: High
	M: Medium
	L: Low




[bookmark: _Ref497316899][bookmark: _Ref514164832]Referring to your responses in Q2. rate each of the risks you identified using the Risk Matrix shown above. Identify the Likelihood and Impact you have determined, plus the overall risk rating. 

Prioritise each risk from 1 to 5 (1 = highest priority, 5 = lowest priority).

	Answer
	Area
	Risk rating
	Priority
	
	
	Environmental
	Likelihood:  2
Impact:  C
Risk rating:  H
	4
	

	
	Finance
	Likelihood:  3
Impact:  B
Risk rating:  H
	3
	

	
	Human resources
	Likelihood:  3
Impact:  B
Risk rating:  H
	2
	

	
	Legal
	Likelihood:  2
Impact:  A
Risk rating:  E
	1
	

	
	Technology
	Likelihood:  4
Impact:  C
Risk rating:  M
	5
	




[bookmark: _Ref408921427]Order the elements of the hierarchy of control, from 1 to 6 (i.e. most effective to least effective).


	Answer
	Label (1 – 6)
	Element
	
	
	3
	Isolate the hazard
	

	
	6
	Provide and use Personal Protective Equipment (PPE)
	

	
	1
	Eliminate the hazard
	

	
	4
	Control the hazard by engineering means
	

	
	5
	Control the hazard by administrative means
	

	
	2
	Substitute the hazard
	




[bookmark: _Ref514164849]Referring to your responses in Q2. propose one (1) risk control for the risk identified in each of the areas listed below. 

	Answer
	Area
	Risk control
	
	
	Environmental
	Provide skip bins with covers to avoid rubbish/debris blowing into ocean.
	

	
	Finance
	Negotiate progress payments based on time since commencement and/or progress milestones.
	

	
	Human resources
	Have a back up Carpenter on call to fill in if needed
	

	
	Legal
	Have employees complete thorough induction processes and sign on to all SWMS/JSA and WHS documents 
	

	
	Technology
	Purchase satellite phone to be kept on site
	



[bookmark: _Ref514164857]Which of the following parties should be consulted and agree to proposed risk managed strategies, plans and reporting mechanisms? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Project manager
	

	
		Project specialist
	

	
		Team members
	




[bookmark: _Ref497317794][bookmark: _Ref514164903]True or False (Tick your response): Organisations all use the same risk analysis methods, techniques and tools.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref497316910]Identify the four (4) options that may be followed once you have established the revised risk level.

	Answer
	Do Nothing
Implement risk controls
Reassess the risk
Accept the risk

	



[bookmark: _Ref514412892]What is the name of the risk level measured after risk controls have been implemented? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Initial risk
	

	
		Revised risk
	

	
		Residual risk
	

	
		Updated risk
	





[bookmark: _Ref514413216]On what document should incidents be recorded?

	Answer
	Issues Register
	



[bookmark: _Ref514413217]What is to be completed when a variation is to be made to the project?

	Answer
	Change request
	



[bookmark: _Ref514414036]True or False (Tick your response): You should report opportunities for action in the same way as risks.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref514668372]Identify two (2) types of documents that may be referred to when conducting a review of a risk management plan.

	Answer
	Project files, Risk diaries
	



[bookmark: _Ref514668814]Explain the relevance of evaluating project outcomes (e.g. agreed major milestones) as part of reviewing risk management activities.

	Answer
	Any mistakes in similar projects are not made again
Future incidents are better managed
Identification of areas that need to be closely monitored
Time is saved in the development of future risk management plans
	



[bookmark: _Ref514668929]True or False (Tick your response): You may refer to past projects for lessons learned regarding risk management, even when the past projects are not identical to the current one.

	Answer
		True 
	
	
	
		False 
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Stacey Lui

	
	

	Participant signature
	
	
	

	Date
	5/07/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
		
	Task 1 (Occasion 2)
		



	ASSESSOR COMMENTS

	


	BSBPMG407A
Apply risk management techniques

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to apply risk management techniques to complex projects– including, assisting with risk analysis, risk management planning and undertaking a review of risk management outcomes.

A complex project is defined as a project which involves:
· The need for a comprehensive and multi-faceted project plan
· The need for a formal internal or external communications strategy
· A dedicated and diverse project budget
· Multiple administrative components
· Multiple operational components
· A wide range of stakeholders
· A project operations team

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· SWMS review checklist completed by the Participant
· Task JSA completed by the Participant
· SWMS signed by the Participant
· Design risk assessment completed by the Participant

The observer is to outline the details of each project observed in the ‘Observer comments’ section. The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment.

	Resources required: 
Project records.

	Assessment of task

	Name of participant:
	Stacey Lui

	Name of observer:
	Shane Lui

	Role of observer 
(Confirm suitability to sign)
	Director

	Email address of observer
	Shane.lui@straitsupport.com

	Signature of observer:
	
	Date:
	1/07/2020
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1.A.  [bookmark: _Ref514164033]Contribute to identifying and prioritising potential risks throughout the project life cycle.
		
	1.B.  [bookmark: _Ref514164039]Within delegated authority, provide input to develop risk management strategies and risk management plans within established guidelines.
		
	1.C.  [bookmark: _Ref514164043]Establish risk analysis methods, techniques and tools to assist in the analysis of risks. 
		
	1.D.  [bookmark: _Ref514164047]Ensure reporting mechanisms for risks were planned for and agreed to.
		
	1.E.  [bookmark: _Ref514164051]Undertake control activities in accordance with agreed project and risk management plans to achieve project objectives.
		
	1.F.  [bookmark: _Ref514164054]Measure progress and act on perceived, potential or actual risks within authority – or report to others for response.
		
	1.G.  [bookmark: _Ref514164058]Contribute to the implementation of agreed risk approaches and the amendment of plans to reflect the changing environment.
		
	1.H.  [bookmark: _Ref514164064]Identify and report opportunities for action in the same way as risks. 
		
	1.I.  [bookmark: _Ref514164068]Contribute to the ongoing review of project outcomes to determine the effectiveness of risk management activities, accessing project records and other available information. 
		
	1.J.  [bookmark: _Ref514164072]Report risk management issues and responses to others for lessons learned or application in future projects.
		
	The Participant’s performance was:  Satisfactory     Not Satisfactory



	OBSERVER COMMENTS

	Stacey has been involved in creating a variety of WHS documents including JSA, SWMS and Risk Assessments and has a comprehensive understanding of risk management.
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