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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Kayla Watson

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	A building licence (QBCC licence in QLD) must be obtained in order to carry out: any building work valued over $3,300, building work valued over $1,100 where it involves Hydraulic Services Design, and building work of any value where it involves drainage, plumbing and drainage, gas fitting, termite management, fire protection, completed residential building inspection, building design – low rise, medium rise and open, and site classification. 

A person is considered to be ‘carrying out building work’ if they are personally carrying out the work, directly or indirectly, causing the building work to be carried out, or providing administration, advisory management or supervisory services for the building work.  
	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	The electrical contractor can complete an enquiry on the client’s behalf, if there is no electricity supply to site. The distribution Network Service Provider (e.g. Energex) will conduct the necessary network investigations and provide an indicative estimate of potential costs and timeframes for the client to make an informed decision within 20 business days. 

After agreeing to the connection offer, the electrical contractor will prepare the premises for connection. Once the work is complete, the electrical contractor will submit an Electrical Work Request (EWR) to the Distribution Network Service Provider. A copy of the EWR will be sent to the client’s preferred electricity retailer. 

Once all forms are received, the Distribution Network Service Provider will perform the requested work to the site. The service provider must adhere to timeframes for new connections e.g. Energex will attend the property within 5 business days.

Timeframes are dependent on network availability, access requirements, traffic control requirements, or any other impacts outside of the control of the service provider.  
	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	To organise water supply to site, a Water Approval application must be submitted (in South East QLD, this is submitted to Queensland Urban Utilities). This process works in conjunction with the Council evelopment assessment process, and the applications don’t need to be submitted at the same time. 

Water and Sewage approvals are customised for all scales of development from a new house to a large factory or multi-stage residential sub-division. 

Council will require evidence that a connection is available. This, and the timing of the two approvals, will depend on the complexity of the proposed development and the likely availability of services.

Standard connections for simple residential developments are usually completed within 5 days.
	



[bookmark: _Ref496611496]Which section of the Building Code of Australia outlines energy efficiency performance standards?

	Answer
	Section J
	




[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	Sustainable buildings are better for the environment as it conserves energy and reduces overall waste. 
	

	
	Client benefit
	The Client has long-term savings e.g. through the use of solar systems can increase the cost efficiency of the building. 
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Plumbing
	Organises water supply, installs pipes and drains, installs roof and guttering, fits taps, hot water systems and toilets, ensures downpipes are fitted and sewer is connected
	

	
	Excavation
	Prepares site for building by removing all vegetation and excavating footings
	

	
	Gas Fitting 
	Places gas pipes to appliances
	

	
	Concreting 
	Installs formwork and boxing; pours concrete (e.g. slabs)
	

	
	Bricklaying 
	Installs brick base (sub-base brickwork, dwarf walls and piers); installs walls 
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	4
	Floor frame
	

	
	5
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	6
	Electrical wiring
	

	
	2
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	3
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavators
	

	
	
	Duration
	Varies
	

	
	2: Slab or base stage
	Trades
	Plumbers, Electricians, Concreters
	

	
	
	Duration
	1-2 weeks
	

	
	3: Frame stage
	Trades
	Steelfixers, Plumbers, Electricians, Bricklayers, Carpentry 
	

	
	
	Duration
	3-4 weeks
	

	
	4: Lockup stage
	Trades
	Plumbers, Electricians,  Plastering, Waterproofers, Carpentry 
	

	
	
	Duration
	4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Plumbers, Electricians, Tilers, Lanscaping, Gas fitters
	

	
	
	Duration
	5-6 weeks
	

	
	6: Practical completion stage
	Trades
	[bookmark: _GoBack]Painters, Plumbers and Electricians (for final inspections), Landscaping 
	

	
	
	Duration
	7-8 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	1. Project size 
2. Height of Building
3. Location
4.Building Requirements e.g. appearance and finishes
5. Building complexity 
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	If requirements of the job are altered, this will change the initially projected timeframes, especially if additional materials and labour must be organised. 
	

	
	Labour availability
	It is important to effectively organise labour in accordance with the construction process sequence. A plumber / electrician cannot access behind walls once plastered up, therefore a plasterer should be organised after plumbers and electricians.
	

	
	Material availability
	It is important to ensure materials are delivered when the sub-contractor is ready to complete their work. Rare of difficult to source materials should be ordered in advance to avoid delays. If this does not happen, construction cannot continue effectively.
	

	
	Weather
	Inclement weather affects a trades ability to complete their jobs e.g. in-ground works cannot proceed in wet weather and construction sites have heat management policies in place to stop workers from working in extreme heat. 
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Dial Before You Dig is to be contacted before undertaking any excavation to ensure no services are damaged during construction
	

	
	Electricity
	Electricity may need to be disconnected prior to construction and temporary utilities are to be installed during the construction process
	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers 
	

	
	Waste disposal
	Designated area for rubbish bins and waste removal are to be set up. Check if permits are required to put bins in the street. 
	

	
	Water connection
	A plumber is to be booked to perform any required disconnections prior to any demolition taking place.
	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☐	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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