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CPCCBC4029B 
Apply construction information to the sales process


	[bookmark: _Ref396827952]THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Miljan Tepic

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	21/08/2019




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	18
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	


Outline the circumstances in which a building licence must be obtained before carrying out building work.

	Answer
	In NSW, a building licence is required before any residential work is carried out that is valued at more than $5,000 (incl. GST) in labour and materials.
This means work involved in constructing a dwelling, or altering or adding to a dwelling. Also includes repairing, renovating, decorating or applying protective treatment to a dwelling.
Some work that requires a licence includes:
-constructing or erecting a garage, carport or shed
-bathroom, kitchen or laundry renovations
-swimming pool building and structural landscaping
-screened, glass or pool enclosures
-atriums and conservatories
-house lifting

	



[bookmark: _Ref428791707][bookmark: _Ref496611482]Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

	Answer
	An electrical contractor (licensed) can complete the necessary enquiries and get in touch with the Distribution Network Service Provider who will conduct the necessary network investigations and provide indicative timeframes and estimated costs. 
If supply is available, the contractor will enter into a Network Connection Agreement with the Network Provider who will advise of a Connection Offer within 10 business days. Once agreement is confirmed, the contractor will prepare the site for connection and then submit a Work Request to the Network Provider. Once all these formalities are completed, the Network Provider will visit the site to complete the requested work. 

Timeframes vary and are dependent on factors including network availability, access, traffic control, weather etc.
	


[bookmark: _Ref496611484]True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496178501]True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

	Answer
	☒	True 
	
	
	
	☐	False 
	
	




[bookmark: _Ref496611488]Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

	Answer
	Organising water to site involves the submission of a Water Approval application to the relevant authority. In NSW, for example Sydney Water.
Water approval process works in conjunction with the Council development assessment process.
Simple residential connections can take usually 5 days to complete. Timeframes are dependent upon the complexity of the development and availability of water. The local council will require evidence that a water connection is available.
	



[bookmark: _Ref496611496]Identify the Volume and Parts of the NCC which outline energy efficiency requirements for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	

	
	Volume 2: Parts 2.6 and 3.12
	Volume 1: Part J
	





[bookmark: _Ref496611503]Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

	Answer
	Topics
	Definition
	
	
	Environmental benefit
	More environmentally friendly buildings with less carbon footprint.
	

	
	Client benefit
	Provides clients with unique selling features and long-term savings as well as possible reduced energy costs.
	




[bookmark: _Ref496611507]Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

	Answer
	Insurances
	Answers
	Definition
	
	
	1
	Builder’s All Risk
	1 -B
	A
	Covers personal injury or property damage.
	

	
	2
	Indemnity
	2 -C
	B
	Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits.
	

	
	3
	Public Liability
	3 -A
	C
	Covers costs where a contractor has caused building errors or omissions.
	

	
	4
	Workers’ Compensation
	4 -D
	D
	Covers death, injury or illness of employees.
	




[bookmark: _Ref496611511]True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

	Answer
	☒	True 
	
	
	
	☐	False 
	
	





[bookmark: _Ref496611526]Select and describe five (5) trades involved in the construction process.

	Answer
	Trade
	Description
	
	
	Excavation
	Prepares the site for building by removing all vegetation and excavating footings.
	

	
	Electrician
	Arranges electricity to be connected; places wiring for lighting and power cables; fixes switches; installs power points; wires electrical systems.
	

	
	Plumbing
	Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected.
	

	
	Steel fixing
	Installs reinforcement steel prior to the placement of concrete.
	

	
	Concreting
	Installs formwork and places concrete including finishing of concrete.
	




[bookmark: _Ref496611530]Order the following steps from 1 to 10 to identify an appropriate construction sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Floor frame
	

	
	4
	Windows and external door frames
	

	
	7
	Wall insulation
	

	
	1
	Set out
	

	
	9
	Painting
	

	
	5
	Electrical wiring
	

	
	6
	Plumbing of waste pipes
	

	
	8
	Internal linings
	

	
	10
	Landscaping
	

	
	3
	Wall frames
	



[bookmark: _Ref496611534]For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

	Answer
	Stage
	Description
	
	
	1: Clearing of the site
	Trades
	Excavation, survey
	

	
	
	Duration
	Varies
	

	
	2: Slab or base stage
	Trades
	Steel fixing, concreters, plumbers
	

	
	
	Duration
	1-2 weeks
	

	
	3: Frame stage
	Trades
	Carpenters, plumbers, electricians
	

	
	
	Duration
	3-4 weeks
	

	
	4: Lockup stage
	Trades
	Carpenters, plumbers, electricians, bricklayers, waterproofing 
	

	
	
	Duration
	4 weeks
	

	
	5: Fit-out or fixing stage
	Trades
	Electricians, plumbers, plasterers, tilers, carpenters
	

	
	
	Duration
	5-6 weeks
	

	
	6: Practical completion stage
	Trades
	Painters, landscapers
	

	
	
	Duration
	7-8 weeks
	



[bookmark: _Ref428791713]Identify five (5) factors that can affect the duration of each construction stage.

	Answer
	-project size
-height of the building
-building complexity
-quality requirements
-location
	



[bookmark: _Ref496611554]Describe how each of the following factors can affect construction times.

	Answer
	Factor
	Effect
	
	
	Changed conditions
	This can greatly affect a timeframe and the initial projections will change especially where additional labour and materials must be organised. With materials lead time is also a major concern.
	

	
	Labour availability
	The construction process sequence is very important when considering labour. I.e. carpenters cannot start on the building frame unless the base slab is poured. One trade being unavailable will have a negative impact on the subsequent labour requirements.
	

	
	Material availability
	Materials are required to complete work and should be ordered to be on site to match sequence. Long lead time items need to ordered well in advance or can hold a project up. Delays in materials can  elay the subsequent work.
	

	
	Weather
	Weather will affect site conditions and ability of trades to complete work. This becomes less of a problem when the roof and some plumbing is installed allowing indoor trades to continue even during inclement weather.
	




[bookmark: _Ref496611557]Describe the site establishment requirements for each of the points listed.

	Answer
	Requirement
	Description
	
	
	Earthworks
	Contact Dial Before You Dig before undertaking any excavation work to ensure services will not be damaged.
	

	
	Electricity
	Electricity may need to be disconnected from work zones prior to construction and temporary utilities installed for the duration of the construction process.
	

	
	Neighbours
	Provide advance notice to neighbours of intended start dates and site contact numbers.
	

	
	Waste disposal
	Set up a designated area for rubbish bins and waste removal. Check if permits are required to place bins on the street.
	

	
	Water connection
	Book in a certified plumber to perform any required disconnections prior to any demolition taking place.
	




[bookmark: _Ref496611559]Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

	Answer
	Regulation section
	Requirement
	
	
	Section 40
	The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety
	

	
	Section 41
	Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. 
	

	
	Section 308
	A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. 
	



[bookmark: _Ref496611563]True or False (Tick your response): The owner is able to access the site at any time.

	Answer
	☐	True 
	
	
	
	☒	False 
	
	




[bookmark: _Ref496611564]Which of the following parties should the client contact to access the site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	☒	Contractor
	

	
	☐	Local Government
	

	
	☐	Industry Regulator 
(e.g. Queensland Building and Construction Commission)
	

	
	☐	Subcontractors
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