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· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.
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Q1.  Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Commencement date
	

	
		Completion date
	

	
		Contract price
	




Q2.  [bookmark: _Ref425159148]Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

	Answer
	Suppliers
	Contractors
	
	
	Windows and doors
	Carpenter
	

	
	Floor Coverings
	Plumber
	

	
	Sand and Gravel
	Electrician
	




Q3.  [bookmark: _Ref530638037]Explain the difference between employees and contractors and how they are influenced by scheduling.

	Answer
	Employees work in a business under close direction from the builder whereas a contractor can decide what work they do the hours that they will work to get the job done. 
	



Q4.  [bookmark: _Ref530484357]Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

	Answer
	Local government authority – the local Council
Regulatory body - QBCC
	



Q5.  [bookmark: _Ref530484824]Why should colour selections be included on the schedules?

	Answer
	Some colour requests may require a special order and take more time than a standard colour selection
	


Q6.  [bookmark: _Ref530488884]True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

	Answer
	
	True 
	
	
	
	
	False 
	
	




Q7.  [bookmark: _Ref530576818]Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules. 

	Answer
	Noosa Shire Council – no audible noise allowed from building work between 6.30pm to 6.30am Monday to Saturday
Or anytime on Sunday or a public holiday.
These requirements are unlikely to affect my schedules as the permitted hours for noise are longer than usual work days. 
	



Q8.  [bookmark: _Ref425158650][bookmark: _Ref530483834]Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

	Answer
	Drawing/Specification
	Information provided for labour and material schedules
	
	
	Product specifications
	Includes items such as electrical goods, lights and switch types
	

	
	Colour specifications
	Colour selection for internal and external areas.
	

	
	Material specifications
	Details of the type, strength and size of materials to be used
	



Q9.  [bookmark: _Ref530577044]What three (3) things should a builder do when variations are made to a contract for a project?

	Answer
	Make changes to the schedule
Notify major suppliers
Make changes to call forward sheet

	



Q10.  [bookmark: _Ref530577045]Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

	Answer
	Variation
	Effect on schedules
	
	
	Moving internal wall
	No effect on schedule
	

	
	Changes to colour scheme
	Delay if special order needs to be done 
	




Q11.  [bookmark: _Ref530577046][bookmark: _GoBack]Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

	Answer
	Variation
	Effect on schedules
	
	
	Inclement weather
	Delay 
	

	
	Unexpected rocks discovered when footings are being excavated
	Delay
	



Q12.  [bookmark: _Ref530490108]Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

	Answer
	Step Number
	Steps
	
	
	1
	Builder to seek quotes from suppliers/contractors
	

	
	4
	Builder to note supplier/contractor details and ordering times on schedule
	

	
	3
	Builder to accept a tender
	

	
	2
	Suppliers/Contractors tender prices back to the builder
	

	
	5
	Parties to sign agreement
	




Q13.  [bookmark: _Ref530577300]What is an ‘overlay drawing’?

	Answer
	Drawings that show further detail on top of any existing plans and specifications
	



Q14.  [bookmark: _Ref530577354]Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	
	Architects
	

	
	
	Builder
	

	
	
	Draftsmen
	

	
	
	Engineers
	




Q15.  [bookmark: _Ref530577363]Identify three (3) details that should be included on a work order and reflected on the labour schedule.

	Answer
	Work
Time Period
Agreed rates
	




Q16.  [bookmark: _Ref530635543]Identify nine (9) details that should be included on a purchase order.

	Answer
	Order date and delivery
Purchase order number
Supplier details
Delivery details
Supplier contact information
Project manager details
Product description
Terms and conditions
Total order cost
	



Q17.  [bookmark: _Ref530490182]What is a ‘call forward sheet’?

	Answer
	A sheet used to track when materials are needed and when they should be ordered
	



Q18.  [bookmark: _Ref530635574]True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

	Answer
	
	True 
	
	
	
	
	False 
	
	




Q19.  [bookmark: _Ref530635589]Identify two (2) approved plans that should be included with the site documents.

	Answer
	Architectural plans and  stamped permit plans
	




Q20.  [bookmark: _Ref495585603]Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

	Answer
	Document
	Answers
	Definition
	
	
	1
	Permits
	1 - B
	A
	May include engineering data
	

	
	2
	Quotes
	2 - E
	B
	Council inspectors may issue a stop work notice until these documents are produced
	

	
	3
	Reports
	3 - A
	C
	Changes requested using a standard form in writing. Need to be signed by both builder and client.
	

	
	4
	Specifications
	4 - D
	D
	List the materials to be used, fittings and fixtures to be installed, and types of finishing required. 
	

	
	5
	Variations
	5 - C
	E
	Used to ensure purchase orders are developed using the correct price.
	




Q21.  [bookmark: _Ref530635990]In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

	Answer
	Trade
	Estimate
	Actual cost
	Cost difference
	
	
	Carpentry
	10,000
	8,500
	-1,500
	

	
	Electrical
	3,000
	4,250
	1,250
	

	
	Painting
	4,000
	3,900
	-100
	

	
	Plumbing
	8,000
	8,000
	0
	

	
	Tiler
	4,500
	4,750
	250
	




Q22.  [bookmark: _Ref530635991]In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

	Answer
	Item
	PC sum
	Actual cost
	Cost difference
	
	
	Basin taps
	100
	130
	30
	

	
	Oven
	2,500
	1,500
	-1000
	

	
	Rangehood
	500
	900
	400
	

	
	Shower bases
	250
	265
	15
	

	
	Shower screen
	400
	350
	-50
	

	
	Shower taps
	150
	120
	-30
	

	
	Stove
	900
	1,200
	300
	



Q23.  [bookmark: _Ref530636949]Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Builder
	

	
	
	Client
	

	
	
	Supplier
	




Q24.  [bookmark: _Ref530636951]Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Builder
	

	
	
	Client
	

	
	
	Supplier
	




Q25.  [bookmark: _Ref530636962]You are given the following table containing the costs for each month of the project. 

	Month
	Estimated cost
	Actual cost

	March
	$36,450
	$38,980

	April
	$65,560
	$62,350

	May
	$62,450
	$64,960

	June
	$61,340
	$61,050

	July
	$40,590
	$38,990

	August
	$42,650
	$42,550

	September
	$35,780
	$34,750

	Total
	$344,820
	$343,630



Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Plot both the estimated and actual costs on a graph
	

	
	
	Plot the actual cost on a graph
	

	
	
	Work out the difference between the estimated and actual costs
	



Q26.  [bookmark: _Ref530636963]The following graph is a visual representation of the difference in each month. 
[image: ]

By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	No, you cannot see this directly from the graph
	

	
	
	Yes, you can see this from the graph
	




Q27.  [bookmark: _Ref530636964]The following graph is a visual representation of the accumulated difference across the project. 
[image: ]

Overall, was the project overestimated or underestimated? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Overestimated
	

	
	     
	Underestimated
	



Refer to the following scenario and house plan to respond to Q28. to Q30. 

 (
SCENARIO
You are a 
site supervisor of a small residential project
, as
 outlined below:
The building is to be constructed using brick veneer.
The building has a floor area of 133 square metres including garage.
The concrete slab floor with garage floor is incorporated.
The building will be constructed using hand built wall frame and prefabricated roof trusses.
The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.
The driveway and landscaping are to be provided.
Services are available directly in front of the site.
The site is almost flat and will only need a scrape with minimal excavation.
The contract period is 120 days.
The total job has been pre-costed at $136,500.
Note:
 You are not required to estimate the quantity required.
)

[image: Plan of a house  single storey 3-bedroom residence with garage]
Q28.  [bookmark: _Ref530639450]Using the list of materials prepared, find the following information for four (4) materials of your choice:

	Answer
	Material
	Lead-in time
	Delivery date
	Order date
	Delivery requirements/ special considerations
	
	
	Windows
	4 weeks
	01/05/19
	08/04/19
	All windows delievered to relevant room on site
	

	
	Roof Trusses
	3 weeks
	14/04/19
	23/03/19
	Trusses to be laid flat on level surface
	

	
	Roof tiles
	3 weeks
	14/04/19
	23/03/19
	To be unloaded per builders instruction on site
	

	
	Bricks
	2 days
	16/04/19
	14/04/19
	To be distributed evenly around site 
	




Q29.  [bookmark: _Ref530641000]Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

	Answer
	Material
	Ordering process
	Considerations
	
	
	External cladding
	Measure amount needed
	Wastage
	

	
	Wall frame
	Measure off floor plan what is needed in lineal metres
	Wastage 
	

	
	Windows
	Send window manufacturers window schedule or site measure
	Reveal sizes
	



Q30.  [bookmark: _Ref530640532]While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client. 

	Answer
	[image: ]
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