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CPCCBC4007A 
Plan building or construction work


	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Haydn Morriss

	

	

	Participant signature
	



	Assessor name
	

	

	

	Assessor signature
	



	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Satisfactory?

	45
	
	Yes
	No

	
	
		

	ASSESSOR COMMENTS

	Answer to Q.13 is True, I was unable to fill in answer in box.
Thanks

Haydn


Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Project plans speifications
	



[bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	QBCC Act 1991 Sec 33
Sch 1B

	Work >$20,000 , 5% of total contract
Between $3,300 & $19,999 – 10%.
Penalty- Demerit points and QBCC can take further action

	




[bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Carpenter
	Install flooring, wall frames, decking etc
	

	
	Bricklayer
	Install brick base and walls
	

	
	Tiler
	Lay wall and floor tiles
	



[bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




[bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	[bookmark: _GoBack]To maximise efficiency of the whole building project
	



[bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	Phone around to determine who has adequate supply of needed materials.
Liase with known suppliers.

	



[bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	If supplies are in stockl
If supplies need to be transported from overseas or interstate 
	


[bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680
	



[bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Compressor
	To run power tools that require compressed air
	

	
	Tower lift
	To lift or suspend a load
	




[bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Ladder
	To reach heights
	

	
	Hammer
	To hammer nails
	




[bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	Invoices and receipts
	


[bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Power box
Water
Fencing
Waste Bin
Seepage Barrier
	



[bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




[bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





[bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	Ensure there is adequate room for trucks to stop
	



[bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Vol2 Sec2.5
	Vol 1 Sec D
	




[bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Compliance Assessment application , allow minimum of 10 working days for approval
	



[bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Boundary relaxation
	Siting Variation – Noosa Councill
	

	
	New Domestic Plumbing work
	Application for compliance assessment – Noosa Council
	



[bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	Purhase Order
	



[bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	Supplier
	



[bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	WHS Reg 2011
Sec 274
	Identify hazards
Assess the risk
Control the risk
Review risk controls
	




[bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	Workers are responsible for ensuring their own safety and that of others in the workplace
	


[bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Managing risks of hazardous chemicals in the workplace
	



[bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10m2
	



[bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	This can save time as the subcontractor can work on the next job while waiting for another to complete
	




[bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	For the job to run efficiently as possible and ensure that each trade is only there when needed and not ahead of when the job is ready for them
	



[bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




[bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	4
	Floor frame
	

	
	3
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





[bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9


 (
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	Answer
	
	



[bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

[bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





[bookmark: _Ref432123]Describe the critical path.

	Answer
	The shortest time to complete a job
	



[bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	Poor project management
Unreliable labour
Failing building inspection
	



[bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




[bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	To support prepared report, helpful if there is a dispute with neighbour
	


[bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




[bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	If damage has occurred due to the construction process
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