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Resilient Homes
Special Conditions
1) A joint bank account is required to be established between the client and Resilient Homes for the $275 000.00 clients cash component to ensure security over these monies.

2) Finance Approval documentation is to be provided for the $390 000.00 loan amount.

3) Client is to provide their company Public Liability, Work Cover and QBCC Licence for their Window supply company.

4) Client is to provide Form 15 for the supply and manufacture of Aluminium window frames and glass shower screens.

5) Construction period excluding inclement weather and possible delays = 23 weeks.

6) Colour selections are to be completed and signed off no later than receiving frame stage progress claim.

7) The client must adhere to all company Work Place Health and Safety Policies and Procedures and the Work Health and Safety Act 2011

8) The client must email the Customer Service to arrange site inspections and or site visits. The client must not enter the site without prior approval a Resilient Homes Representative.

9) Progress claims will be drawn at the following stages of construction
· Please note: Under the QBCC Act - Resilient Homes will not accept extra deposit payment for priority construction etc



PROGRESS CLAIM SCHEDULE


1) Deposit				   5%
2) Slab complete 			 15%
3) Frame stage 				 20%
4) Enclosed stage			 25%
5) Fixing stage 				 20%
6) Completion / Final 			 15%
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