PRACTICAL ASSESMENT 1

Extension of time notice:

The contractor wishes to claim an extension of time of the Date of Practical Completion (PC)
	To: (Owner’s name and address)
	Jim Jones, 50 Wylma Street, Holland Park

	From: (Contractor’s name and address)
	Pelican Constructions, 17 Burke Street, Coorparoo

	The cause of the delay in achieving Practical Completion is:
	We had storms Monday, Tuesday and Wednesday of this week, including 25mm of rain – which made working dangerous and almost impossible.

We didn’t work any of the days for obvious reasons, so we are 3 days behind the planned schedule. The weather is forecast to improve later this week and early next week so we are likely to stay just 3 days behind.

	Cause of delay: (select whichever is applicable)
	Adverse weather.

	The delay arose on:
	Wednesday 7th October 2020

	Number of additional business days claimed by the contractor as a consequence of the delay
	3

	New date for practical completion:
	Wednesday 28th October 2020

	Signature of contractor’s representative:
	[image: ]     Matt Cumiskey

	Note to owner:
	The contractor must give you this form within 10 business days of the delay occurring. If contractor’s claim for an extension is accepted, then the date of practical completion will be extended by the number of business days specified above. Your acceptance, rejection or partial rejection of the contractor’s claim must be specified in this form and returned to the contractor within 10 business days of receiving the claim.

	Owner to select applicable response:
	The owner agrees with the extension of time claim.

	If partially rejected, please select the number of business days rejected:
	N/A

	The reason/s for rejecting all of part of the extension of the claim is/are:
	N/A

	Signed by the owner/owner’s representative:
	[image: ]     Jim Jones





Communication of defects to sub-contractor:
Hey Tony,

Just sending through a list of tiling defects from 50 Wylma Street in Holland Park that will be required to be completed before the practical completion date of 3rd November 2020:
· Tiles in shower strip drain do not line up perfectly with the tiles on the floor inside the shower of the main bathroom
· Chipped tile was installed in kitchen splashback
· Some grout missing on the wall tiles in the ensuite
Please let me know what day you will be on site to fix these things up and please don’t hesitate to get in contact with me if you have any issues.
Thanks
Matt Cumiskey
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