Cashflow

The below cashflow is from a previous project where we highlighted what was left to be completed ahead and cross hatched out the previous months actually completed.
[image: ]

Project Budget
The budget below highlights the estimate for the project highlighting what the tendered budget was and then a revised budget setting a target budget for the project.
[image: ]
Book Keeping and transaction recording
Below are examples I have pulled from Jobpac our accounting system highlighting;
1. Extract from Pending Invoices within the system that have been coded to cost centres.
[image: ]
2. [image: ][image: ]Invoice below relates to 1st item in the above pending invoice report.



















3. Transaction confirming payment of a previous invoice (for another project).
[image: ]

Supplier Account notices with trading terms
Below is an invoice from Boral confirming we have them on a 30 day EOM (End of Month) account and have an extract from the supply agreement highlighting the terms agreed to. We request invoice on the 25th of the month allowing to deal with BCIPA.
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Acknowledgement of Association
I am used to understanding checks about companies / subcontractors and typically we do ABN searches as well as QBCC licence searches as below. This is for WINFAB owned by Andrew Windolf;
[image: ][image: ]
Profit and Loss Statement
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Cost Comparison Report – Highlighting actuals and forecasting against the budget[image: ]
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Business Activity Statement
[image: bas report]
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PAYMENT

(@)

(b)

(©)

(d)

The Supplier may make payment claims progressively on a monthly basis on the 25th day of each month
from the date of execution of this contract.

Each payment claim shall be in the form of a tax invoice in the form required under A New Tax System
(Goods and Services Tax) Act 1999 (“GST Act”) and must contain details of the actual cost of work carried
out by the Supplier in accordance with the rates in Schedule 1 and must provide copies of tax invoices for
any outlays claimed and compliance with these requirements shall be a precondition to payment and if not
provided or incomplete or false the Purchaser may withhold payment in full until a complete and true progress
payment claim is received.

Subject to clause 4(d), the Purchaser is to pay each payment claim within 25 business days from the date
the Purchaser receives the payment claim.

Should the Purchaser dispute any part of the payment claim, the Purchaser will provide written notice to the
Supplier within 10 business days of receiving the claim. The Purchaser does not have to pay any disputed
amount.




image8.png
RALM E;E:-—:-z“:—mnmumm TAX INVOICE

e

Ao Agent o Bl Rescuren (0 Py L ABK: 4600967139
Document Number  : Q1519042

Date : 230420
Cotomar ocston 2o
Aocouns ayate CutomerOrtr o wa
MEAB NGFTY LTD | Comer Ot “
PoBOKZI4 )
TOOWOOUBA LD 4350 Cutomer Ao et
Totalexcluding GST st
GST Payable s1ma30
Total $8,573.33
(umply cuden T
“This Invoica is Du for Payment By,
3twAv-2020

01 Bt Gonncts cusame ot canhlp you g conree e,k e s eport o o
TS o e g0 e Com s oty B Feprsaraie.

AccountContact: Dotbi Honderson Stles Conact: 07 3687 7600
R 073007 7065
& 07 3007 7465
o dobiaranderson@bonatcomau
Pleass sand your Remitance Advice befors 6pm o th day f Paymt o Accounts Recsivable@boralcom.au
For 3l e comespondence and accountauere, Feass Contact your AGcoun Contac decty.

PAYMENT METHODS
refrred method i EFT (ntemet Banking) Send Remitance Advice ONLY to:
Rccourts Recenable@boraLcom .
(2 Pay Elctrnically via EFT Internt Banking = Pay by Creat Cara
Bank: Natonai Ausial Bark R rcharg wh apiy o 0.8% e Vi and Mastrcard, 2.7 o
Bank Account:  Bors ACM. Amarcan Exoress an 3% o Dnrs (s GS1)
Bse: o2
Bank Account No 137263600
0 Pay by Mt
jg Pororaear Mako your checue payate i BrslConsnucton Matrias
ikl — G ik an ik payment i .
Refersnce Number: 207734 o 5o, —
oo your Financil o 1 ki paynat om your ety

o Pamamata W 2124




image9.png
Licence Number: 1152075
Particulars
Business Name: Windolf, Andrew Bradley

Licence Address: 58 NORTH STREET TOOWOOMBA QLD 4350

Trading Name: Winfab.Com
MR Category: Self-Certification 2 - up to $600,000
Licence Class Licence Grade Condition* Status
r ral M Fabrication an: Trade Contractor -
E - Licence NO Active

* NOTE: Where QBCC has imposed a condition, details of the condition can be obtained by downloading a licensee’s full
history.

Click here for a Glossary of Terms

IMPORTANT: The latest version of Adobe Reader is required to create a licensee's full history. You should uninstall any
old versions of Adobe Reader before downloading the current version.
Click on the Get Acrobat Reader link to download the latest free version.
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#ify e | ABN Lookup

Austraian Business Regiter

Current details for ABN 15 872 868 237

ABN details

Entity name: WINDOLF, ANDREW BRADLEY
ABN status: Active from 06 Dec 2015
Entity type: Individual/Sole Trader
Goods & Services Tax (GST): Registered from 01 May 2016
Main business location: QLD 4350

Business name(s)

Business name From
Winfab.com & 10 Apr 2016

Trading name(s)

From 1 November 2023, ABN Lookup will not display trading names and will only display registered business
names. For more information, click help.

Trading name From

ANDREW B WINDOLF 05 Oct 2006

ABN last updated: 09 May 2016 Record extracted: 07 Nov 2018
Disclaimer

The Registrar makes every reasonable effort to maintain current and accurate information on this site. The
Commissioner of Taxation advises that if you use ABN Lookup for information about another entity for
taxation purposes and that information turns out to be incorrect, in certain circumstances you will be
protected from liability. For more information see disclaimer.
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PROJECT BUDGET

Budget Proposal from Estimator and GM/CM Budget Margin Call

Project Name:|Catholic Education Office - Toowoomba Project No: 18053 18053
Estimator Budget Proposal B
Signature
: 7 required before|
item |Trade Tender Sum | EStimator Budget | Diff. from Estimator Comments PM Budget Diff from tender letting this
Proposal Tender
trade? YIN
T[Preliminaries $493.421 $485,981 757,440 | Delete Amenities & Lunchroom. Use on $18,421
sie facilities
2| Metaworks $71518 571,518 50 $71518] 50)
3|Demolition $121,330 $63,750 557,580 Use late quote $63,750 557,580
4[External Works Including $58,968 $62,118 $3,150]tem missed al tender ime 562,118 $3,150
Landscaping
5[Civil Works Including AT $402,649 402,649 0 402,649 50
External Concrete
6In-Situ Concrele $462.918 562,916, 0 $12.918
7|Masonry $179,410) $179.410 50 179,410 50
8[Structural Steel $150,700 $159,700 50 §159,700 50
5[ Timber Work 23,850 $23,859) 50 523,859) 50
T0[Termite Barriers 58,260 58,260 50 58,260 50
11 [Tanking & Waterproofing 59,522 59,522) 50 $9,522 50
12|Roofing & Roof Plumbing $100,161 $100,161 50 $100,161 50
13|Cladding 591,637 591,637 50 591,637 50
T4[Aluminium Windows & $547,165 $547,165 50 $547,165, 50
Doors
75|Doors, Door Furniture & 588,452 $86,452 50 88,452 50
Operable Walls
76[Metal Pariiions & Linings 272,831 $282.851 10,000 ltem missed al tender time 50
17 Joinery 548,150 48,150 50 $48,150 50
18[Fixtures 539,687 539,687, 50 539,657 50
19]Tiing 551,962 551,962 50 551,962 50,
20[Carpel & Resient Finishes $122,498 $122,498 50 §122,498 50
21[Painiing $250.245 246,000 $44.245 246,000, $44,245|
22[Electrical $062,264 962,264 50 522,264
23[Fire Services 593,610 593,610 S0 50
24[Hydraulics $404,130 $404,130 50 514,130
25[Lift Services 599,920 590,920 50 599,920 50
26[Mechanical $202,140 $292,140 S0 262,140 50
27|Provisional Allowances $50,000 $50,000) 50 $50,000 50
$0
$0
$0
$0!
$0
50
$0
$0
$0
$0
Subtotal $5,546,407 $5,450,292 596,115 $5.379,999
Margin $274,333 $344,626
Total §5,724,625 $5,724,625 $5,724,625
Margin on turnover 3.11%) 4.79% 6.02%
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AUSSIE HIRE PTY LTD
ABN 84 009 794 290

102 VIKING DRIVE, WACOL QLD 4076

PO BOX 405, INALA QLD 4077
PH: 07 3271 4500

Date: 30-Apr-2020

1x SPLIT SYSTEM AIR CONDITIONER (SACSPL30)
11 x DESK (4000)

11 x SWIVEL CHAIR (4010)

1 x PLAN BENCH (4025)

9 x STACKER CHAIR (4020)
1 x FIRST AID BED (4080)

1 x BAR FRIDGE (4156)

3x SINK UNIT (4120)

3x HYDRO-BOIL (4145)

24 x STACKER CHAIR (4020)
3 x TABLE (4005)

1 x MICROWAVE (4160)

Invoice No: 311005

Payment Terms: Strictly 30 days from Invoice Date

EFT payment details:

Please quote your Account No. as your payment reference
Account Name: Aussie Hire Pty Ltd

BSB: 034 043 Account No.: 130599

Please cut along the line & return botiom section with payment, thank you

Sub-Total:
GST:
TOTAL:

$1,414.21

$141.42

$1,555.63
Page 20f 2
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AUSSIE HIRE PTY LTD

ABN 84 009 794 290

102 VIKING DRIVE, WACOL QLD 4076
PO BOX 405, INALA QLD 4077

PH: 07 3271 4500

Date: 30-Apr-2020 Invoice No: 311005
TAX INVOICE Contract No.: 45506
MCNAB DEVELOPMENTS (QLD) PTY LTD
PO BOX 2304 Site: CNR CURLEW & HERON DR, PORT OF BRI¢
TEOWOANBEA:GLD! 4550 CNR CURLEW & HERON DR
PORT OF BRISBANE
Account No: C1564 Order No: 19005001
Date From DateTo  Description Amount
01-Apr-20 30-Apr-20 7.2M X 3M END MODULE (SP7.239). $47.14 per week for 4 $202.03

weeks, 2 days (hire continues...)
Hire Start Date: 28/11/2019 & previous invoice number: 309872

01-Apr-20 30-Apr-20 7.2M X 3M INFILL (SP7.2310). $47.14 per week for 4 weeks, 2 $202.03
days (hire continues...)

01-Apr-20 30-Apr-20 7.2M X 3M INFILL (SP7.2311). $47.14 per week for 4 weeks, 2 $202.03
days (hire continues...)

01-Apr20 30-Apr-20 7.2M X 3M INFILL (SP7.2312). $47.14 per week for 4 weeks, 2 $202.03
days (hire continues...)

01-Apr20 30-Apr-20 7.2M X 3M INFILL (SP7.2313). $47.14 per week for 4 weeks, 2 $202.03
days (hire continues...)

01-Apr-20 30-Apr-20 7.2M X 3M INFILL/KITCHEN (SP7.2314). $47.14 per week for 4 $202.03
weeks, 2 days (hire continues...)

01-Apr-20 30-Apr-20 7.2M X 3M END MODULE/ABLUTION (SP7.2315). $47.14 per $202.03

week for 4 weeks, 2 days (hire continues...)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL20)
1 x SPLIT SYSTEM AIR CONDITIONER (SACSPL21)
1x SPLIT SYSTEM AIR CONDITIONER (SAGSPL22)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL23)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL24)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL25)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL26)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL27)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL28)
1x SPLIT SYSTEM AIR CONDITIONER (SACSPL29)




