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CPCCBC4007A 
Plan building or construction work


	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances. 
Answers will be documented and FT003 (Oral examination declaration form) must be completed.
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a participant changes their response in writing, they must put their initials next to the written change.
· If a participant changes their response verbally, this must be noted on the exam paper by the assessor.
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	Date
	Click here to enter a date.
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	Number of questions answered correctly
	Satisfactory?

	45
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	No

	
	
		

	ASSESSOR COMMENTS

	


Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Scope of Works
	



[bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements. 

	Answer
	Section of Act
	Requirements and penalties
	
	
	Queensland Building and Construction Commission Act 1991 (Qld)  - “Division 2 Payments relating to contracts”
	Maximum Deposit Amounts – 
Level 1 regulated contract: 10% of contract price
 Level 2 regulated contract: 5% of contract price
Level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price, 20% of contract price. 
Maximum penalty – 100 penalty units
	




[bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Plumbing
	Organises water supply, installs pipes and drains, installs roof and guttering, fits taps, hot water systems & toilets, ensure downpipes are fitted and sewer is connected
	

	
	Electrician
	Arranges electricity to be connected, places wiring for lighting and power cables, fixed switches, installs power points, wires electrical systems.
	

	
	Bricklaying
	Installs brick base (sub-base brickwork, dwarf walls and piers), installs walls
	



[bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




[bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	It is important for creating an accurate project schedule and determining a timeframe for the job. It is also important to know availability to ensure the job process goes smoothly and no unexpected delays are caused. There is also no point in hiring a subbie or plant if they are not available in the time required to do the job. 
	



[bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	Call around to different suppliers to check material availability
Obtain quotes from different suppliers to compare pricing 
	



[bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	Location of site
[bookmark: _GoBack]Outsourcing
	


[bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680
	



[bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Scissor Lift
	To access areas too high to reach with a ladder 
	

	
	Excavator
	Digs trenches in-ground 
	




[bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Lifting Gear and Harnesses
	To ensure safety when working at heights or in confined spaces 
	

	
	Jackhammers
	To remove concrete in a small area.
	




[bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	Invoices 
Plant Risk Assessments 
	


[bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	Water Tapping to supply water to site
Electrical pole or power box
Temporary fencing
Barricades 
Tiger strips 

	



[bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	
	True 
	
	
	
	
	False 
	
	




[bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




[bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





[bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	Excavation works 
	



[bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume 2 Section 3 Part 3.9
	Volume 1 Section D Part D3
	




[bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	Submit an Operational Works/Compliance Assessment SmartForm. Must submit a site-specific Construction Noise Management Plan, a copy of the letter that will be provided to premises/residents who would likely be affected. A Minimum of 10 working days is required for council to asses an application.  
	



[bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Lane or Road Closure Permit
	Traffic management plan for temporary lane/road closure, copy of development assessment approval, must complete online application for temporary road occupation form. Approval Body is BCC.
	

	
	Footpath Closure Permit
	Site plan sketch, approval plans, site photos, traffic management plan, and an application/notice to work on council property online form. Approval body is BCC.
	



[bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	A Purchase Order
	



[bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	The Supplier 
	



[bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	The Work Health and Safety Act 2011 Section 17-18
	A duty imposed on a person to ensure H&S requires the person to eliminate risks to H&S, so far as is reasonably practicable, and if not reasonably practicable, to minimise those risks so far as is  reasonably practicable. 
	




[bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	Work Health and Safety Regulation 2011 (Qld)
	


[bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheets (SDS)
	



[bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10
	



[bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	It helps with minimising skilled labour from moving off-site when there is work to be done on nearby projects. This saves a great deal of time, as the subbies can work on the next job while waiting for another to complete. If the subbies move to another location it can be difficult to ensure their return for the next stage of the project.   
	




[bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	Sequencing is important as if you’re not aware of the activities that must be done on the project, you cannot successfully plan. You could also be doing activities that disadvantage the projects timeline or may become irrelevant in the future. You could be doing smaller jobs first and then realise that you’ve run out of time or money to complete the job. 
	



[bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




[bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	2
	Excavation of footings
	

	
	3
	Floor frame
	

	
	4
	Installing brick base
	

	
	6
	Roof trusses
	

	
	1
	Set out
	

	
	5
	Wall frames
	





[bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
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[bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Excel
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

[bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




[bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





[bookmark: _Ref432123]Describe the critical path.

	Answer
	The shorted completion time possible to complete a job. 
	



[bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




[bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	Weather
Material Delivery
Resources e.g. unreliable labour
	



[bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




[bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	Take photos to support your report on the condition of existing neighbouring properties as it will be helpful in the event of a dispute with a neighbour. 
	


[bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




[bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	Prior to commencing construction, to see the site status before work commences and to identify if any damage has occurred through the construction process.
	



Page 4 of 14	CSTC Pty Ltd_0699_v1-2_07/02/2019

CSTC Pty Ltd_0699_v1-2_07/02/2019	Page 3 of 14
image2.png




image3.png
Enquiries,
orders

Wait
bricks.

Clear
site

o)

Wait
concrote





image4.png




image5.png




image6.png
Enquiries,

vaitbrcs oy Load bricks

3

Clear site.

concrete

T





image1.PNG




