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[bookmark: _Toc523902164]Written Questions 
[bookmark: _Toc414527050][bookmark: _Toc523902165]Part 1 – Project Scope 
	1. Which of the following are project initiation documentation required at the start of the project?

Select all that apply.

	

	|_|
	a. Communications log

	[bookmark: Check1]|_|
	b. Project plan

	|_|
	c. Work Breakdown Structure (WBS)

	|_|
	d. Gantt Chart

	|_|
	e. Project charter

	|_|
	f. Risk management


[bookmark: _Toc433005346][bookmark: _Toc443292693][bookmark: _Toc444260194][bookmark: _Toc446066025]

	2. Which of the following are components of a project scope-management plan?

Select all that apply.

	

	|_|
	a. Project deliverables

	|_|
	b. Project staff assignments

	|_|
	c. Change request

	|_|
	d. Project justification

	|_|
	e. Product description

	|_|
	f. Performance reports

	|_|
	g. Project objectives

	|_|
	h. Project funding requirements

	|_|
	i. Quality metrics

	|_|
	j. Budget forecasts





	3. In your own words, discuss how project time and cost affect the project scope. Do not exceed 100 words.

	

	Scope, time and cost are part of the projects constraints.  If a change in one factor e.g. time, will invariably affect the other two, scope and cost. An example is the project budget is reduced then the scope will have to change.





	4. Which of the following are events or problem areas relating to project scope that could trigger the need for a formal change request?

Select all that apply.

	

	|_|
	a. The deliverables may not meet quality requirements.

	|_|
	b. Grammatical and typo errors are found in the project initiation documents.

	|_|
	c. The deliverables may not be what the client wanted, even though they were covered in the project plan.

	|_|
	d. The stakeholder considers the change request and advises the project manager.

	|_|
	e. Observance of non-working holidays affecting project time.

	|_|
	f. Additional quality requirements (such as new legislation or changes in standards) will render the deliverables non-compliant.

	|_|
	g. Failure of equipment needed to produce the deliverables.

	|_|
	h. Missing documentations in the project’s information system.

	|_|
	i. Raw materials are no longer available.

	|_|
	j. Supplier or contractor closing business.




	5. Which of the following are procedures that typically must be followed under change control processes?

Select all that apply.

	

	|_|
	a. Project manager seeks advice from supervisor regarding changes in cost.

	|_|
	b. Project manager assigns a project team member to recalculate for the critical path.

	|_|
	c. Project manager provides the change request to the appropriate stakeholder for approval.

	|_|
	d. The stakeholder considers the change request and advises the project manager.

	|_|
	e. The project manager updates the project plan and other documentation where required.

	|_|
	f. Project manager drafts the change request.

	|_|
	g. Project manager delegates the authority to the project team members in advising other stakeholders of the changes.

	|_|
	h. The project manager advises relevant stakeholders (sponsor, team members, etc.) of the changes.

	|_|
	i. Details of the proposed change to be communicated to the project manager.

	|_|
	j. The project sponsor and owner may automatically terminate the project contract.




	6. The following are methods of measuring work outcomes and progress against plans. Match each method to its correct description.

Write the letters that correspond to your answers in the spaces provided.

	

	
	Method
	Description

	c
	Units completed
	a. Also known as the ‘steps’ method, this is used for projects that involve subtasks that need to be completed in an orderly fashion.

	a
	Incremental milestones
	b. In this method, tasks that are being calculated tend to occur over a longer duration time and include multiple subtasks, where subtasks can have different units of measurements.

	d
	Start / finish
	c. This method is used when project tasks are done repeatedly. Assuming that each task is completed at the same amount of time, resources and effort, each task is counted and totaled.

	b
	Weighted or equivalent units
	d. This method is used to determine the percentage of the work completed and the percentage of the work that is still yet to be completed.




	7. Which of the following are activities involved in decomposition of the total work project?

Select all that apply.

	

	|_|
	a. Summarise project tasks in the form of a written report.

	|_|
	b. Identify and analyse the deliverables and related work.

	|_|
	c. Structure and organise the work breakdown structure (WBS).

	|_|
	d. Arrange the smallest project tasks to form an aggregate representation of the total project task

	|_|
	e. Decompose the upper work breakdown structure (WBS) levels into lower level detailed components.

	|_|
	f. Calculate duration and resource effort for each project task.

	|_|
	g. Develop and assign identification codes to the WBS components.

	|_|
	h. Inspect whether work and deliverables meet requirements and product acceptance criteria. 

	|_|
	i. List resources required for each project task.

	|_|
	j. Verify that the degree of decomposition of the work is necessary and sufficient.




	8. List three (3) ways in which the Work Breakdown Structure (WBS) can be created.

	

	a. Using phases of the project lifecycle
b. Using major deliverables 
c. Using subprojects which may be developed by organisations outside the project team




	9. The following are some problem areas in scope management. In your own words, briefly discuss each problem area.

Do not exceed 100 words for each discussion.

	

	Problem areas
	Discussion

	Scope creep
	It refers to changes, continuous or uncontrolled growth in a project's scope at any point after the project begins 

	Sponsor / project owner approval
	A sponsor / project owner approval is a person or group who provides resources and support for the project, program or portfolio for enabling success. 

	Project team accountability
	Project team accoutability is provide a team with a set of expections, milstone and performance which are success 




	10. In your own words, discuss the significance of scope management. 

Do not exceed 150 words.

	

	Project scope management refers to the set of processes that ensure a project's scope is systematically processed to capture, define and monitor scope to accurately ensure that the controls are in place for what is included and what is not included of the project's scope.  




	11. The PMBOK Guide outlines the following processes in project scope management. List one (1) tool or technique used in each process.

	

	Project Scope Management
	Tool or technique

	Collect requirements
	Focus groups 

	Define scope
	Product analysis

	Create WBS
	Decomposition 

	Verify scope
	Inspection

	Control scope
	Variance analysis 





	12. Consider the roles and responsibilities of the project manager in project planning. List five (5) roles of the project manager in project planning and list at least one responsibility for each of these roles.

	

	Roles
(list five (5))
	Responsibilities
(List at least one (1) for each role)

	Understanding the project
	Fully understand and know the reson why the project is initiated, key stakeholders expectations  and deliverables of the project 

	Scope Management
	ensure all requiremnts are taken dow and turned them into work packages

	Time Management
	Scheduleing the prject and coming up with the schedule baseline

	Cost Management
	Cost baseline

	Quality Management
	define what good quality means from your stakeholders and plan the AQ and QC activities




[bookmark: _Toc523902166]Part 2 – Project Time 
	1. The following are estimation tools and techniques used in determining duration. Match each tool and technique to its correct description.

Write the letters that correspond to your answers in the spaces provided. 

	

	
	Estimation tools and techniques
	Description

	b
	Analogous estimating
	a. This technique uses a statistical relationship between historical data and other variables to calculate an estimate for activity duration.

	a
	Parametric estimating
	b. This uses parameters such as duration, budget size, weight, and complexity, from a previous, similar project, as the basis for estimating the same parameter to measure for a future project. This technique relies on the actual duration of previous, similar projects as the basis for estimating the duration of the current project.

	e
	Three-point estimating
	c. This is guided by historical information. It provides duration estimate information or recommended maximum activity durations from prior similar projects. This can also be used to determine whether to combine methods of estimating and how to reconcile differences between them.

	c
	Expert judgement estimating
	d. Contingencies are accounted for into the overall project schedule to account for schedule uncertainties.

	d
	Reserve analysis
	e. This technique uses a mathematical formula to determine a weighted average of estimates. It uses the formula:.





	2. The following are estimation tools techniques used in determining activity resource. Match each to its correct description.

Write the letters that correspond to your answers in the spaces provided. 

	

	
	Estimation tools and techniques
	Description

	d
	Expert judgment
	a. Several companies or organisations routinely distribute updated production rates and unit costs of resources for an extensive array of labour trades, material, and equipment for different countries and geographical locations within countries.

	e
	Alternative analysis
	b. In this technique, when an activity cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The resource needs are estimated. These estimates are then aggregated into a total quantity for each of the activity’s resources.

	a
	Published estimating data
	c. This tool has the capability to help plan, organise, and manage resource pools and develop resource estimates.

	b
	Bottom-Up estimating
	d. This technique is often required to assess the resource-related inputs to this process. Any group or person specialised with knowledge in resource planning and estimating can provide such expertise.

	c
	Project management software
	e. These include using various levels of resource capability or skills, different, size or type of machines, different tools (hand versus automated), and make-or-buy regarding the resource.




	3. In identifying the critical path, the following parameters need to be determined for each task. Discuss each parameter.

Do not exceed fifty (50) words for each discussion.

	

	Parameter
	Discussion

	ES
	Earliest start time - earliest time which the task can start, given that nay predecssor tasks must be completed first

	EF
	Earliest finish time - earliest start time for the task plus the time required to complete the task

	LF
	Latest finish time - Latest time at which the task can be completd without delaying the project

	LS
	Latest Start time - Latest finish time minus the time required to complet the task




	4. Which of the following statements accurately explain the process of developing the project schedule, including the schedule baseline?

Select all that apply.

	

	|_|
	a. Developing the schedule is the process of analysing activity sequences, durations, resource, requirements, and schedule constraints to create the project schedule.

	|_|
	b. The project schedule and schedule baseline are developed or established using the activity lists, activity attributes, project scope statement as the bases.

	|_|
	c. Entering the activities, durations, and resources into the scheduling tool generates the schedule baseline.

	|_|
	d. Tools and techniques used in developing the project schedule and schedule baseline include decomposition of the total project work.

	|_|
	e. Developing the schedule baseline starts and ends in the planning phase of the project.




	5. Schedule control is the process of monitoring the status of the project to update project progress and mange changes to the schedule baseline. 

Which of the following are processes that are involved in schedule control?

Select all that apply.

	

	|_|
	a. Determining the current status of the project schedule.

	|_|
	b. Defining activities or specific actions to be performed to produce project deliverables

	|_|
	c. Influencing the factors that create schedule changes

	|_|
	d. Decomposing total project work into its lowest levels.

	|_|
	e. Determining that the project schedule has changed

	|_|
	f. Estimating duration and resource effort for the project.

	|_|
	g. Managing the actual changes as they occur.





	6. Consider the methods used in project time management.
a. In your own words, discuss the application/use of the Gantt Chart. Do not exceed fifty (50) words.
b. List three (3) project data generated from the Gantt Chart.  
c. List three (2) limitations of the Gantt Chart.

	

	a. An analyses tool to graphicall represent the project's activities, the time to complete and the sequen in which to complete.
b. Activities
Time
Sequence
c. Continual updating
Extraordinarily complex
Unclear amount of work expected





	7. Consider the methods used in project time management.
a. In your own words, discuss the application/use of the Critical Path Method. Do not exceed fifty (50) words.
b. List three (3) project data generated from the Critical Path Method.  
c. Discuss the limitation of the Critical Path Method. Do not exceed fifty (50) words.

	

	a. A process for looking at actitivies that must be completed and calculating the critial path in minimum amount of time
b. Parameters of each task
Critical path
Activities on the critical path
c. Critical Path Method limitations is that it works on assumptions not real practice, time estimates are not based on statistical analysis and can't be used as a controlling device, as any chance will change the entire structure of network.





	8. The following are tools and techniques used in project scheduling. Match each tool and technique to its correct description.

Write the letters that correspond to your answers in the spaces provided.

	

	
	Project scheduling tools and techniques
	Description

	b
	Schedule network analysis
	a. This is the process of looking at all of the activities that must be completed, and calculating the 'best line' – or critical path – to take so that you'll complete the project in the minimum amount of time. The method calculates the earliest and latest possible start and finish times for project activities, and it estimates the dependencies among them to create a schedule of critical activities and dates. 

	a
	Critical Path Analysis
	b. This is a graphic representation of the project's activities, the time it takes to complete them, and the sequence in which they must be done. Project management software is typically used to create these analyses. Common formats for this include Gantt Charts and PERT Charts

	d
	Schedule compression
	c. They expedite the scheduling process by generating start and finish dates based on the inputs of activities, network diagrams, resources, and activity durations.

	c
	Automated scheduling tools
	d. This tool helps shorten the total duration of a project by decreasing the time allotted for certain activities. It's done so that you can meet time constraints, and still keep the original scope of the project. 





	9. Which of the following statements accurately explain the work breakdown structure (WBS) including its application in project schedules?

Select all that apply.

	

	|_|
	a. Work breakdown structure (WBS) is the subdivision of project deliverables and project work into smaller, more manageable components.

	|_|
	b. The work breakdown structure (WBS) identifies project personnel who are responsible for each project task.

	|_|
	c. Work breakdown structure (WBS) helps define activities of the project which provide the basis for estimating, scheduling, executing, and monitoring and controlling the project work.

	|_|
	d. The work breakdown structure (WBS) is used to represent the full project scope of the project.

	|_|
	e. The work breakdown structure provides the relationships among all components of the project and the project deliverables.

	|_|
	f. The work breakdown structure (WBS) is used as the basis for the scope baseline which is used in identifying activities or specific actions to be performed to produce of the project deliverables.

	|_|
	g. Project work at lowest levels are not included in the work breakdown structure (WBS)




[bookmark: _Toc523902167]Part 3 – Project Cost 
	1. The following are processes involved in project cost management including budgeting the cost of the project. In your own words, discuss each.

Do not exceed fifty (50) words for each discussion.

	

	Estimating costs
	Estimating cost is an approximation of the monetary resources need to complete the project activities.

	Determine budget
	The process of aggregating the estimated costs of individial activities or work packages to establish an authorised cost baseline. 

	Control cost
	Monitoring the status of the project to update the project budget and managing changes to the cost baseline 





	2. The following are different tools and techniques used in cost management. Match each to its correct description.

Write the letters that correspond in the spaces provided.

	

	
	Strategy
	Description

	b
	Analogous estimating
	a. This is used to establish both the contingency reserves and the management reserves for the project with regards to cost.

	c
	Parametric estimating
	b. This strategy uses the values of costings from a previous, similar project as the basis for estimating the same parameter or measure for a current project. This is used when the current project is similar to a previous one in terms of defined parameters.

	e
	Cost aggregation
	c. This uses a statistical relationship between historical data and other variables to calculate and estimate for cost. This technique is used to produce higher levels of accuracy depending upon the sophistication and underlying data built into the model. Estimates made through this project can be applied to the whole project or to segments of a project.

	a
	Reserve analysis
	d. These are used to develop mathematical models to predict total project costs. 

	d
	Historical relationships
	e. Cost estimates are combined by work packages in accordance with the Work Breakdown Structure. The work package cost estimates are then combined for the higher component levels of the WBS and ultimately for the entire project.

	g
	Earned value management
	f. In this technique cost performance measurements are used to assess the magnitude of variation to the original cost baseline.

	f
	Variance analysis
	g. This is commonly used as a performance measurement. It integrates project scope, cost, and schedule measure to help the project management team asses and measure project performance and progress. 



	3. List four (4) processes which are followed in monitoring the project costs against outcomes to ensure that additional expenses are not incurred.

	

	a. Spreadsheet or financial management sorftware packages
b. Sending invoices on a regular basis
c. Paying invoices promptly
d. checking incoming invoices against contracts, quotes, agreements etc




	4. You are appointed as one of the Project Managers of Bigger than Big Corporation. As one of the Project Managers, it is essential that you have a full understanding of the organisation’s policies and procedures relevant managing projects within Bigger than Big. 

Review Bigger than Big Corporation’s Project Management Policy and Procedures (username: cstclearner password: CstcPty@123).

a. In your own words, discuss the organisation’s Project Management Policy, including its background, purpose, and its scope. 
b. In your own words, discuss the organisation’s Project Management Procedures including their purpose and scope.
c. In your own words, list and discuss the Project Phases prescribed in the organisation’s Project Management Procedures.

Do not exceed 100 words for each discussion.

	a. The background provides a commitment by the corporation to meet the mission and values of the company. The purpose is provide a consistent approach within the organisation on their deliverables.  The scope demostrates how the  projects will be delivered project in context of policies and procedures of the company.
b. The purpose of the procedures is to ensure throughout the life of a project that management is effiecient and effective. The scope outlines what a project is, timelines and it defined phasses and project management methodology.
c. Pre-initiate Phase  - solve a problem, improve a process or implement a new service.  This phase is the initial assessment of a project.    
d. Initiate Phase - how a project will be executed - investigation of the project
e. Plan phase - how a project will be conducted - schedule and budget information.
f. Implement Phase - how the project outputs will be delivered
g. Close Phase - a formal closure of the delivery component of the project - handover and evaluation                                     




[bookmark: _Toc523902168]Part 4 – Project Quality 
	1. In your own words, discuss each of the following key concepts in Quality Management. 

Do not exceed 100 words for each discussion.

	

	Key Concepts in Quality Management
	Discussion

	Customer satisfaction
	Customer satisfaction is a key measure (meeting project requirements) and indicator (customer expections) of the projects quality. Customer satisfaction can identify whether project is a success. 

	Prevention over inspection
	Cost of Quality includes money spend during the project to avoid failures and money spent after the project from failures.  

	Continuous improvement
	Ongoing effort to improve your services, product etec over time.



	2. In your own words, discuss the difference between Quality Assurance and Quality Control.

Do not exceed 100 words.

	

	Quality Assurance is process oriented, by using processes and techniques such as review, training facilitation etc. a primary audit function.
Quality Control is product oriented. A process for testing and detection of defects. Primary an inspectin  function.




	3. The following are standards that could apply in various projects. In your own words, discuss each standard. Do not exceed fifty (50) words for each discussion.

	

	People standards
	Requirements / Education / training / competency needed to compelete work on a project e.g. scaffolding requiring licensing etc

	Process standards
	Processes for delivering a project and assurance that these process are being meet

	Product / service standards
	Ensuring the product meets required standards (Australian, International etc) / guidelines



	



	4. The following are quality assurance and control methods, techniques and tools. Match each to its correct description.

Write the letters that correspond to your answers in the spaces provided.

	

	
	Methods, tools, techniques
	Description

	h
	Benchmarking standards
	a. This is a distribution of dots comparing two variables. If the two variables are completely independent you would expect the dots to be evenly distributed randomly across the graph. If there is a strong relationship though, the graph will show a straight line or a mathematical curve going through it.

	g
	Brainstorming sessions
	b. These are graphical representations showing a visual impression of the distribution of data. Usually it shows the frequency up the Y axis of the bar graph and the measuring variable along the X axis.

	d
	Control charts
	c. It is a graph where the X axis is time dependent. This allows you to look for time-based cycles in processes.

	f
	Flowcharts
	d. These are also known as Shewhart charts or process-behaviour charts. These charts are used to statistically measure the quality characteristics of a process are under control. This is based on a statistical analysis where a centre line is drawn for the mean of the output, then an upper control limit and a lower control limit is created either side of the centre line. The process is then measured over a period of time and the results plotted on the graph. Once the graph has been created, it can be analysed to test the stability of the process and also any cycles of errors.

	b
	Histograms
	e. It is very similar to a histogram, but it includes a line over the graph indicating the cumulative distribution of the results.

	e
	Pareto charts
	f. A diagram that represents a process. It shows the steps visually as a series of boxes with arrows in between them showing the work flow. Rectangular boxes represent tasks and diamond shaped boxes represent decision points, where the flow can split into two or more directions.

	c
	Run charts
	g. It occurs when a group meets and is presented with a scenario where they creatively come up with a range of solutions.

	a
	Scatter grams
	h. These may be dictated to by legislation through Federal, State or Local Government regulations, and may be dictated by industry bodies.





	5. List five (5) responsibilities of the project manager in quality management.

	

	a. Determing the quality standards for the project deliverable
b. Determing the quality standrds for the project proces
c. Documenting all the required standards in the project plan
d. Coaching and mentoring project eam members as needed to assist in achieving the porject quality objectives
e. Conducting, or coodinating, project audits
f.      





	6. The following are methods used in managing continuous improvement. In your own words, discuss each method. 

Do not exceed fifty (50) words for each discussion.

	

	Six Sigma 
	Techniques and tools for porcess improvement, identifying and removing the causes of defect and minimising variability in manufacturing and biness processes

	Lean Six Sigma
	Collaborative project team effor to improve performance by systematically removing waste

	Total Quality Management
	Ongoing refinement in response to continuous feedback re improvements of products and services





[bookmark: _Toc523902169]Case Study
[bookmark: _Toc446066023][bookmark: _Toc523902170]Instructions to Student
These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.


[bookmark: _Toc446066024][bookmark: _Toc523902171]Introduction
	You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd.  Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle.
You have already provided advice to Awesome Landscapes in the previous workbook.
Today is 24 July 20xx. The project will shortly progress into the implementation stage. You have now been provided with up-to-date project documentation below, including an updated Project Plan. The project steering committee have reviewed the Project Plan, but they wish to have you conduct an independent evaluation of the project prior to signing it off.
As part of your consultancy services, you will be assisting the team in addressing issues around project constraints by answering the questions that follow this scenario.
The documents you need to complete the succeeding tasks can be accessed through the following links:

Project Charter version 2 (.pdf)
Project Plan version 2 (.pdf)
Project Gantt Chart version 2 (.mpp)
Project Gantt Chart version 2 (.pdf) 
Project Network Diagram version 2 (.pdf)
(username: cstclearner password: CstcPty@123)

Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.




	1. List the three (3) project deliverables in Phase 1.

	

	a. Removal of vegetation in areas being cleared and replanting / maintaing the plant for replanting in stage 3
b. Access roads through the existing forest for builders to access each building site
c. Retaining walls to provide stability around the building. Includes three addtioanl retaining walls as per updated site plan



	2. Discuss the project constraints in terms of scope, time, cost, and quality. 

	

	Scope
	The landscaping work must work around the building construction

	Time
	Completion of all work within nine months

	Cost
	Fixed Budget of $550,000 + GST

	Quality
	The natural environment must be carefully preserved as per the strict Council requirement from environmentally sensitive areas. Other conditions imposed by Council



	3. Review the project schedule as set out in the Project Plan and the Gantt Chart Arrange the following tasks in the proper sequence as dictated in Phase 3 of the critical path. 

Write 1 – 12 in the spaces provided; where 1 go first and 12 go last.

	

	8
	Remove weeds

	11
	Plant additional plants

	2
	Move gravel to car park

	1
	Expand car park

	12
	Remove greenhouses

	9
	Plant plants from greenhouses

	3
	Seal car park

	6
	Soil preparation

	7
	Add boulders

	5
	Construct stone paving pathway

	10
	Purchase additional plants

	4
	Landscape over old access roads




	4. Review the Project Plan. The change request has outlined one change in the scope of the project. 
a. What is the change in scope? 
b. How does this change in scope impact the overall duration of the project?
c. How does this change in scope impact the quality aspect of the project?

	

	a. Three new retaining walls need to be added due to a change in the construction plan requiring more chalets to be built
b. No change to the overall duration of project
c. The addition of three extra retaining walls has also resulted in additional time being allocated to the excavation of the incoming utilities and septic system



	5. Why does the change request only list one change in project cost, yet when you look at the financial tables the costs seem to have increased in numerous parts of the project not even related to the item in the change request?

Do not exceed 100 words.

	

	While there has been a change to the scope and cost, there has been no change to the finishing time. The procurement cost for construct access roads has increased due to the scope change, so the original contingency will require adjustment.  In addition, duration of days has increased in Phase 1 relating to project management, project support staff, project meetings.  




	6. Who is responsible for working out these impacts of what initially seemed to be such a simple change, and ensuring all affected stakeholders understand the impact of such a change?

	

	All suggested changes to project scope, time, cost, quality, human resources, communications, risk, procurement and integration will be sent to the project manger who will populate the information into a change request. 



	7. Access and review the Gantt Chart version 2.
a. What important tasks are not included in the project Gantt Chart?
b. Discuss why these tasks must be included in the Gantt Chart? Keep your discussion within 100 – 200 words in length.

	

	a.      
b.      



	8. List the three (3) personnel who signed off on the change request.

	

	a. Susan Wills Program Maanager, Massive Eco-Development Corportation
b. Stephen Lyons (Planning Manager, Cascade Peaks Shire Council
c. Kim Nguyen (Director, Awesome Landscapes Pty Ltd)



	9. What is the total increase in cost of the project as a result of this change request?

	

	$17,900



	10. List five (5) exclusions under Stage 2 – Building Support of the Scope Management Plan.

	

	a. Monitoring and maintaining partially and full constructed buildings
b. Monitoring and maintaining the main road
c. Instalation of utilities
d. Installation of pipes and tanks
e. Purchase and maintenance of additional native plants to replace any that have perished.



	11. Review the Project Plan. Does it follow the change management procedure? Explain your reasoning. 

Do not exceed 50 words.

	

	A draft request will go to the planning manager of Cascade Peak Shire Council who will advise if a new Council approval is needed as part of the proposed changes.
Once Council approvals have been granted , the matters within the change requet will be modified with the project plan and other prject documentation as required.
If appears that the above requirements have not been completed prior to seeking approval by the Stakeholders being notified





	12. Access and review the Gantt Chart version 2. It shows double bars for each task.
a. What do the coloured bars                    represent?
b. What do the grey bars                represent?
c. Why do the grey and coloured bards do not match up in the Gantt chart?

	

	a. Dark Blue Progress and Light Blue Manual Progress
b. External Tasks
c. They have only listed the tasks and have shown any external task of progress



	13. Assuming the project runs on schedule, list two (2) tasks that should be in progress if Sam was to visit the site on Monday 22 August. 

Do not include the task ‘Project Management’.

	

	a. Completion of access roads
b. Install road gravel



	14. If Sam was to visit the site on Thursday, 22 September, he will see that two (2) tasks are in progress, namely:
a. Construction of retaining walls.
b. Install and compact soil behind walls.

According to the procedure documents, these two activities cannot happen at the same time. The retaining wall has to be built first. Once construction is completed, the soil needs to be added behind. Why are these two tasks in progress on the same day?

	

	Construct retaining walls. To be conducted between Monday 9 September and Friday 23 September. • Install and compact soil behind retaining walls. To be conducted between Thursday 25 August and Thursday 15 September. Appears there is an erro in the Gantt chart / schedule and compaction was completed prior to the retaining walls bing constructed.



	15. According to the Gantt Chart, if there is a delay in the completion of Task 57 ‘Construct stone paving walkway’,
a. Which tasks, if any, are immediately delayed?
b. Will this delay push out the completion of the project? Why or why not?
c. Discuss how this could affect the resourcing of the project.
d. List one (1) risk that could arise from this issue.

	a. Erecting Signage, Detailed Landscaping, Planting 

b. 11th March is when planting will be completed however if the delay is miminal extra resources can finish the project on time. 

c. Could increase resourcing for the project.

d. Additional cost - over run of continguency



	16. What is the total budget for the project expenditure?

	

	$462,153




	17. Sam is very concerned about the cash flow of the project. 
a. What is the problem?
b. What would you suggest be done to rectify the cash flow issue?

	

	a. Before the 3rd installment the project will run short on cash flow

b. However, Awesome has reserve cash to cope with the potential to expend up $224,724



	18. Discuss whether Awesome Landscapes should seek increased funding from Massive Eco-development Corporation to absorb some or all of these cost increases.

Your discussion must be 200 – 300 words in length.

Guidance:
The change requests have incurred extra expense, yet the funding to be paid by Massive Eco-development Corporation has not changed. 

If you believe Awesome Landscapes should seek increase funding from Massive Eco-development Corporation, provide a strong argument for your case. If not, explain your reasoning.

	

	As per the project plan outline in section 4.5 Source of Funds, it clearly states that: This is a fixed price contract, so the funds provided will be the same regardless of any project extensins, variations in scope, or increases in cost of labour, procurement or purchases.
As this is clearly outlined in the project plan and assuming in the contract there would be no avenue for to request additional payment for the variation. 



	19. Complete the following Audit Template with the standards determined in the previous question (Case Study Question 18). This will be given to an internal auditor to audit the financial processes at various points along the project.
Guidance: Complete only the fields highlighted in yellow. Do not complete the ‘Assessment’ and ‘Comment’ fields under ‘Audit of Management of Project’.

	

	     



	Quality Audit Template

	Project Name: Cascade Peak Chalets Landscaping Project

	Prepared by: Rue Grimston

	Date: 

	Project Manager: Sam Ng, Awesome Landscapes

	Project Phase: 
	Overall Project Status: 

	Audit Date: 
	Audit Number: 
	Audit Leader: 

	Audit Team: 

	Goal(s) of This Specific Audit:  Construction of Retaining wall as per the Building Standard (structual retaining walls) 

	Audit of Management of Project: 

	1.      
	Assessment: 
	Comment: 

	2.      
	Assessment: 
	Comment: 

	3.      
	Assessment: 
	Comment: 

	4.      
	Assessment: 
	Comment: 

	5.      
	Assessment: 
	Comment: 

	6.      
	Assessment: 
	Comment: 

	7.      
	Assessment: 
	Comment: 

	8.      
	Assessment: 
	Comment: 

	9.      
	Assessment: 
	Comment: 

	Overall Assessment of Management of Project: 


	Recommended Action(s)/Lessons Learned Regarding Management of the Project: 
1.  
2.  
3.  

	Additional Audit Comments: 
1.  
2.  
3.  

	Have you attached additional material(s)?
	
	yes
	
	no

	Name(s) of attachment(s): 
1.  
2. 

	Audit Report Submitted To: 
	Date: 







	20. Sam has provided you with the following audit from a previous project (landscaping the new Cascade Peak Shopping Centre). Evaluate the audit report below and answer the following questions:
a. What was the cause of the unsatisfactory results?
b. What action would you recommend to prevent the issue coming up again in this project?

	

	a. Insufficient detailed information given in a timely manner

b. Regular briefing with additional supporting information to complete tasks, without have to verify




	Quality Audit Template

	Project Name: Cascade Peak Chalets Landscaping Project

	Prepared by: Sam Ng

	Date: 17 August 2015

	Project Manager: Sam Ng, Awesome Landscapes

	Project Phase: Implementation
	Overall Project Status: On schedule

	Audit Date: 17 August 2011
	Audit Number: 26
	Audit Leader: Sam Ng

	Audit Team: Sam Ng, John Cowley, Ann Deak.

	Goal(s) of This Specific Audit: To evaluate the communication and reporting processes.


	Audit of Management of Project: 

	1. Are tasks being communicated to site supervisor in a reasonable amount of time?
	Assessment: 
Satisfactory.
	Comment: 

	2. Are tasks being communicated to site supervisor of sufficient detail?
	Assessment: 
Not satisfactory. 
	Comment: 
Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks.

	3. Are tasks being communicated by the site supervisor to the team members and contractors done in a reasonable amount of time?
	Assessment: 
Not satisfactory.
	Comment: Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks.

	4. Are tasks being communicated by the site supervisor to the team members and contractors of sufficient detail?
	Assessment: 
Satisfactory.
	Comment: 

	Overall Assessment of Management of Project: 
Tasks being communicated to the supervisor do not have the level of detail required by the site supervisor. In particular detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager.

	Recommended Action(s)/Lessons Learned Regarding Management of the Project: 
1.  Project manager to prepare task briefs in enough time to add the required level of detail.
2.  Task briefs are to be supplied with all relevant attachments such as detailed plans.

	Additional Audit Comments: 
1.  
2.  
3.  

	Have you attached additional material(s)?
	
	yes
	x
	no

	Audit Report Submitted To: Kim Nguyen
	Date:  24/08/2015




	21. The quality plan is very weak on cost management. Write a Cost Management Plan (of 200 – 300 words) for managing the quality of the financial processes while the project is in progress. 
Guidance: Your Cost Management Plan must cover the following quality objectives and criteria.
a. Meeting with contractual requirements.
b. Paying invoices on time.
c. Ensure invoices are sent out in time.
d. Ensuring financial reporting is done on time.
e. Include a calendar of when payments are likely to be due.
f. Comparison of actual cash flow against projected cash flow.

	

	     







[bookmark: _Toc523902172]Workbook Checklist
	When you have completed this workbook, please ensure you have completed all parts of it:
|_| Written Questions
|_| Part 1 – Project Scope
|_| Part 2 – Project Time
|_| Part 3 – Project Cost
|_| Part 4 – Project Quality
|_| Case Study

IMPORTANT REMINDER
Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject.

To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.
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