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CPCCBC4007A 
Plan building or construction work 
ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	Participant Name
	Jessica Manley




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	

	Assessor Signature
	
	Unit Competence Determination Date
	Click here to enter a date.
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	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	[bookmark: _Ref396827952]Participant name
	Jessica Manley

	
	

	Participant signature
	
	
	

	Date
	19/04/2021



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	45
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	




	ASSESSOR COMMENTS

	


Q1.  Name one (1) document you might read alongside the contract to identify the following aspects:
· Material requirements
· Plant requirements
· On-site labour requirements
· Any unusual aspects of construction

	Answer
	Project Plan Specifications
	



Q2.  [bookmark: _Ref336349][bookmark: _Ref535482381]Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

	Answer
	Section of Act
	Requirements and penalties
	
	
	Queensland Building and Construction Commission Act 1991 – Part 4, Division 2
	Level 1 contract: 10% deposit of contract price
Level 2 contract: 5% deposit of contract price
Level 1 or 2 contract under the value of the off-site work is more than 50% of the contract price: 20% deposit of contract price

Maximum penalty is 100 penalty units.
	




Q3.  [bookmark: _Ref336355]Identify three (3) subcontractors you may engage for a job and the type of work they may undertake. 

	Answer
	Subcontractor
	Work
	
	
	Plasterer
	Fix, set and sand to wall and ceilings.
	

	
	Concreter
	To lay down the slab (foundation) to build on.
	

	
	Glazier
	Supply and install glazed windows and doors.
	



Q4.  [bookmark: _Ref346751]Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Advertising
	

	
		Networking
	

	
		Online searches
	

	
		Tenders
	

	
		Word of mouth
	




Q5.  [bookmark: _Ref336359]Explain the importance of determining subcontractor or plant availability for a job.

	Answer
	It is important to be sure the subcontractors or plant equipment is available for the job otherwise if they are not, this will cause a delay in the construction program. It can also add more costs to the project, in the instance that the subcontractors prices you used for the initial quote are not available, you would then have to source other subcontractors. The new subcontractor you have to use may be more expensive resulting in a loss at the end of the project..
	



Q6.  [bookmark: _Ref336365]Identify two (2) methods you might use to find a supplier for materials.

	Answer
	Two methods you can use to find suppliers could be ringing around to different suppliers. In some cases, if they don’t have a product you need, they will pass on details of another supplier who would. Also going online and doing a few searches will usually bring up several suppliers who will offer the materials you are wanting. 
	



Q7.  [bookmark: _Ref336369]Name two (2) factors that may impact on the availability of materials.

	Answer
	One factor that may impact availability when getting materials from suppliers could be if they are imported. Sometimes there is delays in the shipments. Also if the material is a popular item amongst fellow builders, the item could run out at times, resulting in you unable to buy the item. 
	


Q8.  [bookmark: _Ref446563]Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

	Answer
	AS/NZS 1680.0
	



Q9.  [bookmark: _Ref351751]Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Plant
	Work
	
	
	Excavator
	Used for excavations but also heavy lifting, demolition, river dredging, cutting of trees etc. 
	

	
	Tower Crane
	Used on tall commercial structures, Tower Cranes hoist up heavy materials like concrete slabs, steel trusses, frames and other materials.
	




Q10.  [bookmark: _Ref356099]Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for. 

	Answer
	Equipment
	Work
	
	
	Wheelbarrow
	Used to carry products or materials from one area to another with ease.
	

	
	Trestle
	Used as a wide and long step to reach areas a short distance above you. 
	




Q11.  [bookmark: _Ref351753]Identify two (2) of the records you should keep when hiring plant and/or equipment.

	Answer
	Records you should keep when hiring our plant/equipment is the documentation that shows the items have been designed, constructed and tested in compliance with applicable WHS legislation and relevant Australian Standards. Another is the record details of the inspection of the equipment.
	


Q12.  [bookmark: _Ref438091]Name five (5) temporary services that need to be organised for a building site.

	Answer
	A few items you will need to organise for a building site is a temporary electrical pole for use of power, a water tap, temporary fencing, portable toilet if toilets are not accessible and waste bins. 
	



Q13.  [bookmark: _Ref438093]True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

	Answer
	    
	True 
	
	
	
		False 
	
	




Q14.  [bookmark: _Ref336377]What is required of a builder before any person is allowed on a building site? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		To check the person has a Construction Induction Card 
	

	
		To check the person has the approval of the local council
	

	
		To check the person is wearing appropriate signage
	

	
		To keep a record of all inductions and all personnel on the site
	




Q15.  [bookmark: _Ref336379]Who issues a construction induction card? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Australian Parliament upon fee payment
	

	
		Each site at the conclusion of a site induction
	

	
		Registered Training Organisations at the conclusion of training
	





Q16.  [bookmark: _Ref445773]Identify one (1) action you might take to facilitate site access for machinery. 

	Answer
	You should always ensure there is enough room around the site roads for trucks to stop and use the machinery from the side of the road onto the sites.
	



Q17.  [bookmark: _Ref427235149]Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

	Answer
	Classes 1 and 10
	Classes 2 to 9
	
	
	Volume Two – Part 2.5
	Volume One – Part D3.2
	




Q18.  [bookmark: _Ref343117]You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval. 

	Answer
	You should allow a minimum of 10 working days for your out of hours request to be approved by the council. You will be required to submit the operational works/compliance assessment form. Along with that form, a site-specific construction noise management plan will be mandatory and a copy of the letter which will be provided to premises/residents who are likely o be affected, which must state; after hours contact name and phone number for the company, date and times the construction activities will take place and the type of construction taking place.  
	



Q19.  [bookmark: _Ref336392]In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval. 

	Answer
	Permit
	Documentation and approval body
	
	
	Footpath Closure Permit
	Permit to close pathways and work on pathways open to the public. You will need to supply documents with this application such as; Site plan sketch, approved plans, site photos and traffic management plan,
	

	
	Commercial Plumbing and Drainage Permit
	This permit is used for a sewered or unsewered commercial construction project. Along with this permit form, you will need to supply documentation of; site plans, site and soil evaluation report, soil classification report, articulation plan and the receipt for payment of fees.
	



Q20.  [bookmark: _Ref424211634]True or False (Tick your response): Project commencement date is always at the date the contract is signed.

	Answer
		True 
	
	
	
		False 
	
	




Q21.  [bookmark: _Ref346763]What document should be developed when purchasing supplies or construction materials?

	Answer
	Purchase order
	



Q22.  [bookmark: _Ref336403]True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

	Answer
		True 
	
	
	
		False 
	
	




Q23.  [bookmark: _Ref336405]Who should be contacted if items are missing from a delivery?

	Answer
	The supplier the items came from.
	



Q24.  [bookmark: _Ref355889]Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

	Answer
	Section of Act
	Requirements
	
	
	Section 17 and 18
	Consider and weigh up relevant matters including; the likelihood of the hazard or risk concerned occurring, the degree of harm that might result from it, what the person concerned knows regarding the hard or risk and ways to eliminate it. Also, the availability and suitability of ways to eliminate it and after assessing the extent of the risk or hazard, the cost associated with eliminating the hazard or risk.
	




Q25.  [bookmark: _Ref355891]Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

	Answer
	One regulation an organisation must comply with is duty to notify of notifiable incidents.
	


Q26.  [bookmark: _Ref359896]What document should be followed when disposing of hazardous materials?

	Answer
	Safety Data Sheets
	



Q27.  [bookmark: _Ref359873]An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

	Answer
	10m2
	



Q28.  [bookmark: _Ref359880]True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

	Answer
		True 
	
	
	
		False 
	
	




Q29.  [bookmark: _Ref417694]True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

	Answer
		True 
	
	
	
		False 
	
	




Q30.  [bookmark: _Ref417696]What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

	Answer
	Hiring the same subcontractor to work on 2 sites nearby is an advantage as this can save time. The subcontractor can work on the  next job while waiting for another to complete. 
	




Q31.  [bookmark: _Ref422991]Provide one (1) example to explain why construction operations must be sequenced.

	Answer
	If operations are not sequenced, this can cause delays in the program. This can be due too one area not being ready for a subcontractor, resulting them having to come back, and they may not be available. For e.g. Painter is booked before the plasterer but if the plasterer hasn’t been in and completed the work, the painter either wont be able to paint or wont have anything at all to paint. 
	



Q32.  [bookmark: _Ref438588]Which of the following should be considered as part of task sequencing? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Holidays
	

	
		Labour availability
	

	
		Plant availability
	




Q33.  [bookmark: _Ref422992]Order the following construction operations from 1 to 6 to form the most efficient sequence.

	Answer
	Step Number
	Steps
	
	
	1
	Excavation of footings
	

	
	3
	Floor frame
	

	
	2
	Installing brick base
	

	
	6
	Roof trusses
	

	
	4
	Set out
	

	
	5
	Wall frames
	





Q34.  [bookmark: _Ref425403]Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

	Task ID
	Task
	Preceding event
	Nodes

	A
	Make enquiries and order all materials required
	Start
	1

	B
	Wait for bricks, sand and cement to arrive
	A
	2

	C
	Clear vegetation from the site
	A
	2

	D
	Order concrete to be delivered
	A
	2

	E
	Dig the trench
	C
	4

	F
	Pour the footings
	E
	5

	G
	Footings curing time
	F
	6

	H
	Load the bricks on the site
	B
	3

	I
	Mix the mortar and lay the bricks
	H
	7

	J
	Clean rubbish from the area
	I
	8

	
	Finish
	J
	9



[image: ]
G
F
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E
I
J
D
C
B
A

	Answer
	

	



Q35.  [bookmark: _Ref425404]Name one (1) computer-based software package that may be used to prepare a project schedule.

	Answer
	Microsoft Project
	




Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence. 

[image: ]

Q36.  [bookmark: _Ref426229]What is the total time for the process if the top path is taken? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




Q37.  [bookmark: _Ref427638]What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	




Q38.  [bookmark: _Ref427870]What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		8 days
	

	
		9 days
	

	
		11 days
	





Q39.  [bookmark: _Ref432123]Describe the critical path.

	Answer
	The critical path is the shortest completion time possible to complete a job. In this case, you would use the path to nodes 2, 3 and 7.
	



Q40.  [bookmark: _Ref433763]True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

	Answer
		True 
	
	
	
		False 
	
	




Q41.  [bookmark: _Ref433133]Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

	Answer
	If materials don’t get delivered on time, if the subcontractor isn’t completing the work in time or if the budget starts to get a bit tight,
	



Q42.  [bookmark: _Ref444868]Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		If the neighbours drive the right kind of car for that neighbourhood
	

	
		Structure and condition of any boundary fences
	

	
		Type and condition of all structures on the boundary
	

	
		Whether the houses are of Victorian heritage
	




Q43.  [bookmark: _Ref444869]Why should you take photographs of site boundaries with neighbouring properties?

	Answer
	You should take photos to help support your report. It would be helpful in case the event of  dispute happens in the future.
	


Q44.  [bookmark: _Ref444874]When should a condition report be given to owners of adjacent buildings? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
		Before construction commences
	

	
		During construction
	

	
		After construction completes
	




Q45.  [bookmark: _Ref444875]When might a neighbouring property owner be required to refer to a condition report?

	Answer
	A neighbouring property owner would be required to refer to a condition report if construction is going to commence. This will ensure all parties are aware of the site status before the work commences and can easily identify if any damage has occurred through the construction process.
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Jessica Manley

	
	

	Participant signature
	
	
	

	Date
	19/04/2021



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
	
	

	Task 1 (Occasion 2)
	
	




	ASSESSOR COMMENTS

	


CPCCBC4007A
Plan building or construction work

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities:
· Occasion 1: Residential projects
· Occasion 2: Commercial projects

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· A construction program/schedule for a project showing:
· The sequencing of the trades, etc.
· Working and non-working days, etc.
· Local authority construction commencement notices
· Pre-construction site inspection reports or dilapidation reports
· WHS policy

The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document.

	Resources required: 
Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. 

	Assessment of task

	Name of participant:
	Jessica Manley

	Name of observer:
	Khyle Glover

	Role of observer 
(Confirm suitability to sign)
	Estimating Manager – Superior Group

	Email address of observer
	khyle@superiorgroup.com.au

	Signature of observer:
	
	Date:
	19/04/2021
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1 Appraise contract documentation

	1.1A.  [bookmark: _Ref536514168]Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties.
		
	1.1B.  [bookmark: _Ref536514171]Determine availability of selected subcontractors to suit the job requirements. 
		
	1.1C.  [bookmark: _Ref536514174]Assess availability of materials and confirm with suppliers. 
		
	1.1D.  [bookmark: _Ref536514176]Identify site access requirements and limitations, taking action to facilitate entry. 
		
	1.1E.  [bookmark: _Ref536514185]Prepare documentation for authorities controlling construction work and determine project commencement date. 
		
	1.1F.  [bookmark: _Ref536514189]Implement procedures for controlling and recording site deliveries. 
		
	2 Construction operation strategies 

	1.2A.  [bookmark: _Ref536514201]Identify organisational strategies for implementing construction. 
		
	1.2B.  [bookmark: _Ref536514204]Implement procedures for recording the hire of plant and equipment. 
		
	1.2C.  [bookmark: _Ref536514207]Implement organisational WHS policies and procedures, including hazard and risk management.
		
	1.2D.  [bookmark: _Ref536514211]Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements.
		
	1.2E.  [bookmark: _Ref536514215]Follow procedures for the control of multiple projects. 
		
	3 Project schedule 

	1.3A.  [bookmark: _Ref536514218]Sequence construction operations. 
		
	1.3B.  [bookmark: _Ref536514221]Enter operation details into a manually prepared project schedule or computer-based software package.
		
	1.3C.  [bookmark: _Ref536514224]Define critical path of the project, revising as required.
		
	1.3D.  [bookmark: _Ref536514227]Adjust project timeframes to account for anticipated delays.
		
	4 Required resources

	1.4A.  [bookmark: _Ref536514241]Determine and document temporary services and site accommodation requirements.
		
	1.4B.  [bookmark: _Ref536514244]Determine and document plant requirements and availability, with reference to contract documentation.
		
	1.4C.  [bookmark: _Ref536514247]Determine and document on-site labour requirements, with reference to contract documentation. 
		
	5 Condition reports

	1.5A.  [bookmark: _Ref536514251]Complete reports on the condition of existing buildings and structures on adjacent site boundaries. 
		
	1.5B.  [bookmark: _Ref536514256]Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction.
		
	1.5C.  [bookmark: _Ref536514373]Effectively communicate using the following methods:
· Telephone, facsimile, email and in writing 
· Language/concepts appropriate to cultural differences
· Non-verbal communication
		
	The Participant’s performance was:  Satisfactory     Not Satisfactory





	OBSERVER COMMENTS

	[bookmark: _GoBack]Jess has done an awesome job at navigating through residential and commercial projects, great work! - Khyle
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