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CPCCBC4005A 
Produce labour and material schedules for ordering
ASSESSMENT SUMMARY

The assessment activities for CPCCBC4005A Produce labour and material schedules for ordering cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB). 

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor. 

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result. 

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work. 


	[bookmark: _Ref396827952]Participant Name
	Matthew Cumiskey




	Task
	Assessment Results 

	Theory Exam
	 Satisfactory 
	 Not Yet Satisfactory

	Practical Assessment
	 Satisfactory 
	 Not Yet Satisfactory

	Outcome for Unit of Competency
	 Competent
	 Not Yet Competent




	Assessor Name
	

	Assessor Signature
	
	Unit Competence Determination Date
	Click here to enter a date.


Theory Exam - CPCCBC4005A Produce labour and material schedules for ordering

	Assessment Summary - CPCCBC4005A Produce labour and material schedules for ordering



Page 4 of 4	CSTC Pty Ltd_RTO#0699_v1-3_02/10/2019

CSTC Pty Ltd_RTO#0699_v1-3_02/10/2019 	Page 1 of 1 
CPCCBC4005A 
Produce labour and material schedules for ordering

	THEORY EXAM INSTRUCTIONS

· This exam will occur under standard assessment conditions.
· An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments)
· Participants must provide enough detail in their responses to demonstrate their knowledge and skills.
· Please fill in the details below, providing your name, signature and date of assessment.
· Your signature acknowledges that this is your own work.
· Assessors are to complete marking in pen of a different colour to the Participant.
· If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below:
· If a Participant changes their response in writing, they must put their initials next to the written change.
· If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.




	Participant name
	Matthew Cumiskey

	
	

	Participant signature
	
	
	

	Date
	27/05/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.




	Number of questions
	Number of questions answered correctly
	Task outcome (Tick)

	30
	
	Satisfactory
	Not Yet Satisfactory

	
	
	
	


	ASSESSOR COMMENTS

	


Q1.  Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
		Commencement date
	

	
		Completion date
	

	
		Contract price
	




Q2.  [bookmark: _Ref425159148]Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

	Answer
	Suppliers
	Contractors
	
	
	Steel
	Tilers
	

	
	Trusses
	Plumbers
	

	
	Appliances
	Electricians
	




Q3.  [bookmark: _Ref530638037]Explain the difference between employees and contractors and how they are influenced by scheduling.

	Answer
	It is important to schedule tasks, as builders will not always have employees on hand who have the specialist skills required to complete a project. 
Generally, a contractor is someone who runs their own business and provides services to other businesses or individuals. An employee works in and is part of a business.
· A builder can closely direct the work to be undertaken by an employee
· A contractor can decide what work they do, how it is to be carried out and the hours when the work is to be completed

	



Q4.  [bookmark: _Ref530484357]Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

	Answer
	Brisbane City Council
Queensland Building and Construction Commission

	



Q5.  [bookmark: _Ref530484824]Why should colour selections be included on the schedules?

	Answer
	They should be included in the schedules to avoid any possible confusion
about colour selection as change in colour selection is one of the most
common areas that can result in variations.

	


Q6.  [bookmark: _Ref530488884]True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

	Answer
	
	True 
	
	
	
	
	False 
	
	




Q7.  [bookmark: _Ref530576818]Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules. 

	Answer
	Brisbane City Councils working hours are from 6:30am to 6:30pm Monday 
to Saturday. Knowing how many working hours you have available per week
will make completing a schedule much more accurate.
	



Q8.  [bookmark: _Ref425158650][bookmark: _Ref530483834]Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

	Answer
	Drawing/Specification
	Information provided for labour and material schedules
	
	
	Plans
	Plans for the building from a bird’s eye view which 
provides all room dimensions so you can calculate 
the required quantity of certain items, for example
flooring
	

	
	Colour specification
	It includes the colour selections for interior and 
external areas 
	

	
	Product 
specification
	Include items such as whitegoods, electrical goods (light and switch types)
	



Q9.  [bookmark: _Ref530577044]What three (3) things should a builder do when variations are made to a contract for a project?

	Answer
	1. Put it in writing.
2. Client/subbies must agree to before commencement of work.
3. All subsequent documentation must be completed by the client/subbies
within 5 business days of when the variation was agreed to.

	



Q10.  [bookmark: _Ref530577045]Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

	Answer
	Variation
	Effect on schedules
	
	
	Changes to room sizes
	Depending how far progressed the
build is this may cause some time 
delays to the schedule and could 
cost the client to change 
	

	
	Style of doors and windows
	Changing the style of a window can
potentially cause a delay to the 
schedule depending on how long 
they take to be made
	




Q11.  [bookmark: _Ref530577046]Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

	Answer
	Variation
	Effect on schedules
	
	
	Needing to break rock when digging
footings
	It may increase the cost of 
excavation and may delay the
schedule
	

	
	Weather delays
	Excessive bad weather can cause a
time delay to the schedule
	



Q12.  [bookmark: _Ref530490108]Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

	Answer
	Step Number
	Steps
	
	
	1
	Builder to seek quotes from suppliers/contractors
	

	
	5
	Builder to note supplier/contractor details and ordering times on schedule
	

	
	3
	Builder to accept a tender
	

	
	2
	Suppliers/Contractors tender prices back to the builder
	

	
	4
	Parties to sign agreement
	




Q13.  [bookmark: _Ref530577300]What is an ‘overlay drawing’?

	Answer
	Overlay drawings are drawings that show further detail on top of any existing plans and specifications. Overlay drawings are generally designed to:
· Provide more visual clarity about a building process
· Provide advice if there have been changes that require subsequent engineering redesign/specialist changes (e.g.  from architects, soil experts)

	



Q14.  [bookmark: _Ref530577354]Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

	Answer
	Choice
	Possible Answers
	
	
	
	Architects
	

	
	
	Builder
	

	
	
	Draftsmen
	

	
	
	Engineers
	




Q15.  [bookmark: _Ref530577363]Identify three (3) details that should be included on a work order and reflected on the labour schedule.

	Answer
	1. Work
2. Time period
3. Agreed rates
	




Q16.  [bookmark: _Ref530635543]Identify nine (9) details that should be included on a purchase order.

	Answer
	1. Order date and delivery date
2. Purchase order number
3. Supplier details
4. Delivery details
5. Supplier contact information
6. Project manager details
7. Product description
8. Terms and conditions
9. Total order cost
	



Q17.  [bookmark: _Ref530490182]What is a ‘call forward sheet’?

	Answer
	A call forward sheet is a sheet used to track when materials are needed and
when they should be ordered.  This tool allows site personnel to schedule
and coordinate activities that are to be undertaken on-site. 

	



Q18.  [bookmark: _Ref530635574]True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

	Answer
	
	True 
	
	
	
	
	False 
	
	




Q19.  [bookmark: _Ref530635589]Identify two (2) approved plans that should be included with the site documents.

	Answer
	Architectural plans and land survey plans
	




Q20.  [bookmark: _Ref495585603]Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

	Answer
	Document
	Answers
	Definition
	
	
	1
	Permits
	1 - B
	A
	May include engineering data
	

	
	2
	Quotes
	2 - E
	B
	Council inspectors may issue a stop work notice until these documents are produced
	

	
	3
	Reports
	3 - A
	C
	Changes requested using a standard form in writing. Need to be signed by both builder and client.
	

	
	4
	Specifications
	4 - D
	D
	List the materials to be used, fittings and fixtures to be installed, and types of finishing required. 
	

	
	5
	Variations
	5 - C
	E
	Used to ensure purchase orders are developed using the correct price.
	




Q21.  [bookmark: _Ref530635990]In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

	Answer
	Trade
	Estimate
	Actual cost
	Cost difference
	
	
	Carpentry
	10,000
	8,500
	-1,500
	

	
	Electrical
	3,000
	4,250
	1,250
	

	
	Painting
	4,000
	3,900
	-100
	

	
	Plumbing
	8,000
	8,000
	0
	

	
	Tiler
	4,500
	4,750
	250
	




Q22.  [bookmark: _Ref530635991]In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

	Answer
	Item
	PC sum
	Actual cost
	Cost difference
	
	
	Basin taps
	100
	130
	30
	

	
	Oven
	2,500
	1,500
	-1000
	

	
	Rangehood
	500
	900
	400
	

	
	Shower bases
	250
	265
	15
	

	
	Shower screen
	400
	350
	-50
	

	
	Shower taps
	150
	120
	-30
	

	
	Stove
	900
	1,200
	300
	



Q23.  [bookmark: _Ref530636949]Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Builder
	

	
	
	Client
	

	
	
	Supplier
	




Q24.  [bookmark: _Ref530636951]Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Builder
	

	
	
	Client
	

	
	
	Supplier
	




Q25.  [bookmark: _Ref530636962]You are given the following table containing the costs for each month of the project. 

	Month
	Estimated cost
	Actual cost

	March
	$36,450
	$38,980

	April
	$65,560
	$62,350

	May
	$62,450
	$64,960

	June
	$61,340
	$61,050

	July
	$40,590
	$38,990

	August
	$42,650
	$42,550

	September
	$35,780
	$34,750

	Total
	$344,820
	$343,630



Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Plot both the estimated and actual costs on a graph
	

	
	
	Plot the actual cost on a graph
	

	
	
	Work out the difference between the estimated and actual costs
	



Q26.  [bookmark: _Ref530636963]The following graph is a visual representation of the difference in each month. 
[image: ]

By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	No, you cannot see this directly from the graph
	

	
	
	Yes, you can see this from the graph
	




Q27.  [bookmark: _Ref530636964]The following graph is a visual representation of the accumulated difference across the project. 
[image: ]

Overall, was the project overestimated or underestimated? 
Tick your response.

	Answer
	Choice
	Possible Answers
	
	
	
	Overestimated
	

	
	
	Underestimated
	



Refer to the following scenario and house plan to respond to Q28. to Q30. 

SCENARIO

You are a site supervisor of a small residential project, as outlined below:
The building is to be constructed using brick veneer.
The building has a floor area of 133 square metres including garage.
The concrete slab floor with garage floor is incorporated.
The building will be constructed using hand built wall frame and prefabricated roof trusses.
The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.
The driveway and landscaping are to be provided.
Services are available directly in front of the site.
The site is almost flat and will only need a scrape with minimal excavation.
The contract period is 120 days.
The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.



[image: Plan of a house  single storey 3-bedroom residence with garage]
Q28.  [bookmark: _Ref530639450]Using the list of materials prepared, find the following information for four (4) materials of your choice:

	Answer
	Material
	Lead-in time
	Delivery date
	Order date
	Delivery requirements/ special considerations
	
	
	Concrete
	7 days
	1/7/2020
	24/6/2020
	Make sure 
weather 
forecast is 
good for the 
day of the pour
	

	
	Timber for 
framing
	7 days
	1/9/2020
	25/8/2020
	Make sure part
of the site is 
clear to 
accept the 
delivery
	

	
	Roof trusses
	2 weeks
	8/9/2020
	25/8/2020
	Organise a 
crane for the 
same day to 
lift trusses 
straight up on 
top of frames
	

	
	Windows
	8 weeks
	10/9/2020
	16/7/2020
	Make sure 
someone is on
site that day to
accept the 
delivery
	




Q29.  [bookmark: _Ref530641000]Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

	Answer
	Material
	Ordering process
	Considerations
	
	
	External cladding
	Calculate how much you
require and complete a 
purchase order
	Allow an extra 10% to cover
any waste there may be
	

	
	Wall frame
	Refer to your schedule to
figure out when you will
require the wall frames, get
in contact with the supplier 
and complete a purchase
order
	Make sure the site is clean
on the day of delivery so the 
truck and drive the frames
all the way up to the slab
	

	
	Windows
	Refer to your schedule to 
figure out when you will
require your windows, get
in contact with the supplier,
complete a purchase order
	Lead time for windows can 
be anywhere from 4 to 8 
weeks, so make sure you 
are on top of your schedule
	



Q30.  [bookmark: _Ref530640532]While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client. 

	Answer
	Please refer to attached file called NHC Form 5 (2)
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	PRACTICAL ASSESSMENT INSTRUCTIONS

· The following practical assessment will require the Participant to complete work related activities.
· The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. 
· Please fill in the details below – providing your name, signature and date of assessment.
· The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment.
· The Assessor may substitute a Practical Task with an alternate task of equal value.
· Alternate tasks must be fully documented by the assessor in the Assessor Comments area.





	Participant name
	Matt Cumiskey

	
	

	Participant signature
	
	
	

	Date
	8/06/2020



	Assessor name
	

	
	

	Assessor signature
	
	
	

	Date
	Click here to enter a date.





	Task
	Task outcome (Tick)

	
	Satisfactory
	Not Yet Satisfactory

	Task 1 (Occasion 1)
		
	Task 1 (Occasion 2)
		



	ASSESSOR COMMENTS

	


CPCCBC4005A
Produce labour and material schedules for ordering

	Practical Task 1 (2X)

	Description of task:
On two (2) occasions, a suitable observer is to verify the participant’s ability to produce schedules of resource requirements so that orders can be placed for materials and labour for projects, and costs can be recorded and tracked as they are incurred. 
· Occasion 1: Residential project
· Occasion 2: Commercial project

The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: 
· A copy of a material/labour schedule or supplier list for a project 
· A copy of a purchase order for purchasing materials or other resources 
· A cost report 
· Site condition reports or dilapidation reports 
· Contract documents 
· Call forward sheets 
· Variations

The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document.

	Resources required: 
Contract documentation (including plans and specifications), computer.

	Assessment of task

	Name of participant:
	Matthew Cumiskey

	Name of observer:
	

	Role of observer 
(Confirm suitability to sign)
	

	Email address of observer
	

	Signature of observer:
	
	Date:
	Click here to enter a date.
	When completing the task, did the participant:
	Tick if satisfactorily completed. 
Provide comments if left unticked.

	
	1st
Occasion
	2nd
Occasion

	1.A.  [bookmark: _Ref530477477]Consider all contract conditions in the schedules, including:
· All contractual requirements
· Local government and regulatory bodies’ conditions of approval
· Colour selections
· Variations to contracts, raised by the client or builder
		
	1.B.  [bookmark: _Ref530477488]Produce material and labour schedules, including:
· Details of nominated suppliers and contractors in work schedules
1) Application of contract rates 
		
	1.C.  [bookmark: _Ref530477495]Produce relevant overlay drawings.
		
	1.D.  [bookmark: _Ref530477499]Include contract details and instructions on orders. 
		
	1.E.  [bookmark: _Ref530477502]Prepare site files, including:
· All necessary site documents, including plans and specifications
· Preparation of call forward sheets, detailing all orders
		
	1.F.  [bookmark: _Ref530477506]Analyse project costs against estimates during construction.
		
	1.G.  [bookmark: _Ref530477509]Analyse approved variation costs.
		
	1.H.  [bookmark: _Ref530477512]Provide a final project cost analysis.
		
	1.I.  [bookmark: _Ref530477522]Maintain data files of standard costs, including:
· Approved variation cost increases
· Changes to standard plans, specifications, and cost files
		
	1.J.  [bookmark: _Ref530479080]Effectively communicate using the following methods:
· Verbally using language/concepts appropriate to cultural differences
· Non-verbal communication
		
	The Participant’s performance was:  Satisfactory     Not Satisfactory



	OBSERVER COMMENTS
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